## Slide 1: MARS Taskforce
COPS Update August 11, 2009
Notes: <number>

## Slide 2: July 30, 2009 MARS Taskforce Meeting
Discussed changes needed to ERCOT’s process to support 15-minute AMS load/generation data, such as:
    New DDL(s)
    Reports
    Extracts
    Web Services
  Action Item: Jackie Ashbaugh will provide Settlement and Extract Working Group (SEWG) with an update on the changes being created to support 15 minute Settlement for AMS meters.
Discussed DRAFT 814_20 Transaction Schedule to support high volumes of AMS Load Profile and Meter changes.
  MARS Taskforce will continue that discussion during the August 11th meeting following COPS.
Reviewed project status report that includes milestones and critical dates (slide 3).
Reviewed a timeline of events that was developed by ERCOT for Market Participants to understand the sequence in which transactions must be accepted and posted at ERCOT for Load Profile changes prior to sending usage/generation data (slide 4)
<number>
Notes: <number>

## Slide 3
Execution Milestones | Baseline Date | Status
Technical Architecture Complete | 05/15/2009 | Completed
Development Complete | 07/24/2009 | Completed
Detailed Designs Complete | 08/11/2009 | On Schedule
pTest Complete | 08/11/2009 | Tracking ~1 week behind but expected to recover and complete by baseline date
iTest Complete | 11/06/2009 | On Schedule
Market Test Complete | 11/06/2009 | On Schedule
Go Live | 11/14/2009 (off-cycle) | On Schedule
Go Live (Contingency Date) | 12/12/2009 | 
Stabilization Complete | 03/19/2010 | 
Project Complete | 05/21/2010 | 
ERCOT’s AMS Project
7/30/09 Status Report
2
Notes: <number>

## Slide 4
<number>
Timeline of Events
AMS 15-Min. Settlement
Notes: <number>

## Slide 5: July 30, 2009 MARS Taskforce Meeting
Discussed with the high volume of 814_20s expected by end of year there isn’t enough time to have all or a majority of the Load Profile changes successfully posted at ERCOT and for TDSPs to follow-up with the usage/generation LSE files for those premises to be loaded at ERCOT for initial settlement, therefore our goal as a Market could be to have the backlogged 814_20s along with usage/generation LSE files posted at ERCOT no later than final settlement.
This would mean:
  If the TDSPs waited to change the Load Profiles for AMS meters after initial settlement, TDSPs would have 47 days to complete all 814_20 Load Profile backlogs for AMS meters and provide LSE files with usage/generation to ERCOT for loading before final settlement or
  If the Load Profile was changed prior to initial settlement and LSE file with usage/generation had not loaded at ERCOT, then the premise would be settled according to the default profile for initial settlement.
    Load Profile change required for AMS Provision Meters “Meter Data Type Code changes to IDR and the Weather Sensitivity Code changes to WS”
      Note Load Profile contains the following:
        Profile Group and Segment Code, Weather Zone Code, Meter Data Type Code, Weather Sensitivity Code, TOU Schedule Code.
<number>
Notes: <number>

## Slide 6: Next Steps for MARS
Next meeting Tuesday , August 11, 2009
  Continue to refine and finalize 814_20 high volume transaction plan to change Load Profile assignment for AMS meters and manage 814_20 routine business.
    Currently draft plan includes Oncor and CenterPoint Energy’s AMS deployment schedules
  Create a detailed document of the changes required to SCR740 Web Services, DDLs, Data Extracts and Reports to support 15-minute Settlement of AMS meters
    Meet with SEWG to keep them updated on these changes and final of state.
Continue to update RMS and COPS on the progress of Project 80027 Market Interim Settlement Solution for AMS meters.
<number>
Notes: <number>

## Slide 7: Questions?
<number>
Notes: <number>