## Guidelines
Rules for Submission of Large Volume of Transactions
Block out all maintenance and release windows
Block out ERCOT holidays
Block out Tuesday or Wednesday, if possible.
Rate of Submission:
During the week
Prior to 5 PM
Submit transactions at a rate of once an hour
In bundles that are no more than 33,000 transactions at a time
OR
After 5 PM
No restrictions as to rate or number of transactions
On weekends
No restrictions as to rate or number of transactions
Updates:
I moved out the first day of sending 814_20s to the Tuesday after implementation.
Blocked the Wednesday of that week.
Moved Oncor's numbers out and added 5,500 814_20s to each day in schedule for the meter change.
Original schedule - Oncor dropped to maintenance levels on December 17th
New schedule - Oncor drops to maintenance levels on January 4th
Extends schedule about 2 weeks

## Draft Timeline
| November |  |  |  |  | December |  |  |  |  | January
|  | Max # | Oncor | CenterPoint | Remaining |  | Max # | Oncor | CenterPoint | Remaining |  | Max # | Oncor | CenterPoint | Remaining
Tues | 3 |  |  |  |  | 1
Wed | 4 |  |  |  |  | 2 | 60000 | 29786 |  | 30214
Thurs | 5 |  |  |  |  | 3 | 60000 | 29786 |  | 30214
Fri | 6 |  |  |  |  | 4 | 60000 | 29786 |  | 30214 | 1 | New Year's Weekend
Sat | 7 |  |  |  |  | 5 | 100000 |  |  | 100000 | 2
Sun | 8 |  |  |  |  | 6 |  |  |  |  | 3
Mon | 9 |  |  |  |  | 7 | 60000 | 35786 |  | 24214 | 4 | 60000 | 11000 |  | 49000
Tues | 10 |  |  |  |  | 8 |  |  |  |  | 5
Wed | 11 |  |  |  |  | 9 | 60000 | 35786 |  | 24214 | 6 | 60000 | 11000 |  | 49000
Thurs | 12 |  |  |  |  | 10 | 60000 | 35786 |  | 24214 | 7 | 60000 | 11000 |  | 49000
Fri | 13 |  |  |  |  | 11 | 60000 | 35786 |  | 24214 | 8 | 60000 | 11000 |  | 49000
Sat | 14 | PR80027 Go Live |  |  |  | 12 | December Retail Release |  |  |  | 9 | 100000 |  |  | 100000
Sun | 15 |  |  |  |  | 13 |  |  |  |  | 10
Mon | 16 |  |  |  |  | 14 | 60000 | 29786 |  | 30214 | 11 | 60000 | 11000 |  | 49000
Tues | 17 | 60000 | 29786 |  | 30214 | 15 |  |  |  |  | 12
Wed | 18 |  |  |  |  | 16 | 60000 | 35786 |  | 24214 | 13 | 60000 | 11000 |  | 49000
Thurs | 19 | 60000 | 29786 |  | 30214 | 17 | 60000 | 35786 |  | 24214 | 14 | 60000 | 11000 |  | 49000
Fri | 20 | 60000 | 29786 |  | 30214 | 18 | 60000 | 32786 |  | 27214 | 15 | 60000 | 11000 |  | 49000
Sat | 21 | 100000 |  |  | 100000 | 19 | 100000 |  |  | 100000 | 16 | 100000 |  |  | 100000
Sun | 22 |  |  |  |  | 20 |  |  |  |  | 17
Mon | 23 | 60000 | 29786 |  | 30214 | 21 | 60000 | 32786 |  | 27214 | 18 | 60000 | 11000 |  | 49000
Tues | 24 |  |  |  |  | 22 |  |  |  |  | 19
Wed | 25 | 60000 | 29786 |  | 30214 | 23 | 60000 | 32786 |  | 27214 | 20 | 60000 | 11000 |  | 49000
Thurs | 26 | Thanksgiving Weekend |  |  |  | 24 | Christmas Weekend |  |  |  | 21 | 60000 | 11000 |  | 49000
Fri | 27 |  |  |  |  | 25 |  |  |  |  | 22 | 60000 | 11000 |  | 49000
Sat | 28 |  |  |  |  | 26 |  |  |  |  | 23 | January Retail Release
Sun | 29 |  |  |  |  | 27 |  |  |  |  | 24
Mon | 30 | 60000 | 29786 |  | 30214 | 28 |  |  |  |  | 25 | 60000 | 11000 |  | 60000
Tues | [5 empty] | 29 |  |  |  |  | 26
Wed | [5 empty] | 30 | 60000 | 32786 |  | 27214 | 27 | 60000 | 11000 |  | 60000
Thurs | [5 empty] | 31 | 60000 | 32786 |  | 27214 | 28 | 60000 | 10000 |  | 60000