## Slide 1: Single Entry Model (SEM) Go-Live Update
http://nodal.ercot.com <number>
ROS Update
August 13, 2009

## Slide 2: SEM Go-Live
http://nodal.ercot.com <number>
Summary of current SEM activities
Market engagement summary
ERCOT and Market Criteria Status for Go-Live Aug 31, 2009
Market Readiness Criteria approval process
Appendix
  What is SEM Go-Live?
  Market Engagement/Communications
  Training Update
  Transition summary during June – August 2009
  Next steps

## Slide 3: Summary of current SEM Activities
http://nodal.ercot.com <number>
Market/TSP engagement calendar for Single Entry Model Implementation
  May 28- SEM Market Kick-off Call
  June 4- Began weekly ERCOT/TSP market calls for SEM
  June 8- ERCOT deployed test system for TSP testing on schedule
  June 23- Training commenced on schedule 6-weeks of 3-day classes
  July 30- Training complete
  We are here - August stakeholder meetings
  August 31- SEM Go-Live milestone
Stakeholder communications
  ERCOT has reported detailed progress on testing and training to market on SEM Weekly calls, NDSWG/ROS, NATF, and TAC
ERCOT activity highlights
  On-going support of testing/questions/weekly-calls
  Converted final copy of 6/1/2009 of zonal operations model into nodal model
  Confirmed consumption of model into NMMS/EMS/MMS test systems
  Nodal integration testing aligned to use post-SEM Go-Live model

## Slide 4
http://nodal.ercot.com <number>
SEM Go-Live Market Engagement Dashboard (as of 8/11/2009)

## Slide 5: Market engagement summary (continued)
http://nodal.ercot.com <number>
Excellent TSP engagement over the summer
  12 weeks of market calls (calls to continue through go-live)
  10 weeks of ad-hoc system testing by TSPs
  6 weeks of instructor led training for 19 different TSPs is complete
  No severity 1 or 2 defects identified by the market
  All 20 TSPs engaged that will be responsible for ERCOT network modeling
  Working with one TSP to catch-up on training
    TSP has signed up for Sept 29th training make-up class after SEM Go-Live
    ERCOT will support this TSP (and any other TSP) with coordinating submission of NOMCRs

## Slide 6: Overall SEM Go-Live ERCOT/Market Criteria Dashboard
Summary of Criteria from TAC-approved SEM Go-Live Procedure (http://nodal.ercot.com/readiness/golive/index.html )

## Slide 7: August implementation activity summary
http://nodal.ercot.com <number>
Engagement has shifted gears from training to cut-over activities:
  TSP coordination for access to production systems with digital certificates
    Aug 10th ERCOT sent instructions & “potential user” list sent to TSP USA administrators
  ERCOT completing analysis and posting of key artifacts/analysis
    Modeling Guidelines final review at NDSWG last week, blackline to post Aug 14
      Work through 500+ comments to 3 issues (discussed at last ROS meeting)
      Aug 4th NDSWG had special meeting for discussion of workarounds related to MVA measurement, Limits, Owner/Operator for SEM Go-Live
    Wrapping up analysis of CIM Audit, Consistency Check, Rules Validation
      Methodology provided to NDSWG July 14th, analysis/sign-off to be delivered July 17th
    Posting of CIM schema and data dictionary complete
  ERCOT to continue to test systems and ensure Service Level Agreements met
    99.9% availability of system
    4 hour recovery time
    Support 25 concurrent modeling users
    Stress testing to continue focus on system performance
  July 31 Market Notice sent reminding TSPs that no modeling Service Requests should be submitted after Aug 15 to allow synchronization of models
    Emergency modeling changes will be accepted with approval from Director of Grid Operations

## Slide 8
SEM Go-Live Approval of Market Readiness Criteria (TAC and Board)
http://nodal.ercot.com <number>

## Slide 9: SEM Go-Live Criteria and Approval (TAC and Board)
http://nodal.ercot.com <number>
Summary of remaining Stakeholder meeting dates for SEM discussion/approval of Go-Live
  August
    30-day Market Notice - sent July 31st
    NDSWG special meeting Aug 4th
    TAC met Aug 6th, deferred approval consideration to special TAC on Aug 18th
    ROS meeting Aug 13th
    ERCOT publishes results and sign-off from Directors on Aug 17th
    TAC special meeting- Aug 18th 7:30am
    BOD - Aug 18th
    10-day Market Notice - Aug 21st
    SEM Go-Live - Aug 31st
  Consideration of whether “Certification that all Market Readiness Criteria have been met”
    All training complete, and plans in place to support one TSP
    Remaining activities are for ERCOT to complete/sign-off model analysis
    Note that no protocol changes go into effect Aug 31 (system change only)

## Slide 10
http://nodal.ercot.com <number>
  APPENDIX
  What is SEM Go-Live?
  Training Update
  Transition summary during June – August 2009

## Slide 11: SEM Go-Live Overview
http://nodal.ercot.com <number>
Single Entry Model (SEM) Go-Live is the switchover on Aug 31, 2009 for TSP submissions of network operations model change requests
  from “Service Request” submissions via TML
  to “NOMCR” submissions via the NMMS
    System of record for model changes becomes NOMCRs on 8/31//09
    System of record for Network operations Model for reliability and dispatch remains Zonal/Genesys system until Dec 2010
TSP
Current Activity
Submit Modeling
Change via Service Request
ERCOT Uploads
Svc Request
into Zonal
Genesys Model
ERCOT Copies/Converts
Zonal Model “seed”
Into Nodal
NMMS Model
TSP
Aug 31, 2009
Submit Modeling Change via
NOMCR/NMMS Tool
(includes ICCP)
ERCOT Incrementally
Converts NOMCR
Into Svc Req
Uploads into Zonal
Genesys Model
ERCOT uploads
NOMCR
Into Nodal
NMMS Model to
support nodal testing
Data Consistency Checks are run to
ensure model synchronization/fidelity
Periodic checks are run to
ensure model synchronization/fidelity
Full
Copy
Incr.
NOMCR

## Slide 12: Current Network Operations Model Maintenance for TSPs
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
Submits Service Request to Change Model
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
Periodic full copy and conversion of model
(zonal seed used for nodal systems)
TSP
Notes: <number>
<number>

## Slide 13: After 8/31/2009: SEM Go-Live Network Operations Model Maintenance for TSP
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
ERCOT enters NOMCRs into zonal model
ERCOT runs consistency checks to ensure models are aligned and maintained
Submits Model Change Request (NOMCR)
TSP
NMMS Model
System of Record
Nodal Go-Live 12/1/2010
Notes: <number>
<number>

## Slide 14: Network Operations Model Maintenance for Resource & QSE (today and post 8/31/09)
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
ERCOT enters into zonal model
NMMS Model
System of Record
Nodal Go-Live 12/1/2010
Submits RARF
(Resource Asset Reg Form)
via Service Request
Submits ICCP Change
via Service Request
ERCOT process
QSE
RE
Notes: <number>
<number>

## Slide 15: Training Update
http://nodal.ercot.com <number>
TSP Testing and Training environments will be the same
Testing system access
  Available June 8 – Aug 10
  NOMCR testing system will be on-line and available to all TSPs
  ERCOT will established dedicated email and have staff available to support questions (nomcrhelp@ercot.com)
Instructor Led Training to be hosted in Taylor
  Pre-SEM classes June 22 – Aug 3
    Current plans for at least six 3-day sessions
    Planning for 12-18 seats for each class
    Large dedicated training room
  Post-SEM classes Sept 23- Oct 20
    Fewer sessions and smaller classes (tbd)
    Make-up classes, not just-in-time training for all staff after go-live

## Slide 16: Transition summary during June-Aug’09
http://nodal.ercot.com <number>
  Currently no limits on submissions (Market Notice sent March 5)
    “… to clarify that there are no restrictions or “freezes” currently in place limiting network model change submissions via the service request process.”
  Transition periods:
    June 1- Aug 30, 2009 (objective to minimize SvcReq during this period)
      No equipment name changes (defer until after SEM Go-Live 8/31/09)
      Submit changes as far in advance as possible
    Aug 15-30, 2009
      Two weeks no submissions, except for emergency changes
    Aug 31, 2009 - Feb 2010 (NOMCRs for any/all network changes)
      Initially the NOMCR timeline will align with zonal timeline
        NOMCRs received and translated to zonal model change
        30-day lead-time, compliant with current zonal database schedule
        Status is tracked and communicated via system emails
      SRs that did not go into zonal production will be converted to NOMCRs for verification and submission by TSPs in Sept
      TSP gradually transitions to NodalProtocols(3.10) 90-day reqts