## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
August 25, 2009

## Slide 2: PMO Update - Agenda
  2010 Project Prioritization
    Approval Update
  2009 Project Spending Forecast
    As of 8/18/2009
  Recent Project Implementations
    July 2009

## Slide 3: Revised 2010 Project Prioritization Schedule
April 2009
  CARTs develop draft 2010 project lists
May 2009
  Initial review at Market Subcommittee meetings
    MO - COPS (May 12)
    RO - RMS (May 13)
    SO - ROS, WMS (May 14 / May 20)
June 2009
  Approval by market subcommittees
    MO - COPS (June 9)
    RO - RMS (June 10)
    SO - ROS, WMS (June 11 / June 17)
July 2009
  Approval by PRS
    CO, IO, MO, RO, SO (July 23)
August 2009
  Approval by TAC (August 6)
September 2009
  Available for F&A and Board review (September 20)

## Slide 4: 2010 Project Priority List / Funding Level Review
2010 Project Prioritization – Introductory Comments
  Nodal delivery is the focus of the organization next year
  Zonal projects are limited to:
    Critical projects
    Completion of projects already executing
    Records management project
  On May 1, 2010, production and testing environments will be locked down to reduce risk during the months preceding Nodal implementation
  Resource constraints between other efforts and Nodal must be limited as much as possible
  No “Capability” line projected in 2010 due to multiple constraints
One project added by TAC on 8/6/2009
  PRR805 – Add AMS Meter Flag to Database Query Function on MIS
  $50k Retail Operations project
  Priority “2-High”, Rank 23.5 (immediately above the cutline)

## Slide 5: 2010 Project Priority List / Funding Level Review
2010 Project Budgets and Project Counts by Program Area
Program Area | Budget Request | Projects Started in 2008/2009 | New 2010 Projects
CO | $ 1,150,000 | 3 | 2
IO | $ 1,450,000 | 0 | 3
MO | $ 1,500,000 | 1 | 0
RO | $ 1,900,000 | 3 | 1
SO | $ 150,000 | 2 | 0
Subtotal | $ 6,150,000 | 9 | 6
Met Center (CO) | $ 31,900,000 | 1 | 0
Data Center Refresh (IO) | $ 7,500,000 | 0 | 6
Minor Cap (CO) | $ 750,000 | 0 | 1
Grand Total | $ 46,300,000 | 10 | 13
Changes highlighted in yellow

## Slide 6: 2010 Project Priority List / Funding Level Review
Program Area | 2010 Budget Request | 2009 F | 2008 A | 2007 A | 2006 A
CO | $ 1,150 | $ 1,721 | $ 4,092 | $ 5,409 | $ 3,612
IO | $ 1,450 | $ 2,809 | $ 4,609 | $ 6,701 | $ 7,261
MO | $ 1,500 | $ 778 | $ 1,194 | $ 1,008 | $ 2,281
RO | $ 1,900 | $ 3,992 | $ 2,622 | $ 3,257 | $ 5,648
SO | $ 150 | $ 987 | $ 922 | $ 2,855 | $ 5,074
Subtotal | $ 6,150 | $ 10,287 | $ 13,439 | $ 19,230 | $ 23,876
Met Center | $ 31,900 | $ 20,000 | $ 1,113 | $ 0 | $ 0
DC Refresh | $ 7,500 | $ 6,152 | $ 0 | $ 0 | $ 0
Minor Cap | $ 750 | $ 893 | $ 1,334 | $ 1,895 | $ 1,308
Nodal Interdependent | $ 0 | $ 0 | $ 6,715 | $ 21,745 | $ 9,281
Total | $ 46,300 | $ 37,332 | $ 22,601 | $ 42,870 | $ 34,465
Previous Year Forecast (F) / Actuals (A) (in thousands)
Changes highlighted in yellow

## Slide 7: 2009 Project Spending Update – 8/19/2009
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 1,145,000 | $ 2,092,134 | $ 2,675,993
IO | $ 4,995,000 | $ 2,791,000 | $ 2,761,658
MO | $ 520,000 | $ 520,000 | $ 489,832
RO | $ 3,390,000 | $ 4,092,982 | $ 3,895,053
SO | $ 1,350,000 | $ 1,350,000 | $ 833,919
Released but Not Yet Reallocated | $ 0 | $ 153,884 | $ 0
Subtotal | $ 11,400,000 | $ 11,000,000 | $ 10,656,455
Met Center Replacement | $ 20,000,000 | $ 20,000,000 | $ 20,480,088
Data Center Expansion | $ 6,750,000 | $ 6,200,000 | $ 6,198,310
Grand Total | $ 38,150,000 | $ 37,200,000 | $ 37,334,583
Adjustments in project forecasts
Adj. to Reduce Total 2009 Spend
Funding for POLR & Expedited Switch

## Slide 8: PMO Update - YTD 2009 Project Implementations
January 2009
  RO PR-70007_01 MarkeTrak Enhancements (SCR749)
  CO PR-80003_01 Employee Performance Management
  CO PR-80038_01 ACL Audit Exchange
  CO PR-80036_01 ERCOT / TRE Accounting Structure
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0217/20090217_FA_Meeting_Materials.pdf (p. 83)
February 2009
  CO PR-60058_01 Microsoft Project Server Upgrade
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0317/20090317_FA_Meeting_Materials.pdf (p. 44)
March 2009
  CO PR-70046_01 SEM Enhancement
  IO PR-80026_01 Enterprise Visibility
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0422/20090422_FA_Meeting_Materials.pdf (p. 69)

## Slide 9: PMO Update - YTD 2009 Project Implementations
April 2009
  None
May 2009
  CO PR-80016_01 Security Configuration Management
  RO PR-80040_01 TIBCO Siebel Integration Enhancements
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0616/20090616_FA_Meeting_Materials.pdf (p. 25)
June 2009
  IO PR-80044_01 Tape Hardware Backup Replacement
    Replacement of aging tape backup system
    Enhanced speed and capacity; power and space reduction in data center
  SO PR-90022_01 Zonal AWS Wind Gen Forecast for QSEs
    SCR754 / PRR763
    Replace ERCOT email delivery of AWS forecast to QSEs with a more secure and programmatic mechanism

## Slide 10: PMO Update - YTD 2009 Project Implementations
July 2009
  CO PR-70034_01 Vendor Contract Information Database Enhancements
    Phase 2 of an effort to allow better management and reporting of vendor contracts by ERCOT’s Legal Department
  CO PR-80042_01 Cyber-Security Project
    Upgrade and enhance ERCOT cyber-security capability
  CO PR-90023_01 Single Time Entry
    Eliminate dual entry of project time reporting into project management system and time reporting system