| PRR Number | 805 | PRR Title | Adding POLR Customer Class and AMS Meter Flag to the Database Query Function on the MIS |
| --- | --- | --- | --- |
| Impact Analysis Date |  | August 5, 2009 |  |
| Cost/Budgetary Impact |  | $50k to $100k |  |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. |  | The requirements of this Protocol Revision Request (PRR) will be completed as a project. The estimated time requirement for completion of the project is two to three months. Constraints impacting project delivery: - AMIT project (PR-80027) completes in late 2009. - Resource constraints prevent ERCOT from working on AMIT and this project simultaneously. - Nodal market trials begin in February 2010. - Resource constraints increase at this time. - ERCOT freezes environments on May 1, 2010 in preparation for Nodal go-live. As a result of these factors, the project for PRR805 must begin in early 2010 and complete prior to the environment freeze on May 1, 2010. |  |
| ERCOT Staffing Impacts (across all areas) |  | No additional full-time equivalents (FTEs) needed. However, resources involved in implementing PRR805 are actively engaged in the Nodal project. Using these resources to support both PRR805 and the Nodal project poses a risk to the Nodal program. Extensive coordination would be required between the business owners, Enterprise Integration, Web Services, Enterprise Information Services (EIS) and Release Management during market trials. Implementing PRR805 in early 2010 also poses other significant challenges as development staff will be busy with Nodal and will be competing for test environments during that time. |  |
| ERCOT Computer System Impacts |  | PRR805 would require a multi-system release to change the three separate components that provide the Advanced Metering System (AMS) meter flag information: - Find ESIID lookup function on the Market Information System (MIS) - TDSP ESIID Extract - Retail API (Application Programming Interface) ERCOT believes that all three elements above must be changed to ensure proper synchronization of data from these three sources. The following ERCOT systems would be impacted by this PRR: - Texas Market Link (TML) (Retail Application) - Information Services Master (ISM) - TIBCO - Web Services - EIS - Retail API |  |
| ERCOT Business Function Impacts |  | No impact to existing business processes. |  |
| Grid Operations & Practices Impacts |  | None. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

Implement PRR805 after the Texas Nodal Market Implementation Date.

Evaluation of Interim Solutions (e.g., manual workarounds)

The required data is currently made available by the TDSPs in various formats (PDF, XLS, TXT) on various schedules (weekly, monthly, etc.)

Feasibility of Implementation

Impact on Resource Availability: Impact on Other Projects: (See notes above)

Comments

If the project for PRR805 is initiated in early 2010, there is a risk that resource constraints with Nodal market trials will cause the project effort to be put on hold until after the Texas Nodal Market Implementation Date. Provider of Last Resort (POLR) Customer Class is already available so that portion of this PRR has no cost, schedule, or resource impacts.