## Slide 1: MARS Taskforce
COPS Update September 8, 2009
Notes: <number>

## Slide 2: August 11, 2009 MARS Taskforce Meeting
Discussed changes needed to ERCOT’s process to support 15-minute AMS load and DRG, such as:
    New DDL(s)
    Reports
    Extracts
    Web Services
    User Guides
  ERCOT provided updated Power Point document outlining the numerous changes
    Draft documents will be posted to MARS web page 9/2009
  Action Item:
    ERCOT (Jackie Ashbaugh) will provide the Settlement and Extract Working Group (SEWG) with an update on the changes being created to support 15 minute Settlement for AMS meters.
Discussed DRAFT 814_20 Transaction Schedule to support high volumes of AMS Load Profile and Meter changes.
  Action Item: CenterPoint Energy will add their numbers to the AMS 814_20 transaction schedule
<number>
Notes: <number>

## Slide 3
Execution Milestones | Baseline Date | Status
Technical Architecture Complete | 05/15/2009 | Completed
Development Complete | 07/24/2009 | Completed
Detailed Designs Complete | 08/11/2009 | Completed
pTest Complete | 08/11/2009 | Completed
iTest Complete | 11/06/2009 | On Schedule
Market Test Complete | 11/06/2009 | On Schedule
Go Live | 11/14/2009 (off-cycle) | On Schedule
Go Live (Contingency Date) | 12/12/2009 | 
Stabilization Complete | 03/19/2010 | 
Project Complete | 05/21/2010 | 
ERCOT’s AMS Project
8/11/09 Status Report
2
Notes: <number>

## Slide 4
<number>
Timeline of Events
AMS 15-Min. Settlement
Notes: <number>

## Slide 5: August 11, 2009 MARS Taskforce Meeting
Discussed with the high volume of 814_20s expected by end of year there isn’t enough time to have all or a majority of the Load Profile changes successfully posted at ERCOT and for TDSPs to follow-up with the usage and DRG data in the LSE files for those ESI IDs to be loaded at ERCOT for initial settlement, therefore our goal as a Market could be to have the backlogged 814_20s along with usage/ DRG LSE files posted at ERCOT no later than final settlement.
This would mean:
  If the TDSPs waited to change the Load Profiles for AMS meters after initial settlement, TDSPs would have 47 days to complete all 814_20 Load Profile backlogs for AMS meters and provide LSE files with usage/DRG to ERCOT for loading before final settlement or
  If the Load Profile was changed prior to initial settlement and LSE file with usage/DRG had not loaded at ERCOT, then the premise would be settled according to the scaled default profile for initial settlement.
    Load Profile change required for AMS Provision Meters “Meter Data Type Code changes to IDR, the Weather Sensitivity Code changes to WS, and TOU, since TOU is no longer applicable”
      Note Load Profile contains the following:
        Profile Group and Segment Code, Weather Zone Code, Meter Data Type Code, Weather Sensitivity Code, TOU Schedule Code.
<number>
Notes: <number>

## Slide 6: Next Steps for MARS
Next meeting is scheduled on September 30, 2009 at ERCOT Met Center Conference RM 168.
Continue to refine and finalize 814_20 high volume transaction plan to change Load Profile assignment for AMS meters and still manage then 814_20 routine business.
    Currently draft plan will include Oncor and CenterPoint Energy’s AMS deployment schedules. Additional TDSPs will be added as their settlement plans are approved by the PUCT.
Provide Draft detailed document of the changes required to SCR740 Web Services, DDLs, Data Extracts, User Guides, and Reports to support 15-minute Settlement of AMS meters to the MARS Taskforce listserv and post to MARS Taskforce Website no later than September 2009
    Meet with SEWG to keep them updated on these changes and of the final state of web services, extracts, reports, user guides, and DDLs.
Continue to update RMS and COPS on the progress of Project 80027 Market Interim Settlement Solution for AMS meters.
<number>
Notes: <number>

## Slide 7: Questions?
<number>
Notes: <number>