## Slide 1: Nodal Program Update
Mike Cleary
Sr. VP and Chief Technology Officer
Technical Advisory Committee
3 September 2009
Notes: <number>

## Slide 2: Agenda
Technical Advisory Committee
3 September 2009
Program Status
Market Readiness
Traceability
Notes: <number>
<number>

## Slide 3: Nodal Systems Blueprint
3 September 2009
Technical Advisory Committee

## Slide 4: Nodal Timeline
Technical Advisory Committee
3 September 2009

## Slide 5: Completed Milestones
Program Milestone: SEM Go-Live
  Included the following project milestones
    Systems/SEM/External Verification Testing
      EDS complete
    Systems/SEM/Go-Live Activities
      SEM modeling guidelines , final nodal CIM model posted; TAC/BoD approval of SEM Go-Live
    Readiness/Operational Readiness/Environment Configuration & Management
      SEM PROD build complete, SEM monitoring complete
    Readiness/Operational Readiness/Load & Performance
      SEM performance test complete, SEM cutover sequence begins
  Project Milestones
  Systems/Applications/MMS Functional Acceptance Testing
    MMS5 FAT complete – Aug. 21
  Systems/Applications/CMM Functional Acceptance Testing
    CMM4.1 FAT complete – Aug. 21
  Integration Testing
    All core integration components verified in iTest
Technical Advisory Committee
3 September 2009
Notes: <number>

## Slide 6: Single Entry Model Go-Live Update
3 September 2009
Technical Advisory Committee
SEM went live on time Aug. 31
Early results (as of Sept. 2)
  No functional issues
  6 of 20 TSPs have successfully submitted 77 NOMCRs
  >75% of Help Desk tickets have been access-related
  Maximum of 13 concurrent users
  Additional configuration and performance tuning continues to improve performance
Monthly touch points will be established with MPs to verify integrity of network model data
Notes: <number>
<number>

## Slide 7: Upcoming Milestones
Program Milestones
  Phase 2: Market Connectivity
  Project Milestones (30 day look-ahead)
  Readiness/Market Readiness/External Outreach & Training
    MP site visits begin
  Readiness/Operational Readiness/Environment Configuration & Management
    Phase 2.1 NPROD build complete
  Inclusion of progress measures
Technical Advisory Committee
3 September 2009

## Slide 8: Upcoming Program Milestone Definition
Technical Advisory Committee
3 September 2009
Phase 2: Market Connectivity
  Scope
    Market Participant interface testing (API, UI)
    Market System Rules Validation - Phase 1 (as defined in MMS – Explanation of Market Participant Submission Items v0.25 document)
  Objectives
    Make available Market Trials environment with latest version of MMS, Market Manager UI and External Web Services
    Provide MPs access to Market Trials environment to complete development and qualification preparation
  Schedule
    Sept.-Oct.: Bi-weekly Market Calls
    Week of Oct. 5: Kickoff meeting
    Oct. 28: Market Connectivity

## Slide 9: Nodal Program Risks/Issues Approach
Program risks/issues to be prioritized as they pertain to next major market deliverable
  October Market Connectivity
  Subsequent functional deliveries for MP testing
General programmatic risks/issues, proposed mitigations and impact assessments
  Included in daily PMO discussions
  Escalated to marketplace when needed
For example …
  CMM’s delivery status has low impact to current program deliverables
  Issues related to Market Connectivity have relatively high impact
Technical Advisory Committee
3 September 2009

## Slide 10: Nodal Program Risks & Issues
Technical Advisory Committee
3 September 2009
Immediate
  Risk: Reconciling protocols, systems and market expectations
  Risk: Integration Testing
Long-Term
  Risk: Data Center capacity concerns
Notes: <number>

## Slide 11: Participant Readiness Touch Points
MP Handbooks
  SCED/LFC
  CRR
  DAM/RUC
2009
Technical Advisory Committee
3 September 2009
Meetings
Training
Outreach
Market trials
December
Material preparation
Full schedule confirmation
3 site visits: w/o 9/28
November
October
September
Readiness Center
Limited ERCOT metrics
6 site visits
Additional ERCOT & MP metrics
6 site visits
3 site visits
Bi-weekly calls
Bi-weekly calls
Voluntary MP connectivity testing
Bi-weekly calls
2010 Market Trials Roadmap: w/o 10/5
Technical Workshop
Market Connectivity open to MPs
NATF 9/1
NATF 9/29
NATF 10/27
NATF 12/8
Nodal 101
LSE 201
Generation 101, 201
Basic Training
Economics of LMP
Transmission 101
Nodal 101
LSE 201
Generation 101, 201
Economics of LMP
Transmission 101
Settlement Workshops
Nodal 101
LSE 201
Generation 101
Basic Training
Nodal 101
LSE 201
Last Resource registration data collection window open
Bi-weekly market calls
  Outage Scheduler
  Settlement
Notes: <number>

## Slide 12: Upcoming Milestones
Program Milestones
  Phase 2: Market Connectivity
  Market Readiness Project Milestones (30 day look-ahead)
  Readiness/Market Readiness/External Outreach & Training
    MP site visits begin (week of Sept. 28)
Technical Advisory Committee
3 September 2009

## Slide 13: Outreach Candidates
AEP
ANP
APX
Austin Energy
BP
Brazos
BTU
Calpine
CPS Energy
Constellation
Direct Energy
Eagle Energy
Technical Advisory Committee
3 September 2009
Exelon
Garland
LCRA
Luminant
Nextera/FPL Energy
NRG Texas
Occidental
Shell
STEC
Suez
Tenaska
Topaz Energy
ERCOT is proactively contacting the following entities to request a site visit. Additional participants will be accommodated where the schedule permits.*
* Represents:
  Level IV QSE
  NATF participation
  Vendor diversity
Notes: <number>

## Slide 14: Protocol Traceability Effort Update
Technical Advisory Committee
3 September 2009
Tier 1 Sections |  |  |  | 
 | Definition | SME Analysis/Validation | Begin Reviews w/Business | Target for Reports to NATF
Section 7 | Congestion Revenue Rights | 85-90% | In progress | Sept
Section 8 | Performance Monitoring | 75% | 9/03 | Nov*
Section 3 | Management Activities for the ERCOT system | 40% | 9/15 | Nov
Section 4 | Day Ahead Operations | 5% | 9/22 | Oct
Section 5 | Transmission Security Analysis and RUC | 5% | 9/29 | Nov
Section 9 | Settlement & Billing | 5% | 10/01 | Nov
Section 6 | Adjustment Period and Real-Time Operations | 15% | 10/20 | Dec
Section 17 | Market Monitoring and Data Collection | 0% | 10/22 | Dec
Section 16.11 | Financial Security for Counter-Parties | 0% | 10/27 | Dec
  Tier 2 (Moderate Impact): 10, 11, 12, 13, 20, 22 (Dec. ’09 completion target)
  Tier 3 (Low Impact): 1, 2, 14, 15, 18, 19, 21, 23, 24 (Nov. ’09 completion target)
  * Delays in approving performance criteria may affect date.

## Slide 15
Questions ?

## Slide 16
Appendix
Notes: <number>

## Slide 17: Program Risk: Reconciling Protocols, Systems and Market Expectations
Technical Advisory Committee
3 September 2009
Risk: Reconciling Protocols, Systems and Market Expectations |  |  |  | Experience with deploying nodal markets by other ISOs has shown that expectations of the market participants are often missed, despite best efforts at defining tariffs or protocol requirements. ERCOT needs to assume such a risk exists for this nodal implementation as well. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Assess maturity and readiness of software in the initial nodal release, focusing on new/tailored capability for Texas Nodal. |  |  |  | B. Day K. Farley | Tier 1: 10/5/09 Tier 2: 12/15/09 Tier 3: 11/30/09 | 8/7/09 – Work is underway to trace protocols, requirements and business processes alignment analyses are in progress.
2. Add team members to the nodal program with Texas market experience to ensure readiness for Market Trials. SMEs will report requirements to testing traceability gaps to ERCOT business owners for resolution. |  |  |  | B. Day K. Farley | Ongoing | 8/7/09 – SMEs were added to the team in May. Work is underway to trace protocols, requirements and business processes alignment analyses are in progress.
3. Keep the oversight groups apprised of progress. |  |  |  | M. Cleary | Ongoing | 4/13/09 Risk incorporated into the set being reported externally; will be maintained actively.
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 18: Program Risk: Integration Testing
Technical Advisory Committee
3 September 2009
Risk: Integration Testing |  |  |  | Continued risk around technology delivery of business systems integration due to complexity and continuing maturing of application and data dependencies. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
Planned Integration Test phases and associated functional and technology components. Created effort-based testing delivery work plan to prioritize and align deliverables to key external milestones. Instituted daily PMO meetings to manage and mitigate day-to-day risks to scope and schedule deliverables. |  |  |  | PMO | Ongoing | 9/2/09 – Planning of Test phases and associated work plan has been completed Execution of work plan, with specific focus on October Market Trials functionality has begun
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 19: ERCOT-Wide Risk: Data Center Capacity Concerns
Risk: Data Center Capacity Space Concerns |  |  |  | Data center capacity, space, and power may be inadequate for Nodal go-live, unless plans for expansion are adequate. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Establish an Information Lifecycle Management approach to manage the life cycle of data being managed. |  |  |  | D. Forfia | Implementation expected Q1 2010 for Retail Applications | ERCOT project PR 90006_01 Commercial Systems Information Lifecycle Management Project will be presenting as an update during the October Board of Directors Meeting, and will request Execution and Funding approval at the November Board of Directors Meeting
2. Expand current data center space, and build out new data center, to increase ERCOT data center capacity. |  |  |  | D. Forfia | TCC1 build out is complete Bastrop DC in production Feb 2011 TCC3 in production May 2011 | TCC Expansion commissioned as of 9/2/09
3. Validate and monitor Nodal data capacity assumptions for Go Live |  |  |  | D. Forfia | Ongoing | 7/17/09 Status reports are provided to the Board of Directors in executive sessions
Potential Milestone Impact: Nodal Go-Live
3 September 2009
Technical Advisory Committee
Notes: <number>
<number>
<number>