## Guidelines
Rules for Submission of Large Volume of Transactions
Block out all maintenance and release windows
Block out ERCOT holidays
Block out Tuesday or Wednesday, if possible.
Rate of Submission:
During the week
Prior to 5 PM
Submit transactions at a rate of once an hour
In bundles that are no more than 33,000 transactions at a time
OR
After 5 PM
No restrictions as to rate or number of transactions
On weekends
No restrictions as to rate or number of transactions
Updates:
I moved out the first day of sending 814_20s to the Tuesday after implementation.
Blocked the Wednesday of that week.
Moved Oncor's numbers out and added 5,500 814_20s to each day in schedule for the meter change.
Original schedule - Oncor dropped to maintenance levels on December 17th
New schedule - Oncor drops to maintenance levels on January 4th
Extends schedule about 2 weeks

## Draft Timeline
| November | [5 empty] | December | [5 empty] | January
|  | Max # | Oncor | CenterPoint | Remaining |  |  | Max # | Oncor | CenterPoint | Remaining |  |  | Max # | Oncor | CenterPoint | Remaining
Tues | 3 | [5 empty] | 1 |  |  | 2000 |  | cycle 7
Wed | 4 | [5 empty] | 2 | 60000 | 29786 | 2000 | 28214 | cycle 8
Thurs | 5 | [5 empty] | 3 | 60000 | 29786 | 11560 | 18654 | cycle 9
Fri | 6 | [5 empty] | 4 | 60000 | 29786 | 16773 | 13441 | cycle 10 | 1 | New Year's Weekend
Sat | 7 | [5 empty] | 5 | 100000 |  | 17511 | 82489 | cycle 11 | 2
Sun | 8 | [5 empty] | 6 | [5 empty] | 3
Mon | 9 | [5 empty] | 7 | 60000 | 35786 | 2238 | 21976 | cycle 12 | 4 | 60000 | 11000 | 0 | 49000
Tues | 10 | [5 empty] | 8 |  |  | 2000 |  |  | 5 |  |  | 3000
Wed | 11 | [5 empty] | 9 | 60000 | 35786 | 2000 | 22214 | cycle 13 | 6 | 60000 | 11000 | 5205 | 43795 | cycle 9
Thurs | 12 | [5 empty] | 10 | 60000 | 35786 | 8388 | 15826 | cycle 14 | 7 | 60000 | 11000 | 5680 | 43320 | cycle 10
Fri | 13 | [5 empty] | 11 | 60000 | 35786 | 3852 | 20362 | cycle 15 | 8 | 60000 | 11000 | 5796 | 43204 | cycle 11
Sat | 14 | PR80027 Go Live |  |  |  |  | 12 | December Retail Release |  |  |  |  | 9 | 100000 |  | 3911 | 96089 | cycle 12
Sun | 15 | [5 empty] | 13 | [5 empty] | 10
Mon | 16 |  |  | 2000 |  |  | 14 | 60000 | 29786 | 0 | 30214 | cycle 16 | 11 | 60000 | 11000 |  | 49000
Tues | 17 | 60000 | 29786 | 2000 | 28214 |  | 15 |  |  | 2000 |  |  | 12 |  |  | 3000
Wed | 18 |  |  | 2000 |  |  | 16 | 60000 | 35786 | 10038 | 14176 | cycle 17 | 13 | 60000 | 11000 | 7198 | 41802 | cycle 14
Thurs | 19 | 60000 | 29786 | 7017 | 23197 | cycle 1 | 17 | 60000 | 35786 | 8772 | 15442 | cycle 18 | 14 | 60000 | 11000 | 3614 | 45386 | cycle 15
Fri | 20 | 60000 | 29786 | 9787 | 20427 | cycle 2 | 18 | 60000 | 32786 | 2145 | 25069 | cycle 19/20 | 15 | 60000 | 11000 | 3000 | 46000
Sat | 21 | 100000 |  | 2000 | 98000 | cycle 3 | 19 | 100000 |  | 2000 | 98000 |  | 16 | 100000 |  | 4778 | 95222 | cycle 17
Sun | 22 | [5 empty] | 20 | [5 empty] | 17
Mon | 23 | 60000 | 29786 | 4499 | 25715 | cycle 4 | 21 | 60000 | 32786 | 168 | 27046 | cycle 1 | 18 | 60000 | 11000 | 1362 | 47638 | cycle 18
Tues | 24 |  |  | 2000 |  |  | 22 |  |  | 2000 |  |  | 19 |  |  | 3000
Wed | 25 | 60000 | 29786 | 2000 | 30214 | cycle 5 | 23 | 60000 | 32786 | 3808 | 23406 | cycle 2 | 20 | 60000 | 11000 | 3000 | 46000
Thurs | 26 | Thanksgiving Weekend |  |  |  |  | 24 | Christmas Weekend |  |  |  |  | 21 | 60000 | 11000 | 3000 | 46000
Fri | 27 | [5 empty] | 25 | [5 empty] | 22 | 60000 | 11000 | 3000 | 46000
Sat | 28 | [5 empty] | 26 | [5 empty] | 23 | January Retail Release
Sun | 29 | [5 empty] | 27 | [5 empty] | 24
Mon | 30 | 60000 | 29786 | 0 | 30214 | cycle 6 | 28 |  |  | 2000 |  |  | 25 | 60000 | 11000 | 174 | 59826 | cycle 1
Tues | [6 empty] | 29 |  |  | 2000 |  |  | 26 |  |  | 3000
Wed | [6 empty] | 30 | 60000 | 32786 | 2000 | 25214 | cycle 4 | 27 | 60000 | 11000 | 6658 | 53342 | cycle 2
Thurs | [6 empty] | 31 | 60000 | 32786 | 2597 | 24617 |  | 28 | 60000 | 10000 | 3664 | 56336 | cycle 4
Note on E21: 00017167: meter changes + cycle 1
Note on E22: 00017167: meter changes + cycle 2
Note on E23: 00017167: meter changes

## Sheet1
20000 | 19 | 1052.6316