Project 80027 Progress Report

| Execution Milestones | Baseline Date | Status |
| --- | --- | --- |
| Technical Architecture Complete | 05/15/2009 | Complete |
| Development Complete | 07/24/2009 | Complete |
| Detailed Designs Complete | 08/11/2009 | Complete |
| pTest Complete | 08/11/2009 | Complete |
| iTest Complete | 11/06/2009 | On Schedule |
| Market Test Complete | 11/06/2009 | On Schedule |
| GO LIVE | 11/14/2009 | On Schedule |
| Go Live Contingency Date | 12/12/2009 |  |
| Stabilization Complete | 03/19/2010 |  |
| Project Complete | 05/21/2010 |  |