## Slide 1: Nodal Program Update
Mike Cleary
Sr. VP and Chief Technology Officer
Technical Advisory Committee
1 October 2009
Notes: <number>

## Slide 2: Agenda
Technical Advisory Committee
1 October 2009
Program Status
Market Readiness
Traceability
Follow-Up Discussion Points
Notes: <number>
<number>

## Slide 3: Nodal Systems Blueprint
1 October 2009
Technical Advisory Committee

## Slide 4: Nodal Timeline
Technical Advisory Committee
1 October 2009

## Slide 5: Completed Milestones
  Project Milestones
  Readiness/Market Readiness/External Outreach & Training
    MP site visits begin
      LCRA Oct. 9
  Readiness/Operational Readiness/Environment Configuration & Management
    Phase 2.1 NPROD build complete
      Hardware installed, baseline code set on schedule
Technical Advisory Committee
1 October 2009
Notes: <number>

## Slide 6: Upcoming Program Milestone Definition
Technical Advisory Committee
1 October 2009
Phase 2.1: Market Connectivity
  Scope
    Market Participant interface testing (API, Market Manager UI)
    Market System Rules Validation - Phase 1*
  Objectives
    Make available Market Trials environment with latest version of MMS, Market Manager UI and External Web Services
    Provide MPs access to Market Trials environment to complete development and qualification preparation
  Schedule
    Oct. 8: Kickoff meeting (MP readiness seminar, market trials roadmap)
    Oct. 28: Market Connectivity testing begins; MP Technical Workshop
    October: Bi-weekly Market Calls
  *As defined in MMS – Explanation of Market Participant Submission Items v0.26 document.

## Slide 7: Current Milestones: Detailed Status (9-18-09)
Program Milestones
  Phase 2.1: Market Connectivity
  Project Milestones (30-day look-ahead)
  Integration/Connectivity Testing/Integration Testing
    MMS UI: initial test cycle 99% complete (94% pass rate)
    MMS EWS: initial test cycle 91% complete (92% pass rate)
  Market Trials/Connectivity Testing/Market Trials External Testing
    Kickoff meeting Oct. 8
    External interface specification document posted
    Phase 2.1 Market Connectivity Handbook to be posted Oct. 2
  Readiness/Market Readiness/External Outreach & Training
    Market Readiness Seminar Oct. 8
  Readiness/Market Readiness/Metrics Tracking & Assessment
    Phase 2.1 Commencement Criteria met
  Readiness/Operational Readiness/Environment Configuration & Management
    Nodal Production environment build-out (installation, verification of 2.1 code sets): 75% (hardware installed, baseline code set on schedule)
    Final build scheduled for Oct. 16
  Readiness/Operational Readiness/Security Testing
    Performance testing: 26% (web service stability and loading, UI stability and loading)
Technical Advisory Committee
1 October 2009

## Slide 8: Future Program Milestone Definition
Technical Advisory Committee
1 October 2009
Phase 3: Real Time Market
  Scope
    MMS-SCED execution
    SCED results and report publishing
    CRR auction execution (CRR UI)
    Outage Scheduler submissions (API, OS RUI)
  Objectives
    Execute real-time functionality on latest versions of EMS and MMS, using common NMMS Network Model
    Publish SCED results through ICCP and MIS
    Provide MPs access to Market Trials environment for continued defect resolution of critical Real-Time Outputs from ERCOT systems

## Slide 9: Future Program Milestone Definition
Technical Advisory Committee
1 October 2009
Phase 4: Day-Ahead Market, Reliability Unit Commitment
  Scope
    MMS-DAM, DRUC, HRUC, SCED execution
    Market results and report publishing
    Initial Settlements & Billing execution
    Outage and CRR integration
  Objectives
    Execute Nodal Markets on latest versions of EMS and MMS running on an integrated NMMS Network Model
    Publish SCED results through ICCP and MIS
    Provide MPs access to Market Trials environment for continued defect resolution of critical Market and Settlement outputs from ERCOT systems
    Publish initial Settlement statements and extracts

## Slide 10: Nodal Earned Value (March-August)
1 October 2009
Technical Advisory Committee

## Slide 11: Nodal Program Risks & Issues
Technical Advisory Committee
1 October 2009
Immediate
  Risk: Reconciling protocols, systems and market expectations
  Risk: Integration Testing
Long-Term
  Risk: Data Center expansion capacity concerns
  Risk: Internet Explorer upgrade
Notes: <number>

## Slide 12: Participant Readiness Touch Points
MP Handbooks
  SCED/LFC
  CRR
2009/2010
Technical Advisory Committee
1 October 2009
Meetings
Training
Outreach
Market trials
January
Readiness Center
Limited ERCOT metrics
6 site visits
December
November
October
Additional ERCOT & MP metrics
6 site visits
3 site visits
Bi-weekly calls
Voluntary MP connectivity testing
Bi-weekly calls
Voluntary MP connectivity testing
NATF 10/27
NATF 12/8
Nodal 101
LSE 201
Generation 101, 201
Basic Training
Economics of LMP
Transmission 101
Settlement Workshop
Nodal 101
LSE 201
Generation 101, 201
Economics of LMP
Transmission 101
Settlement Workshop
Nodal 101
LSE 201
Generation 101
Basic Training
Bi-weekly calls
2010 Market Trials Roadmap: 10-8
Technical Workshop: 10-28
Market Connectivity open to MPs 10-8
  DAM/RUC
  Outage Scheduler
  COMS
Nodal 101
LSE 201
Generation 101, 201
CRR – online
Settlement Workshop
8 site visits
Initiate Phase 3 metrics
Start weekly calls
MP re-qualification begins
NATF tbd
Notes: <number>

## Slide 13: Outreach Menu
Program Update
Readiness Scorecard & Metrics
Functional Topics
Day-Ahead Market/Reliability Unit Commitment
Real-Time Operations/SCED
Outage Scheduling
Settlements & Billing
Reports & Extracts
Congestion Revenue Rights
Telemetry
Basic Nodal Concepts
Technical Advisory Committee
1 October 2009
Presentation Materials for the site visits will be posted to the Readiness Center. Topics to choose from include:
Outline by Functional Topic
Background of Zonal
How changing in Nodal
Central list of artifacts
Overview of Implementation
MP Engagement
Notes: <number>

## Slide 14: Protocol Traceability Effort Update
Technical Advisory Committee
1 October 2009
Tier 1 Sections |  |  |  | 
 | Definition | SME Analysis/Validation | Begin Reviews w/Business | Target for NATF reports
Section 7 | Congestion Revenue Rights | 90% | In progress | Sept
Section 8 | Performance Monitoring | 75% | In progress | Dec (revised)
Section 3 | Management Activities for the ERCOT system | 70% | In progress | Nov
Section 4 | Day Ahead Operations | 75% | 9/22 | Nov
Section 5 | Transmission Security Analysis and RUC | 10% | 9/29 | Nov
Section 9 | Settlement & Billing | 50% | 10/01 | Nov
Section 6 | Adjustment Period and Real-Time Operations | 25% | 10/20 | Dec
Section 17 | Market Monitoring & Data Collection | 0% | 10/22 | Dec
Section 16.11 | Financial Security for Counter-Parties | 0% | 10/27 | Dec
  Tier 2 (Moderate Impact): 10, 11, 12, 13, 20, 22 (Dec. ’09 completion target)
  Tier 3 (Low Impact): 1, 2, 14, 15, 18, 19, 21, 23, 24 (Dec. ’09 completion target)

## Slide 15: Protocol Traceability Effort Update
Technical Advisory Committee
1 October 2009
Tier 1 Sections |  |  |  | 
 | PTE Traced Items | PTE Full Trace Report | PTE Research Items | PTE Alignment Items
Section 7 – Congestion Revenue Rights | 486 | Will post for Oct NATF | 14 | 1
Section 3 – Management Activities for the ERCOT system | 905 | Will post for Nov NATF | 327 | TBD
Section 8 – Performance Monitoring | 204 | Will post for Dec NATF | 85 | TBD
Details | 
 | Overview of PTE Alignment Items
Section 7 – Congestion Revenue Rights | Alignment – 1. CRR Handbook – assigned, due 12/31/09
Section 3 – Management Activities for the ERCOT system | Research items in progress
Section 8 – Performance Monitoring | Research items in progress

## Slide 16: Follow-Up Discussion Points
Technical Advisory Committee
1 October 2009
  DAM sizing approach/status
  ERCOT, ABB team working defect through iterative approach (analyzing and identifying sizing targets; updating and testing code; evaluating performance and solution results)
  Options for additional management of transactions will be determined and evaluated once the code solution has reached optimal performance and results
  Updates will be provided as testing progresses
  Business process and desk procedure postings

## Slide 17
Questions ?

## Slide 18
Appendix
Notes: <number>

## Slide 19: Phase 2 Market Connectivity Defect Update
Technical Advisory Committee
Project | Sub-Project | Status | Open Critical Defects Sept. 8/Sept. 22 |  |  | 
MMS | Core Application | MMS Release 5 with several patches currently being used for Market Connectivity testing. A portion of the outstanding defects have been fixed in a patch that is currently in the MMS FAT environment, with testing underway. Once that testing is complete, the patch will be migrated to iTest; remaining defects have been logged with the vendor and are being worked into an upcoming patch. | MMS5 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s (P1/P2) | 0 2 33 | 0 2 31 | 
 | MMS UI | MMS Market Manager UI (MMS MM UI) release 1.16.1 currently being used for Market Connectivity testing. All outstanding defects have been logged with the in-house development team; development/testing/deployment cycles to address critical defects are in progress. | MMS MM UI 1.16.1 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s (P1/P2) | 0 7 9 | 0 13 8 |  
EIP | EWS-MMS Interface | EIP external Web Services spec release1.19 with several patches currently being used for Market Connectivity testing. All outstanding defects have been logged with the in-house development team; development/testing/deployment cycles to address critical defects are in progress. | EIP 1.19 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s (P1/P2) | 0 1 2 | 0 0 2 | 
1 October 2009

## Slide 20
Technical Advisory Committee
1 October 2009
Project | Weight | Forecast % | Est % | PFI* | Forecast Wgt.* | Est. Wgt.*
ERT | 127,359 | 11.65% | 14% | 1.20 | 14,838 | 17,830
INF | 236,728 | 17.08% | 14% | 0.82 | 40,440 | 33,142
MT | 174,399 | 0% | 0% | 0.00 | 0 | 0
INT | 95,145 | 0% | 0% | 0.00 | 0 | 0
Program | 633,631 |  |  | 0.92 | 55,278 | 50,972
 |  |  |  | * As of July |  | 
Performance Factor Index (PFI)
Initial baselines and weighting (weighting will be based on initial estimates of effort/work required)
  PFI 1.00: optimum; shows program effort on track according to estimated work
  PFI <1.00: program’s performance behind budgeted effort; work is slipping based on estimated work
  PFI >1.00: program’s performance ahead of the budgeted effort; work is ahead of budgeted work
  PFI should be as near to 1.00 as possible (strong estimation, efficient delivery)
NOTE: PFI data preliminary from PMO ground-up planning efforts; FMO validating as part of October budget updates.

## Slide 21: Program Risk: Reconciling Protocols, Systems and Market Expectations
Technical Advisory Committee
1 October 2009
Risk: Reconciling Protocols, Systems and Market Expectations |  |  |  | Experience with deploying nodal markets by other ISOs has shown that expectations of the market participants are often missed, despite best efforts at defining tariffs or protocol requirements. ERCOT needs to assume such a risk exists for this nodal implementation as well. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Assess maturity and readiness of software in the initial nodal release, focusing on new/tailored capability for Texas Nodal. |  |  |  | B. Day K. Farley | Tier 1: 10/5/09 Tier 2: 12/15/09 Tier 3: 11/30/09 | 8/7/09 – Work is underway to trace protocols, requirements and business processes alignment analyses are in progress.
2. Add team members to the nodal program with Texas market experience to ensure readiness for Market Trials. SMEs will report requirements to testing traceability gaps to ERCOT business owners for resolution. |  |  |  | B. Day K. Farley | Ongoing | 8/7/09 – SMEs were added to the team in May. Work is underway to trace protocols, requirements and business processes alignment analyses are in progress.
3. Keep the oversight groups apprised of progress. |  |  |  | M. Cleary | Ongoing | 4/13/09 Risk incorporated into the set being reported externally; will be maintained actively.
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 22: Program Risk: Integration Testing
Technical Advisory Committee
1 October 2009
Risk: Integration Testing |  |  |  | Continued risk around technology delivery of business systems integration due to complexity and continuing maturing of application and data dependencies. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
Planned Integration Test phases and associated functional and technology components. Created effort-based testing delivery work plan to prioritize and align deliverables to key external milestones. Instituted daily PMO meetings to manage and mitigate day-to-day risks to scope and schedule deliverables. |  |  |  | PMO | Ongoing | 9/2/09 – Planning of Test phases and associated work plan has been completed Execution of work plan, with specific focus on October Market Trials functionality has begun
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 23: ERCOT-Wide Risk: Data Center Capacity Concerns
Risk: Data Center Capacity Space Concerns |  |  |  | Data center capacity, space, and power may be inadequate for Nodal go-live, unless plans for expansion are adequate. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Establish an Information Lifecycle Management approach to manage the life cycle of data being managed. |  |  |  | D. Forfia | Implementation expected Q1 2010 for Retail Applications | ERCOT project PR 90006_01 Commercial Systems Information Lifecycle Management Project will be presenting as an update during the October Board of Directors Meeting, and will request Execution and Funding approval at the November Board of Directors Meeting.
2. Expand current data center space, and build out new data center, to increase ERCOT data center capacity. |  |  |  | D. Forfia | TCC1 build out is complete Bastrop DC in production mid -2011 TCC3 in production mid-2011 | TCC Expansion commissioned as of 9/2/09. TCC1 expansion and risk-mitigation steps for Met Data Center provide sufficient space for Nodal Go-Live in December 2010. Relocation to the new data centers occurs in mid-2011 after Nodal Go-Live.
3. Validate and monitor Nodal data capacity assumptions for Go Live |  |  |  | D. Forfia | Ongoing | 7/17/09 Status reports are provided to the Board of Directors in executive sessions.
Potential Milestone Impact: Nodal Go-Live
1 October 2009
Technical Advisory Committee
Notes: <number>
<number>
<number>