## Slide 1: MARS Taskforce
COPS Update October 13, 2009
Notes: <number>

## Slide 2
Execution Milestones | Baseline Date | Status
Technical Architecture Complete | 05/15/2009 | Completed
Development Complete | 07/24/2009 | Completed
Detailed Designs Complete | 08/11/2009 | Completed
pTest Complete | 08/11/2009 | Completed
iTest Complete | 11/06/2009 | On Schedule
Market Test Complete | 11/06/2009 | On Schedule
Go Live | 11/14/2009 (off-cycle) | On Schedule
Go Live (Contingency Date) | 12/12/2009 | 
Stabilization Complete | 03/19/2010 | 
Project Complete | 05/21/2010 | 
ERCOT’s AMS Project
9/30/09 Status Report
2
Notes: <number>

## Slide 3: Project 80027 - Update Market Testing
Scope of Market Testing:
  TDSP submits Advanced Metering LSE interval data file submission and ERCOT returns a file-level acknowledgement
Target Dates for Market Testing:
  October 19 – November 6, 2009
Next Steps:
  As the project progresses through development activities and the detailed ERCOT testing schedule is refined, coordination activities will be scheduled with the TDSPs.
Notes: <number>

## Slide 4: September 30, 2009 MARS Taskforce Meeting
We discussed the changes to ERCOT’s reporting, DDLs, extracts and web services that are needed to support AMS 15 minute interval data.
  Link to MARS Taskforce key documents: http://www.ercot.com/committees/board/tac/rms/marstf/
We agreed to the scheduling plan for 814_20s that would be expected to be sent to ERCOT from Oncor and CenterPoint Energy to change load profiles and/or AMS meter information effective November 16, 2009.
  There was some concern voiced that the AMS 814_20 scheduling team at ERCOT may need to be aware of the Business Annual Validation 814_20s because TDSPs may also schedule AV 814_20s to be sent to ERCOT in November that could create a problem based upon the volume of 814_20s and when they are sent.
<number>
Notes: <number>

## Slide 5: September 30, 2009 MARS Taskforce Meeting
The TDSPs proposed a 6 day delay in sending LSE files/data to ERCOT for settlement processing. The TDSPs stated that in their current design there would always be a 6 day delay in providing LSE data to ERCOT because:
  There would always be new meters being installed,
  The transactional process and timeline needed to change non-IDR to IDR profiles must coincide with a cycle meter read , and
  To minimize the volume of rejects for transactions within the LSE file where the load profile change transactions may not have successfully posted at ERCOT.
TDSPs agreed that they will continue to post daily LSE files to TDSP’s FTP sites or Web Portal for CR(s) downloads so any delay in LSE files/data being sent to ERCOT will not impact the CRs processes where 15-minute data will continue to be provided daily.
Notes: <number>

## Slide 6: September 30, 2009 MARS Taskforce Meeting
Due to some confusion with the information being provided by the TDSPs during this meeting, the Taskforce did not come to any conclusion on the TDSP’s proposed process in sending LSE files to ERCOT, therefore Oncor and CenterPoint Energy were given the following action item:
  What is the expected timeline that TDSPs will provide LSE files to ERCOT?
    A WebEx conference call was scheduled on Friday, October 9, 2009 for TDSPs to provide a response to this action item.
Notes: <number>

## Slide 7: October 9, 2009 MARS Taskforce WebEx
Notes: <number>

## Slide 8: Next Steps for MARS
Next meeting will be a WebEx scheduled on Wednesday, October 28, 2009 at 3:30 PM-5:00 PM
  Agenda Items:
    Project Status Report update, may include Market test results to date.
    Make sure all procedures/task required for a smooth November 14th production implementation have been resolved or completed
    Schedule next meeting date(s) Post Go-Live
Continue to update RMS and COPS on project status.
<number>
Notes: <number>

## Slide 9: Questions?
<number>
Notes: <number>