## Market Design
ERCOT
Renewable Technology Working Group (RTWG)
List of Market Design Issues
August 2009
Issue Category | Issue No. | Title | Description | Current Group | Priority | Impact | Solution Implemented by | Revision Mechanism | Status | Other REF No. | RTWG Last Action/Next Step
MD | 4 | New Ancillary Service Products Needed for Reliability | Determine if new ancillary services are needed to reliably integrate the large amounts of wind generation coming into the ERCOT market. | ROS | Long Term | Medium | ERCOT | PRR/NPRR | Dependent on results of SO-5
MD | 8 | Reactive and Voltage Requirements Applicable to Wind Generators | Review of current ERCOT Protocols to ensure reactive and voltage control requirements are applicable to all generating technologies, including wind generation. | WOTF | Near Term | Low | ERCOT | PRR | In Docket 36482, the deadline to request a hearing is Nov 6. Meanwhile, PRR 830 "Reactive Power Capability Requirement" is up for a vote at ROS on Oct 15. Additionally, PRR 835 "Reactive Capability Requirement", a competing proposal, is also up for a vote at ROS on Oct 15. | WOTF 1a

## System Ops
ERCOT
Renewable Technology Working Group (RTWG)
List of System Operations Issues
[9 empty] | August 2009 | August 2009
Issue Category | System Ops Issue No. | Title | Description | Current Group | Priority | Impact | Solution Implemented by | Revision Mechanism | Status | Other Ref No.
SO | 5 | Operational Studies Related to Wind Generation | Operational studies re: Wind (ramp rate, low load situations, forecasting) to identify if new ancillary services are needed. | RTWG | Long Term | Medium | ERCOT | NPRR | Finalize list of recommendations at September RTWG meeting to be provided to TAC.
SO | 7 | Wind Generation and High System Frequency | Determine impact of wind generation on high system frequency events and develop possible solutions. | WOTF | Near Term | Medium | Market Participants | PRR/NPRR | PRR824 "Primary Frequency response" is at PRS for IA review. | WOTF 5
SO | 9 | SCADA Control of Generator Circuit Breakers | Develop guidelines for better control of generator circuit breakers via SCADA. | OGRR TF | Near Term | Low | Market Participants | OGRR | OGRR 226 approved by OWG and now for consideration by ROS. | WOTF 1b
SO | 15 | Communications between Wind Farms and TSPs | Examine possible improvements in real-time communications between wind farms and transmission service providers (TSPs). | WOTF | Near Term | Medium | Market Participants | OGRR | OGRR 226 "Generation Resource Response Time Requirements" was approved by OWG on 9/15 and endorsed by WMS on 9/16, and is now up for consideration by ROS on 10/15. | WOTF 2a
SO | 25 | Generator Governor Response for Wind Generators | : Determine proper generator governor response requirements for wind generators in the Nodal Market design. | WOTF | Short Term | Medium | Market Participants | NPRR | See SO-7 | WOTF 1e