|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for September 2009 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 224 active generation interconnection requests totaling over 79,000 MW. This includes almost 45,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $1,038.6 Million - Transmission Projects approved in 2009 total $257.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.2 Billion - Transmission Projects energized in 2009 total about $416 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	3

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	6

2.	Regional Planning Group Project Reviews	9

3.	Other Notable Activities	9

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Papalote Creek I Wind (08INR0012a) for 180 MW in San Patricio County

## The total installed wind capacity is now 8,515 MW, of which 6,992 MW (82%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements

## Cedro Hill Wind (09INR0082) for 150 MW in Webb County

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 224 active generation interconnection or change requests |  |  |  |  |
| As of September 30, 2009 | North | South | West | Total |
| Security Screening Study | 6 | 6 | 10 | 22 |
| SSS Completed | 4 | 10 | 15 | 29 |
| Full Interconnect Study | 26 | 22 | 83 | 131 |
| FIS Completed | 3 | 10 | 2 | 15 |
| Interconnect Agreement Completed | 7 | 11 | 9 | 27 |
| Capacity under Interconnection Agreements | 4,487 | 2,423 | 1,578 | 8,488 |
| Capacity for Grid, MW | 21,233 | 22,854 | 34,998 | 79,085 |
| Wind Capacity, MW | 4,025 | 7,920 | 32,656 | 44,601 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,881 | 16,977 |
| Gas-CT |  |  | 527 | 1,177 |
| Total Gas | 1,279 | 12,467 | 4,408 | 18,154 |
| Nuclear |  |  | 5,986 | 5,986 |
| Coal |  | 3,712 | 2,958 | 6,670 |
| Wind | 7,245 | 30,264 | 7,092 | 44,601 |
| Solar | 636 | 459 |  | 1,095 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 1,126 | 1,200 |  | 2,326 |
| Grand Total | 10,344 | 48,152 | 20,589 | 79,085 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of September 30, 2009 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0079 | Pearsall Expansion | IA | Frio | South | Oct-09 | Gas-CT | 200 |  |
| 09INR0047 | Loraine Windpark | IA | Mitchell | West | Oct-09 | Wind | 251 | date |
| 09INR0028 | V H Braunig 6 | IA | Bexar | South | Oct-09 | Gas-CT | 185 | date |
| 09INR0072 | Dansby3 | PL | Brazos | North | Oct-09 | Gas-CT | 48 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 10INR0026 | Langford Wind Power | IA | Tom Green | West | Dec-09 | Wind | 150 |  |
| 10INR0047 | Bluff-Kendall Windfarm | IA | Kendall | South | Jan-10 | Wind | 0 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Feb-10 | Gas-CC | 50 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Apr-10 | Biomass | 45 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Apr-10 | Gas-CC | 327 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | May-10 | Coal | 855 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | May-10 | Wind | 150 | new |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 09INR0045 | Sand Hill Peakers | IA | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Dec-10 | Coal | 263 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Dec-10 | Wind | 136 | Capacity |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 06INR0022c | Penascal Wind Farm 2 | IA | Kenedy | South | Dec-10 | Wind | 202 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 07INR0036 | Coyote Run Windfarm | XX | Borden | West | Mar-11 | Wind | 225 | Cancelled |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Dec-11 | Wind | 100 | Capacity |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1001 |  |
| 09INR0026 | Sterling Energy Center | IA | Sterling | West | Jun-12 | Wind | 300 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 200 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 08INR0040 | Lenorah Project | IA | Martin | West | Sep-12 | Wind | 251 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1792 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2700 |  |
|  |  |  |  |  |  | Total | 20589 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 08INR0044 | Concho | 200 | TBD | Wind |
| 08INR0041 | Coke | 200 | TBD | Wind |  | 08INR0042 | Coke | 200 | TBD | Wind |
| 08INR0054 | Comanche | 401 | TBD | Wind |  | 09INR0025 | Concho | 180 | TBD | Wind |
| 08INR0031 | Childress | 100 | Nov-09 | Wind |  | 09INR0048 | Jack | 150 | TBD | Wind |
| 08INR0022 | Floyd | 100 | Dec-09 | Wind |  | 09INR0073 | Scurry | 200 | Nov-09 | Wind |
| 08INR0012b | San Patricio | 151 | Dec-09 | Wind |  | 08INR0023 | Floyd | 100 | Dec-09 | Wind |
| 08INR0056 | Nolan | 149 | Dec-09 | Wind |  | 08INR0039 | Hamilton | 90 | Dec-09 | Wind |
| 09INR0054 | Stonewall | 148.5 | Dec-09 | Wind |  | 09INR0051 | Borden | 249 | Dec-09 | Wind |
| 09INR0061 | Kent | 258 | Dec-09 | Wind |  | 09INR0058 | Howard | 250 | Dec-09 | Wind |
| 11INR0012 | Duval | 400 | Dec-09 | Wind |  | 09INR0065 | Webb | 150 | Dec-09 | Wind |
| 09INR0077 | Reagan | 500 | Dec-09 | Wind |  | 11INR0013 | Mills | 150 | Dec-09 | Wind |
| 10INR0024 | Briscoe | 2940 | Jan-10 | Wind |  | 10INR0011 | Johnson | 275 | Jan-10 | Gas |
| 10INR0048 | Hardeman | 1000 | Jan-10 | Wind |  | 11INR0033a | Cameron | 200 | Jan-10 | Wind |
| 10INR0045 | Webb | 734 | Apr-10 | Wind |  | 10INR0046 | Jim Hogg | 264 | Apr-10 | Wind |
| 09INR0018 | Concho | 249 | May-10 | Wind |  | 07INR0032 | Tom Green | 249 | May-10 | Wind |
| 10INR0016 | Childress | 150 | May-10 | Wind |  | 09INR0035 | Concho | 750 | May-10 | Wind |
| 09INR0069 | Reagan | 36 | May-10 | Wind |  | 10INR0023 | Haskell | 386 | May-10 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 09INR0070 | Reagan | 42 | May-10 | Wind |
| 10INR0079 | Nolan | 60 | May-10 | Wind |  | 10INR0062a | Pecos | 49.5 | May-10 | Wind |
| 09INR0081 | Rusk | 18 | Jun-10 | Coal |  | 10INR0069 | Rusk | 13 | May-10 | Coal |
| 10INR0035 | Harris | 416 | Jun-10 | Gas |  | 10INR0029 | Hood | 810 | Jun-10 | Gas |
| 10INR0013 | Upton | 400 | Jul-10 | Wind |  | 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0071 | Matagorda | 88 | Sep-10 | Wind |  | 10INR0038 | Glasscock | 350 | Aug-10 | Wind |
| 10INR0041 | Floyd | 135 | Oct-10 | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 10INR0070 | Hunt | 50 | Nov-10 | Gas |  | 09INR0074 | Motley | 70 | Oct-10 | Wind |
| 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |  | 10INR0039 | Dickens | 200 | Nov-10 | Wind |
| 10INR0032 | Navarro | 775 | Dec-10 | Gas |  | 09INR0031 | Ector | 275 | Dec-10 | Gas |
| 07INR0013 | Coke | 200 | Dec-10 | Wind |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 07INR0026 | Baylor | 400 | Dec-10 | Wind |  | 07INR0015 | Foard | 180 | Dec-10 | Wind |
| 10INR0008 | Pecos | 500 | Dec-10 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 08INR0062 | Archer | 249 | Dec-10 | Wind |  | 08INR0061 | Hardeman | 200 | Dec-10 | Wind |
| 10INR0033 | Armstrong | 399 | Dec-10 | Wind |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 09INR0076 | Jackson | 300 | Dec-10 | Wind |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 10INR0056 | Borden | 249 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 10INR0060 | Willacy | 400.5 | Dec-10 | Wind |  | 10INR0059 | Zapata | 250.7 | Dec-10 | Wind |
| 09INR0041 | Mitchell | 300 | Dec-10 | Wind |  | 10INR0077 | Callahan | 101 | Dec-10 | Wind |
| 08INR0014 | Webb | 183 | Mar-11 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 11INR0049 | Wharton | 275 | Apr-11 | Gas |  | 11INR0050 | Crosby | 149 | Mar-11 | Wind |
| 11INR0028 | Grimes | 1280 | May-11 | Gas |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 11INR0048 | Harris | 300 | May-11 | Gas |  | 11INR0046 | Brazoria | 300 | May-11 | Gas |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 10INR0009 | Castro | 300 | May-11 | Wind |  | 11INR0058 | Pecos | 135 | May-11 | Solar |
| 10INR0062b | Pecos | 49.5 | May-11 | Wind |  | 09INR0075 | Kinney | 248 | May-11 | Wind |
| 09INR0050 | Fannin | 1200 | Jun-11 | Gas |  | 11INR0062 | Nueces | 149 | May-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0006 | Lamar | 579 | Jul-11 | Gas |  | 11INR0057 | Cameron | 144 | Jun-11 | Wind |
| 11INR0008a | Roberts | 1000 | Sep-11 | Wind |  | 11INR0040 | freestone | 640 | Aug-11 | Gas |
| 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |
| 06INR0022d | Kenedy | 200 | Dec-11 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 10INR0062c | Pecos | 201 | May-12 | Wind |
| 12INR0002 | Briscoe | 750 | Jul-12 | Wind |  | 10INR0022 | Harris | 3500 | Jun-12 | Gas |
| 08INR0019c | Gray | 250 | Nov-12 | Wind |  | 12INR0016 | Nueces | 1200 | Nov-12 | Other |
| 08INR0019b | Gray | 250 | Nov-12 | Wind |  | 08INR0019a | Gray | 250 | Nov-12 | Wind |
| 12INR0005 | Floyd | 1100 | Dec-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 12INR0018 | Gray | 600 | Dec-12 | Wind |
| 13INR0006 | Gray | 750 | Oct-13 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 06INR0022e | Kenedy | 200 | Dec-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 14INR0005 | Matagorda | 1200 | Jul-14 | Coal |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Centerpoint Energy has submitted a project to expand the Zenith substation, add one 800 MVA autotransformer, connect Zenith to existing circuits near the Gertie substation and upgrade/reconfigure nearby 138 kV circuits.  The estimated completion date of this project is summer 2014 and the estimated cost is $ 25.5 M.   The ERCOT Independent Review for this project is complete and an ERCOT Endorsement Letter has been sent.

# American Electric Power Service Corporation submitted a project to construct several improvements in the Corpus Christi area.  The estimated completion date of this project is June 2012 and estimated cost is $ 214 M.   This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Luminant Energy has submitted the Comanche Peak Area Congestion Mitigation Plan project to loop the future Parker to Everman 345 kV CREZ line into the Comanche Peak 345 kV switch station.  Luminant Energy’s estimated completion date for this project is April 2010 and the estimated cost is $3 M.  This project is in ERCOT Independent Review.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints – August, 2009

| Contingency | Binding Element | Estimated Costs | Transmission Project |
| --- | --- | --- | --- |
|  | Capacity Shortage | $ 4,554,174 |  |
| Temple Pecan Creek - Tradinghouse & Temple Switch - Lake Creek SES | San Angelo Power Station -Shrew Tap | $ 3,702,120 | San Angelo Power Station, to Menard 138 kV line improvements (09TPIT0212) |
| Watermill - West Levee SW & Sargent Road | Watermill – DeSoto | $ 1,545,708 | Trinidad – Watermill 345kV line (07TPIT0140) |
| Dilley Switch - San Miguel 138kV | Derby - Pearsall 69kV | $ 473,910 | Pearsall to Dilley 69 kV Line Upgrade (09TPIT0189) |
| Watermill – Tricorner & Trinidad 345kV | Watermill – DeSoto | $ 390,506 | Trinidad – Watermill 345kV line (07TPIT0140) |
| North Denton 138/69kV Autotransformer | North Denton 138/69kV Autotransformer | $ 233,598 |  |
| Austrop – Daffin & Decker 138kV | Austrop –Decker 138kV | $ 221,789 | Decker to Techridge 138kV Relocation (07TPIT0050) |
| Outages | Zorrillo Planned Outage | $ 175,321 |  |
| RPRS |  | $ 62,646 |  |
| W_N Stability |  | $ 59,422 |  |

Binding Constraints – September, 2009 – DATA PENDING

| Contingency | Binding Element | Estimated Costs | Transmission Project |
| --- | --- | --- | --- |
| Oak Creek – Ballinger 138kV | Miles – Rowena 69kV | $ 2,547,232 | Yellow Jacket Phase Shifting Transformer addition (08TPIT0135) |
|  | Capacity Shortage | $ 1,622,568 |  |
| Oak Creek – Ballinger 138kV | Abilene South – Ballinger 69kV | $ 819,234 | Ballinger to Abilene South 69kV, rebuild (08TPIT0080) |
| Temple Pecan Creek - Tradinghouse & Temple Switch - Lake Creek SES | San Angelo Power Station -Shrew Tap | $ 370,342 | Yellow Jacket Phase Shifting Transformer addition (08TPIT0135) |
| Garfield - Onion Creek & Hicross AEN 138kV | Lytton Springs 345/138kV Autotransformer #4 | $ 338,471 | Lytton Springs Autotransformer, addition (10TPIT0058) |
| Tradinghouse SES - Venus Switch 345kV | Rogers Hill TU - Elm Mott 138kV | $ 327,011 | Elm Mott – Waco Northcrest 138kV, upgrade (10TPIT0091) |
| Dilley Switch - San Miguel 138kV | Derby - Pearsall 69kV | $ 199,939 | Pearsall to Dilley 69 kV Line Upgrade (09TPIT0189) |
| Everman Switch - Sherry Switch 345kV | Everman Switch - Oak Hill 2 Tap 138kV | $ 129,597 |  |
| Hillje - Holman 345kV | Columbus - Stafford Hill 69kV | $ 79,526 |  |
| North Denton 138/69kV Autotransformer | North Denton 138/69kV Autotransformer | $ 69,064 |  |

Inter-zonal Congestion Costs – last 13 months

# Other Notable Activities

  - The reliability phase of the 2009 Five-Year Transmission Plan utilizing the latest SSWG base cases is nearly complete.  Projects to eliminate unserved energy in 2010-2014 have been identified.  Projects to reduce congestion in 2014 have been identified and communicated with the TSPs and other market participants.  Projects to reduce congestion in 2010 through 2013 are currently being studied.

  - Voltage Ride Through Study  Update:

    - Following the development of an acceptable “wind flat start” for the two study cases, High Wind High Load and High Wind Low Load, the simulation of dynamic events comprised of normally cleared and delayed clearing events is 100%. The analysis of the results and Phase I draft report documentation is underway.

    - A second email was sent to WGRs for data submission of VRT capability and more responses have been received. WGRs with no response to the second reminder email have been put in direct contact with ERCOT in order to facilitate timely data collection for Phase II. The data submitted by the remainder of the WGRs is being validated, especially in terms of dynamic models for the respective resources in PSS/E Version 31

    - Options associated with utilizing the data collected by means of the VRT Study Data Request Form to develop equivalents for wind farm collection systems are being investigated

  - The West-to-North Stability Limit study Phase II Update:Operations Planning released a revised W-N stability limit set in September, that added limit values with the CTs at Permian Basin and Morgan Creek out of service.  The resulting new stability limits are appreciably larger than in the previous limit set. The same revisions have been applied to the data set in the System Planning study as well. Work on the project has been underway since mid-September and is on course to being completed within the three month time-frame given in the last report in December 2009.

  - The ERCOT TPIT update for November 1, 2009 is in progress.