## 2009
No. | PWG 2009 Goals | Target Date | % Complete
7 | IDR Analysis – 2 issues outstanding from original analysis. | 2009-04-30 | 100%
11 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16, 2007) | 2009-06-30 | 100%
16 | The shift in proportion of UFE to NIDR metered premises as AMS matures | 2009-07-18 | 100%
1 | Review 2008 UFE Analysis (April 30, true-up in Aug or Sept) | 2009-08-23 | 100% | Chg
15 | UFE allocation factors in lieu of AMS meter installations | 2009-08-23 | 100% | Chg
14 | Evaluate language changes for Annual Validation Process due to AMS | 2009-09-14 | 50% | Chg
2 | 2009 Annual Validation. (Survey for 2010) | 2009-10-01 | 50% | Chg
4 | Review Weather Sensitivity Correlation | 2009-12-31 | 0%
5 | Review Proxy Day Method | 2009-12-31 | 0%
10 | Reevaluate distribution loss methodology due to advanced metering. | 2009-12-09 | 50% | Chg
17 | Distribution loss factors in relation to UFE | 2009-12-09 | 50% | Chg
12 | Update Long Term Strategy of Load Profiles including refreshed timeline | 2009-12-02 | 5% | Chg
6 | Evaluate Hurricane Ike affect on settlement for possible improvements | 2009-12-09 | 10%
3 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2009-12-31 | 5% | Chg
8 | Review profile models using Round 2 load research data, review if having more weather stations adds accuracy, and review if the weighting of weather stations is appropriate. | 2009-12-31 | 0%
9 | Improve Business Profile ID assignment process (pending AMS Metering) | 2009-12-31 | 0%
13 | Demand Response LPG or PRR language changes as needed | 2009-12-31 | 0%
Complete
NEW
Carry over to 2010
Combined