## Sheet1
|  |  | Submitter Information |  | CEO Determination |  | Approval Information |  |  |  | Priority / Rank |  |  | Impact Analysis | [5 empty] | Impacted Systems
# | Source | Description | Submitter | Posting Date | Needed for Go-Live? | Posting Date | Status | PRS | TAC | Board | Priority | Rank | Comments | Cost Impact | Schedule Impact | Resource Impact | Other | Planned Release | Dependencies | EMS | MMS | OS | MOTE | OTS | NMMS | COMS S&B | COMS Reg | COMS DA | COMS CMM | CRR | EDW | CDR | INF / MPIM | MER | MIS | EIP | INT
Approved | [10 empty] | Approved | [8 empty] | Approved
In Stakeholder Process | [10 empty] | In Stakeholder Process | [8 empty] | In Stakeholder Process
131 | NPRR | Ancillary Service Trades with ERCOT | NRG Texas | 2008-05-15 | No | 2009-10-07 | Tabled at PRS | 2008-06-19 |  |  |  |  | Deemed "Approved Post-Go-Live" by TPTF | TBD | TBD | TBD |  | TBD |  | 4 | 1 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 1 | 4 | 1 | 1 | 4 | 4 | 4 | 4 | 4
146 | NPRR | ICCP Telemetry Information Submittals | AEP | 2008-07-31 | TBD |  | Tabled at TAC | 2008-09-24 |  |  |  |  | Deemed "Approved Post-Go-Live" by TPTF | TBD | TBD | TBD |  | TBD |  | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
153 | NPRR | Generation Resource Fixed Quantity Block Offer | TPTF | 2008-09-12 | No | 2009-10-05 | Tabled at PRS | [5 empty] | Deemed "Approved Post-Go-Live" by TPTF | TBD | TBD | TBD |  | TBD |  | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 4 | 4 | 4
156 | NPRR | Transparency for PSS and Full Interconnection Studies | PSEG Texas | 2008-09-19 | No | 2009-05-11 | Tabled at PRS | 2009-04-23 | [5 empty] | TBD | TBD | TBD |  | TBD
164 | NPRR | Resubmitting Ancillary Service Offers in SASM | TPTF | 2008-11-11 | No | 2009-10-05 | Tabled at PRS | 2008-11-20 |  |  |  |  | Deemed "Approved Post-Go-Live" by TPTF | $100k-$250k + $6M-$8M | TBD | TBD |  | TBD |  |  | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 4 | 4 | 4
169 | NPRR | Clarify the Calculation and Posting of LMPs for the Load Zone and LMPs for each Hub | TPTF | 2008-12-15 | No | 2009-09-10 | Tabled at PRS | 2008-12-18 | [5 empty] | TBD | TBD | TBD |  | TBD |  | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 4 | 3 | 2 | 4 | 1
181 | NPRR | FIP Definition Revision | Luminant | 2009-06-10 | No | 2009-06-10 | Tabled at PRS | [6 empty] | TBD | TBD | TBD |  | TBD
756 | SCR | Enhancements to the MarkeTrak Application | MTTF | 2009-05-06 | No | 2009-06-19 | Tabled at RMS | [6 empty] | TBD | TBD | TBD |  | TBD
755 | SCR | ERCOT.com Website Enhancements | CCWG | 2009-02-25 | No | 2009-06-04 | Tabled at COPS | [6 empty] | TBD | TBD | TBD |  | TBD
757 | SCR | Real-Time Wind Production by Zone | AEP | 2009-09-08 | No | 2009-09-08 | Pending at WMS | [6 empty] | TBD | TBD | TBD |  | TBD