## Requirements_Redline_Tracking
Requirement Documents | Redlines received from business | Target date for posting to nodal.ercot.com | Posted
COMS - Average Incremental Energy Cost Settlements Requirements (B2) v3.0 Redline v3.04 | y | 2009-10-16 | 2009-10-13
COMS - Black-Start Services Real-Time Settlements Requirements (B2) v3.0 Redline v 3.05 | y | 2009-10-16 | 2009-10-13
COMS - Commercial Systems Commercial Systems Integration Requirements (B3) V0.01 | will be 10/30/09 | 2009-11-06
COMS - Congestion Revenue Rights Auction Revenue Distribution Requirements (B2) v3.0 Redline v 3.05 | y | 2009-10-16 | 2009-10-13
COMS - Congestion Revenue Rights Balancing Account Settlements Requirements (B2) v3.0 Redline v 3.02 | y | 2009-10-16 | 2009-10-13
COMS - Credit Monitoring and Management Requirements v2.0 | no modifications | no posting
COMS - Data Aggregation Requirements (B2) v3.0 Redline v 3.01 | y | 2009-10-16 | 2009-10-24
COMS - Day-Ahead Market Ancillary Service Settlements Requirements (B2) v3.0 Redline v 3.02 | y | 2009-10-16 | 2009-10-13
COMS - Day-Ahead Market Congestion Revenue Rights Settlements Requirements (B2) v3.0 Redline v 3.05 | y | 2009-10-16 | 2009-10-14
COMS - Day-Ahead Market Energy Settlements Requirements (B2) v3.0 Redline v 3.02 | y | 2009-10-16 | 2009-10-14
COMS - Day-Ahead Market Make-Whole Settlements Requirements (B2) v3.0 Redline v 3.05 | y | 2009-10-16 | 2009-10-14
COMS - Dispute Management Requirements (B2) v3.0 | no modifications | no posting
COMS - Eligibility Process for Settlements Requirements (B2) v3.0 Redline v5.06 | y | 2009-10-16 | 2009-10-14
COMS - Financial Transfer Requirements (B2) v3.0 Redline v 3.5 | y | 2009-10-16 | 2009-10-14
COMS - Market Data Transparency Requirements v1.0 | no modifications | no posting
COMS - Real-Time Ancillary Services Settlements Requirements (B2) v3.0 Redline v 3.03 | y | 2009-10-16 | 2009-10-14
COMS - Real-Time Congestion Revenue Rights Settlements Requirements (B2) v3.0 Redline v3.03 | y | 2009-10-16 | 2009-10-14
COMS - Real-Time Emergency Operations Settlements Requirements (B2) v3.0 Redline v3.5 | y | 2009-10-16 | 2009-10-14
COMS - Real-Time Energy Settlements Requirements (B2) v3.0 Redline v3.01 | y | 2009-10-16 | 2009-10-15
COMS - Real-Time Reliability Must-Run Services Settlements Requirements (B2) v3.0 Redline 3.12 | y | 2009-10-16 | 2009-10-14
COMS - Registration Requirements (B2) v3.0 | no modifications | no posting
COMS - Reliability Unit Commitment Settlements Requirements (B2) v3.0 Redline v3.01 | y | 2009-10-16 | 2009-10-14
COMS - Settlement Invoice Requirements (B3) v3.0 Redline v3.06 | y | 2009-10-16 | 2009-10-14
COMS - Settlement Statement Requirements (B2) v3.0 Redline v3.04 | y | 2009-10-16 | 2009-10-15
COMS - Verifiable Costs Requirements (B2) v3.0 Redline v3.01 | y | 2009-10-16 | 2009-10-15
COMS - Voltage Support Real-Time Settlements Requirements (B2) v3.0 Redline v3.08 | y | 2009-10-16 | 2009-10-16
COMS/EDW - Consolidated Market Data Transparency Specifications v0.01 | will be 11/6/09 | 2009-11-13
CRR - Requirements (B2) v4.0 | will be 10/30/09 | 2009-11-06
EDW Market Monitoring and Data Collection Requirements v1.0 | will be 11/6/09 | 2009-11-13
EDW State Estimator and Telemetry Reports Business Specifications v1.0 | will be 11/6/09 | 2009-11-13
EMS - Data Models Requirements (B2) v2.0 Redline v2_01 Blackline v3_0 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Dynamic Ratings Requirements (B2) v2.0 Blackline v3_0 Redline v2_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Forced Outage Detection Requirements (B2) v2.0 Redline v2_01 Blackline v3_0 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Generation Subsystem Requirements (B2) v3.0 Redline v3_01 Blackline v4_0 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Load Forecasting Requirements Specification (B2) v3.0 Redline v3_01 Blackline v4_0 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Network Security and Stability Analysis Requirements Specification (B2) v3.0 Blackline v4_0 Redline v3_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Outage Evaluation Requirements (B2) v2.0 Blackline v3_0 Redlinev2_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - State Estimator Requirements Specification (B2) v3.0 Blackline v4_0 Redline v3_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Supervisory Control and Data Acquisition Requirements Specification (B2) v2.0 Redline v2_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Voltage Support Requirements Specification (B2) v2.0 Redline v2_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS - Wind Power Forecasting Requirements Specification (B2) v3.0 Blackline v4_0 Redline v3_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
EMS/MMS - Market Operations Test Environment Requirements (B2) v1.0 | no modifications | no posting
MIS - Business Requirements for Notices, Notifications, Alarms and Alerts v1.0 | will be 10/30/09 | 2009-11-06
MIS - Web Portal Requirements (B2) v2.0 | will be 10/30/09 | 2009-11-06
MMS - Constraint Competitiveness Test Requirements Specification (B2) v2.0 Redline v2_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
MMS - Day-Ahead Market and Supplemental Ancillary Service Market Requirements Specification (B2) v3.0 Redline v3_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
MMS - Outage Scheduler Requirements Specification v1.0 Redline v1_4 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
MMS - Overall Market Management System and Other Processes Requirements (B2) v2.0 Redline v2_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
MMS - Reliability Unit Commitment Requirements Specification (B2) v2.0 Redline v2_01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
MMS - Security-Constrained Economic Dispatch and Real-Time MMS Processes Requirements (B2) v3.0 Redline v3.01 | y | 2009-10-23 | redline - archives page blackline - requirements page 10/15/09
NMMS - Requirements v1.0 | will be 10/30/09 | 2009-11-06