## Guidelines
Rules for Submission of Large Volume of Transactions
Block out all maintenance and release windows
Block out ERCOT holidays
Block out Tuesday or Wednesday, if possible.
Rate of Submission:
During the week
Prior to 5 PM
Submit transactions at a rate of once an hour
In bundles that are no more than 33,000 transactions at a time
OR
After 5 PM
No restrictions as to rate or number of transactions
On weekends
No restrictions as to rate or number of transactions
Updates:
I moved out the first day of sending 814_20s to the Tuesday after implementation.
Blocked the Wednesday of that week.
Moved Oncor's numbers out and added 5,500 814_20s to each day in schedule for the meter change.
Original schedule - Oncor dropped to maintenance levels on December 17th
New schedule - Oncor drops to maintenance levels on January 4th
Extends schedule about 2 weeks

## Draft Timeline
NOVEMBER 22, 2009 ERCOT Go=Live
| November |  |  |  |  | cycle send |  |  | December | [8 empty] | January
|  | Max # | Oncor | CenterPoint | Remaining |  | Oncor cycle # | ONCOR Cycle for 814 20 Profile Changes |  | Max # | Oncor 814 20 profile chg count | Oncor Meter Change Counts | CenterPoint 814 Count | ERCOT Remaining 814 20 Capacity | CenterPoint Meter Cycle | Oncor cycle # | ONCOR Cycle for 814 20 Profile Changes |  | Max # | Oncor 814 20 profile chg count | Oncor Meter Change Counts | CenterPoint 814 Count | ERCOT Remaining 814 20 Capacity | CenterPoint Meter Cycle
Tues | 3 | [5 empty] | 10 |  | 1 |  |  | 7000 | 2000
Wed | 4 | [5 empty] | 11 |  | 2 | 60000 |  | 7000 | 2000 | 51000 | cycle 7 and 8
Thurs | 5 | [5 empty] | 12 |  | 3 | 60000 |  | 7000 | 11560 | 41440 | cycle 9
Fri | 6 | [5 empty] | 13 | 2 | 4 | 60000 | 25000 | 7000 | 16773 | 11227 | cycle 10 |  |  | 1 | New Year's Weekend
Sat | 7 | [6 empty] | 3 | 5 | 100000 | 25000 | 8000 | 17511 | 49489 | cycle 11 |  |  | 2
Sun | 8 | [7 empty] | 6 | [8 empty] | 3
Mon | 9 | [5 empty] | 14 | 4 and 5 | 7 | 60000 | 50000 | 7000 | 2238 | 762 | cycle 12 | 10 | 20 21 | 4 | 60000 | 50000 | 7000 |  | 3000 | cycle 6 and 7
Tues | 10 | [5 empty] | 15 |  | 8 |  |  | 7000 | 2000 | -9000 |  | 11 |  | 5 |  |  | 7000 | 3000 | -10000
Wed | 11 | [5 empty] | 16 | 6 | 9 | 60000 | 25000 | 7000 | 2000 | 26000 | cycle 13 | 12 | 1 | 6 | 60000 | 25000 | 7000 | 2505 | 25495 | cycle 8 and 9
Thurs | 12 | [5 empty] | 17 |  | 10 | 60000 |  | 7000 | 8388 | 44612 | cycle 14 | 13 |  | 7 | 60000 |  | 7000 | 5680 | 47320 | cycle 10
Fri | 13 | [5 empty] | 18 | 7 | 11 | 60000 | 25000 | 7000 | 3852 | 24148 | cycle 15 | 14 |  | 8 | 60000 |  | 7000 | 5796 | 47204 | cycle 11
Sat | 14 | PR80027 Go Live | [6 empty] | 12 | December Retail Release | [7 empty] | 9 | 100000 |  | 8000 | 3911 | 88089 | cycle 12
Sun | 15 | [7 empty] | 13 | [8 empty] | 10
Mon | 16 | [5 empty] | 19 | 8 9 | 14 | 60000 | 50000 | 7000 | 8038 | -5038 | cycle 16 and 17 | 15 |  | 11 | 60000 |  | 7000 |  | 53000 | cycle 13
Tues | 17 | [5 empty] | 20 |  | 15 |  |  | 7000 | 2000 | -9000 |  | 16 |  | 12 |  |  | 7000 | 3000 | -10000
Wed | 18 | [5 empty] | 21 | 10 11 | 16 | 60000 | 50000 | 7000 | 8772 | -5772 | cycle 18 | 17 |  | 13 | 60000 |  | 7000 | 7198 | 45802 | cycle 14
Thurs | 19 | [5 empty] | 1 |  | 17 | 60000 |  | 7000 | 2000 | 51000 | cycle 19 | 18 |  | 14 | 60000 |  | 7000 | 3614 | 49386 | cycle 15
Fri | 20 | [5 empty] | 2 | 12 | 18 | 60000 | 25000 | 7000 | 2145 | 25855 | cycle 20 | 19 |  | 15 | 60000 |  | 7000 | 3000 | 50000 | cycle 16
Sat | 21 | [6 empty] | 13 | 19 | 100000 | 25000 | 8000 | 2000 | 65000 | cycle 21 |  |  | 16 | 100000 |  | 8000 | 4778 | 87222 | cycle 17
Sun | 22 | [7 empty] | 20 |  |  |  |  | 0 |  |  |  | 17
Mon | 23 | 60000 |  |  | 60000 |  | 3 | 14 15 | 21 | 60000 |  | 7000 | 5185 | 47815 | cycle 1 | 20 |  | 18 | 60000 |  | 7000 | 1362 | 51638 | cycle 18
Tues | 24 |  |  | 2000 |  |  | 4 |  | 22 |  |  | 7000 | 2000 | -9000 |  | 21 |  | 19 |  |  | 7000 | 3000 | -10000
Wed | 25 | 60000 |  | 2000 | 60000 |  | 5 | 16 | 23 | 60000 | 25000 | 7000 | 11595 | 16405 | cycle 2 | 1 |  | 20 | 60000 |  | 7000 | 3000 | 50000 | cycle 19
Thurs | 26 | Thanksgiving Weekend | [6 empty] | 24 | Christmas Weekend | [5 empty] | 2 |  | 21 | 60000 |  | 7000 | 3000 | 50000 | cycle 20
Fri | 27 | [7 empty] | 25 | [6 empty] | 3 |  | 22 | 60000 |  | 7000 | 3000 | 50000 | cycle 21
Sat | 28 | [7 empty] | 26 | [8 empty] | 23 | January Retail Release
Sun | 29 | [7 empty] | 27 | [8 empty] | 24
Mon | 30 | 60000 |  |  | 60000 | cycle 6 | 6 |  | 28 |  |  | 7000 |  | -7000 |  | 4 |  | 25 | 60000 |  | 7000 | 3832 | 49168 | cycle 1 and cycle2
Tues | [6 empty] | 7 |  | 29 |  |  | 7000 | 2000 | -9000 |  | 5 |  | 26 |  |  | 7000 | 3000 | -10000
Wed | [6 empty] | 8 | 17 18 | 30 | 60000 | 50000 | 7000 | 7096 | -4096 | cycle 3 and 4 | 6 |  | 27 | 60000 |  | 7000 | 3000 | 50000 | cycle 3
Thurs | [6 empty] | 9 | 19 | 31 | 60000 | 25000 | 7000 | 2000 | 26000 | cycle 5 | 7 |  | 28 | 60000 |  | 7000 | 3664 | 49336 | cycle 4
11-23 schedule meter read for cycle 6
11-24 process in CIS
11-25 send 867_03 to ERCOT
11-26 TO 11-29 Thanksgiving
11-30 validate 867-03's are loaded
11/30 send 1st file of AMS load profile changes * based on what is automation ready for reads, there are 0 for cycle 6
** 2000 average AMS meter installs each day |  |  |  | 2009

## timing
cycle | read date | process in cis | 867_03 to ercot | validate | send 814_20
cycle 6 | 2009-11-23 | 2009-11-24 | 2009-11-25 | 2009-11-30 | 2009-11-30
cycle 7 | 2009-11-24 | 2009-11-25 | 2009-11-30 | 2009-12-01 | 2009-12-02 | 12/1 black out
cycle 8 | 2009-11-25 | 2009-11-30 | 2009-12-01 | 2009-12-02 | 2009-12-02
cycle 9 | 2009-11-30 | 2009-12-01 | 2009-12-02 | 2009-12-03 | 2009-12-03
cycle 10 | 2009-12-01 | 2009-12-02 | 2009-12-03 | 2009-12-04 | 2009-12-04
cycle 11 | 2009-12-02 | 2009-12-03 | 2009-12-04 | 2009-12-05 | 2009-12-05
cycle 12 | 2009-12-03 | 2009-12-04 | 2009-12-05 | 2009-12-06 | 2009-12-07
cycle 13 | 2009-12-04 | 2009-12-07 | 2009-12-08 | 2009-12-09 | 2009-12-09
cycle 14 | 2009-12-07 | 2009-12-08 | 2009-12-09 | 2009-12-10 | 2009-12-10
cycle 15 | 2009-12-08 | 2009-12-09 | 2009-12-10 | 2009-12-11 | 2009-12-11 | Dec 12, 13 black out |  | ercot outage | (12:00pm Saturday until 12:00am Monday
cycle 16 | 2009-12-09 | 2009-12-10 | 2009-12-11 | 2009-12-12 | 2009-12-14 | Dec 15 black out
cycle 17 | 2009-12-10 | 2009-12-11 | 2009-12-12 | 2009-12-13 | 2009-12-14
cycle 18 | 2009-12-11 | 2009-12-14 | 2009-12-15 | 2009-12-16 | 2009-12-16
cycle 19 | 2009-12-14 | 2009-12-15 | 2009-12-16 | 2009-12-17 | 2009-12-17
cycle 20 | 2009-12-15 | 2009-12-16 | 2009-12-17 | 2009-12-18 | 2009-12-18 | Dec 20 black out day
cycle 21 | 2009-12-16 | 2009-12-17 | 2009-12-18 | 2009-12-19 | 2009-12-19
cycle 1 | 2009-12-17 | 2009-12-18 | 2009-12-19 | 2009-12-20 | 2009-12-21 | Dec 22 black out day
cycle 2 | 2009-12-18 | 2009-12-21 | 2009-12-22 | 2009-12-23 | 2009-12-23
cycle 3 | 2009-12-21 | 2009-12-22 | 2009-12-23 | 2009-12-24 | 2009-12-30 | 12/24 through 12/29 black out
cycle 4 | 2009-12-22 | 2009-12-23 | 2009-12-24 | 2009-12-28 | 2009-12-30
cycle 5 | 2009-12-23 | 2009-12-28 | 2009-12-29 | 2009-12-30 | 2009-12-31
cycle 6 | 2009-12-28 | 2009-12-29 | 2009-12-30 | 2009-12-31 | 2010-01-04 | Jan 1st , 2nd and 3rd black out day
cycle 7 | 2009-12-29 | 2009-12-30 | 2009-12-31 | 2010-01-01 | 2010-01-04
cycle 8 | 2009-12-30 | 2009-12-31 | 2010-01-01 | 2010-01-02 | 2010-01-06
cycle 9 | 2009-12-31 | 2010-01-04 | 2010-01-05 | 2010-01-06 | 2010-01-06
cycle 10 | 2010-01-04 | 2010-01-05 | 2010-01-06 | 2010-01-07 | 2010-01-07
cycle 11 | 2010-01-05 | 2010-01-06 | 2010-01-07 | 2010-01-08 | 2010-01-08
cycle 12 | 2010-01-06 | 2010-01-07 | 2010-01-08 | 2010-01-09 | 2010-01-09 | Jan 10th | black out
cycle 13 | 2010-01-07 | 2010-01-08 | 2010-01-09 | 2010-01-10 | 2010-01-11
cycle 14 | 2010-01-08 | 2010-01-11 | 2010-01-12 | 2010-01-13 | 2010-01-13
cycle 15 | 2010-01-11 | 2010-01-12 | 2010-01-13 | 2010-01-14 | 2010-01-14
cycle 16 | 2010-01-12 | 2010-01-13 | 2010-01-14 | 2010-01-15 | 2009-01-15
cycle 17 | 2010-01-13 | 2010-01-14 | 2010-01-15 | 2010-01-16 | 2010-01-16 | 1/19 black out
cycle 18 | 2010-01-14 | 2010-01-15 | 2010-01-16 | 2010-01-17 | 2010-01-18
cycle 19 | 2010-01-15 | 2010-01-18 | 2010-01-19 | 2010-01-20 | 2009-01-20
cycle 20 | 2010-01-18 | 2010-01-19 | 2010-01-20 | 2010-01-21 | 2010-01-21
cycle 21 | 2010-01-19 | 2010-01-20 | 2010-01-21 | 2010-01-22 | 2010-01-22 | 1/23 and 1/24 black out
cycle 1 | 2010-01-20 | 2010-01-21 | 2010-01-22 | 2010-01-23 | 2009-01-25 | 1/26 black out
cycle 2 | 2010-01-21 | 2010-01-22 | 2010-01-23 | 2010-01-24 | 2010-01-25
cycle 3 | 2010-01-22 | 2010-01-25 | 2010-01-26 | 2010-01-27 | 2010-01-27
cycle 4 | 2010-01-25 | 2010-01-26 | 2010-01-27 | 2010-01-28 | 2010-01-28