## Slide 1: Nodal Program Update
Jason Iacobucci
Nodal Program Manager
Technical Advisory Committee
5 November 2009
Notes: <number>

## Slide 2: Agenda
Technical Advisory Committee
5 November 2009
Program Status
Traceability
Market Readiness
Follow-Up Discussion
Notes: <number>
<number>

## Slide 3: Nodal Systems Blueprint
5 November 2009
Technical Advisory Committee

## Slide 4: Nodal Timeline
Technical Advisory Committee
5 November 2009
Notes: <number>

## Slide 5: Market Trials Roadmap
Technical Advisory Committee
5 November 2009
Notes: <number>

## Slide 6: Completed Milestones
  Program Milestone: Phase 2.1 Market Connectivity
  Included the following project milestones
    Readiness/Market Readiness/External Outreach & Training
      Phase 2.1 Market Connectivity Handbook posted Oct. 2; Market Readiness Seminar Oct. 8 (approx. 140 MPs); completed first 7 of 33 MP site visits
    Market Trials/Phase 2.1 Connectivity Testing/MT External Testing
      Phase 2.1 kickoff Oct. 8; Technical Workshop Oct. 28
    Readiness/Market Readiness/Metrics Tracking & Assessment
      Phase 2.1 Commencement Criteria met: readiness review complete
    Integration/Phase 2.1 Connectivity Testing/Integration Testing
      Phase 2.1 testing complete: known issues list posted for Market Trials
    Readiness/Operational Readiness/Environment Configuration & Management
      Phase 2.1 run books and monitoring: IT review complete
    Readiness/Operational Readiness/Security Testing
      Performance testing: Web Services and user interfaces (UI) benchmarks complete
      Security testing complete
    Readiness/Operational Readiness/Environment Configuration & Management
      Phase 2.1 NPROD build complete: final code installed and tested
Technical Advisory Committee
5 November 2009
Notes: <number>

## Slide 7: Near-Term Milestones: Detailed Status (10-29-09)
Program Milestones
  Phase 3: Real-Time Markets
  Project Milestones (look-ahead)
Technical Advisory Committee
5 November 2009
Project Milestone | Status | Detail
Readiness/ Environment Configuration & Mgmt/ Phase 3-6 NPROD Build Complete | Complete | Infrastructure build complete.
Readiness/ Load & Performance/ Phase 3 Performance Testing | On target | Planning in progress
Integration/ Integrated Testing/ Phase 3 Testing | On target | Planning complete Integrated testing under way (CRR, OS, SCED) Running Real-Time operating scenarios twice weekly
Integration/ Integrated Testing/ Phase 3 Kickoff | On target | Meeting to be held in early January

## Slide 8: Future Program Milestones
Technical Advisory Committee
5 November 2009
Phase | When | Scope | Status
3: Real-Time Markets | Mid January-Early February | MMS-SCED execution SCED results, report publishing CRR auction execution (CRR UI) OS submissions (API, OS UI) | Planning complete Integrated testing under way (CRR, OS, SCED) Running Real-Time operating scenarios twice weekly
4: DAM/RUC | Late March-Early April | MMS-DAM, DRUC, HRUC, SCED execution Market results, report publishing Initial S&B execution Outage, CRR integration | Planning in progress Integrated testing under way Executing DAM mechanics
5: Full Functionality | Late April-Early May | Run full nodal systems | Planning in progress Internal DST test Nov. 1

## Slide 9: Nodal Program Risks & Issues
Technical Advisory Committee
5 November 2009
Risk/Issue | Priority | Target | Status
Integration Testing Continued risk around technology delivery of business systems integration due to complexity and continuing maturing of application and data dependencies. | Medium | May 2010 | On track; test phase planning, work plan complete. Execution of work plan, with specific focus on January Market Trials functionality, under way. Daily meetings being held.
Reconciling Protocols, Systems and Market Expectations Experience by other ISOs in deploying nodal markets has shown that expectations of the market participants are often missed, despite best efforts at defining tariffs or protocol requirements. ERCOT needs to assume such a risk exists for this nodal implementation as well. | High | 12/15/09 | On track; work underway to trace protocols, requirements and business processes alignment analyses are in progress. SMEs added to the team in May.
Data Center Expansion Capacity Concerns Data center capacity, space and power may be inadequate for Nodal Go-Live, unless plans for expansion are adequate. | Medium | 3/31/10 | Taylor capacity risk fully mitigated. Austin capacity constraint will continue until Met facility is replaced. Capacity sufficient for Go-Live.
Internet Explorer Upgrade Nodal Integration testing for the Market Participant (MP) User Interfaces and MIS reporting is using Internet Explorer (IE) version 6. MPs have requested ERCOT support a newer version: IE7 (IE8 is also available). If the nodal market-facing application requires certification against other IE versions, there will be internal and external costs associated with re-testing and updating the UIs. | High | 12/31/09 | On track. ERCOT Enterprise Architecture team completed initial Zonal analysis and developed options. Nodal Impact assessment to be completed in parallel with Integration Testing over the next several weeks.
Market Interaction Operating Level Agreements (OLAs) Need to determine operating level agreements associated with market interactions to assist ERCOT in establishing operational thresholds. ERCOT is responsible for ensuring any market thresholds required before Go-Live are defined, managed through the appropriate stakeholder processes and communicated in a timely fashion. | High | April/May 2010 | On track. Phase 2.1 OLAs established and communicated to the market during Oct. 8 Market Readiness Seminar. Phase 3 and 4 OLA definitions in process
Notes: <number>

## Slide 10: Program Risk: Reconciling Protocols, Systems and Market Expectations
Technical Advisory Committee
5 November 2009
Risk: Reconciling Protocols, Systems and Market Expectations |  |  |  | Experience with deploying nodal markets by other ISOs has shown that expectations of the market participants are often missed, despite best efforts at defining tariffs or protocol requirements. ERCOT needs to assume such a risk exists for this nodal implementation as well. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Assess maturity and readiness of software in the initial nodal release, focusing on new/tailored capability for Texas Nodal. |  |  |  | B. Day K. Farley | 12/22/09 (revised) | 11/02/09 – SMEs are working with business owners on research and alignment items. NATF web ex for 11/30/09 and 12/18/09 to review full trace reports with Market Participants.
2. Add team members to the nodal program with Texas market experience to ensure readiness for Market Trials. SMEs to discussion alignment issues with ERCOT business owners. SMEs to report the results of the assessment to the ERCOT business owners for resolution. |  |  |  | B. Day K. Farley | Ongoing | 11/02/09 – Work is underway to trace protocols, requirements and business processes alignment analyses are in progress.
3. Keep the oversight groups apprised of progress. |  |  |  | M. Cleary | Ongoing | 11/02/09 – status reports provided to program, NATF, TAC, Special Nodal Committee monthly.
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 11: Protocol Traceability Effort Update
Tier 1 Sections |  |  |  |  | 
 | PTE Traced Items | Research Items | In Progress: Business Procedures | In Progress: Reports/ Extracts | PTE Alignment Items
Section 3 – Management Activities for the ERCOT system (Nov NATF) | 904 | 271 | 449 | 116 | TBD
Section 4 – Day Ahead Operations (Nov NATF) | 640 | 124 | 61 | 65 | TBD
Section 5 – Transmission Security Analysis and RUC (Nov NATF) | 167 | 28 | 58 | 8 | TBD
Section 6 – Adjustment Period and Real-Time Operations (Dec NATF) | 921 | 168 | 434 | 52 | TBD
Section 7 – Congestion Revenue Rights (Oct NATF) | 481 | 68 | 85 | 29 | 1
Section 8 – Performance Monitoring (Dec NATF) | 224 | 86 | 149 | 2 | TBD
Section 9 – Settlement & Billing (Nov NATF) | 410 | 0 | 0 | 0 | TBD
Section 16.11 – Financial Security for Counter Parties (Dec NATF) | 200 | 109 | 9 | 1 | TBD
Section 17 – Market Monitoring & Data Collection (Dec NATF) | 25 | 3 | 21 | 1 | TBD
Total | 3972 | 800 | 1266 | 274 | TBD
5 November 2009
Technical Advisory Committee

## Slide 12: Protocol Traceability Effort Update
Tier 1 Sections |  |  |  |  | 
 | PTE Traced Items | Research Items | In Progress: Business Procedures | In Progress: Reports / Extracts | PTE Alignment Items
Section 7 – Congestion Revenue Rights (Oct NATF) | 481 | 68 | 85 | 29 | 1
Section 3 – Management Activities for the ERCOT system (Nov NATF) | 904 | 271 | 449 | 116 | TBD
Section 4 – Day Ahead Operations (Nov NATF) | 640 | 124 | 61 | 65 | TBD
Section 5 – Transmission Security Analysis and RUC (Nov NATF) | 167 | 28 | 58 | 8 | TBD
Section 6 – Adjustment Period and Real-Time Operations (Dec NATF) | 921 | 168 | 434 | 52 | TBD
Section 8 – Performance Monitoring (Dec NATF) | 224 | 86 | 149 | 2 | TBD
Section 9 – Settlement & Billing (Nov NATF) | 410 | 0 | 0 | 0 | TBD
Section 16.11 – Financial Security for Counter Parties (Dec NATF) | 200 | 109 | 9 | 1 | TBD
Section 17 – Market Monitoring & Data Collection (Dec NATF) | 25 | 3 | 21 | 1 | TBD
Total | 3972 | 800 | 1266 | 274 | TBD
PTE working with business owners to find answers in functional requirements
5 November 2009
Technical Advisory Committee

## Slide 13: Protocol Traceability Effort Update
Tier 1 Sections |  |  |  |  | 
 | PTE Traced Items | Research Items | In Progress: Business Procedures | In Progress: Reports / Extracts | PTE Alignment Items
Section 7 – Congestion Revenue Rights (Oct NATF) | 481 | 68 | 85 | 29 | 1
Section 3 – Management Activities for the ERCOT system (Nov NATF) | 904 | 271 | 449 | 116 | TBD
Section 4 – Day Ahead Operations (Nov NATF) | 640 | 124 | 61 | 65 | TBD
Section 5 – Transmission Security Analysis and RUC (Nov NATF) | 167 | 28 | 58 | 8 | TBD
Section 6 – Adjustment Period and Real-Time Operations (Dec NATF) | 921 | 168 | 434 | 52 | TBD
Section 8 – Performance Monitoring (Dec NATF) | 224 | 86 | 149 | 2 | TBD
Section 9 – Settlement & Billing (Nov NATF) | 410 | 0 | 0 | 0 | TBD
Section 16.11 – Financial Security for Counter Parties (Dec NATF) | 200 | 109 | 9 | 1 | TBD
Section 17 – Market Monitoring & Data Collection (Dec NATF) | 25 | 3 | 21 | 1 | TBD
Total | 3972 | 800 | 1266 | 274 | TBD
Business procedures being worked in preparation for Market Trials (ERT)
5 November 2009
Technical Advisory Committee

## Slide 14: Protocol Traceability Effort Update
Tier 1 Sections |  |  |  |  | 
 | PTE Traced Items | Research Items | In Progress: Business Procedures | In Progress: Reports / Extracts | PTE Alignment Items
Section 7 – Congestion Revenue Rights (Oct NATF) | 481 | 68 | 85 | 29 | 1
Section 3 – Management Activities for the ERCOT system (Nov NATF) | 904 | 271 | 449 | 116 | TBD
Section 4 – Day Ahead Operations (Nov NATF) | 640 | 124 | 61 | 65 | TBD
Section 5 – Transmission Security Analysis and RUC (Nov NATF) | 167 | 28 | 58 | 8 | TBD
Section 6 – Adjustment Period and Real-Time Operations (Dec NATF) | 921 | 168 | 434 | 52 | TBD
Section 8 – Performance Monitoring (Dec NATF) | 224 | 86 | 149 | 2 | TBD
Section 9 – Settlement & Billing (Nov NATF) | 410 | 0 | 0 | 0 | TBD
Section 16.11 – Financial Security for Counter Parties (Dec NATF) | 200 | 109 | 9 | 1 | TBD
Section 17 – Market Monitoring & Data Collection (Dec NATF) | 25 | 3 | 21 | 1 | TBD
Total | 3972 | 800 | 1266 | 274 | TBD
A subset of reports and extracts will be available during Market Trials
5 November 2009
Technical Advisory Committee

## Slide 15: Protocol Traceability Effort Update
Tier 1 Sections |  |  |  |  | 
 | PTE Traced Items | Research Items | In Progress: Business Procedures | In Progress: Reports / Extracts | PTE Alignment Items
Section 7 – Congestion Revenue Rights (Oct NATF) | 481 | 68 | 85 | 29 | 1
Section 3 – Management Activities for the ERCOT system (Nov NATF) | 904 | 271 | 449 | 116 | TBD
Section 4 – Day Ahead Operations (Nov NATF) | 640 | 124 | 61 | 65 | TBD
Section 5 – Transmission Security Analysis and RUC (Nov NATF) | 167 | 28 | 58 | 8 | TBD
Section 6 – Adjustment Period and Real-Time Operations (Dec NATF) | 921 | 168 | 434 | 52 | TBD
Section 8 – Performance Monitoring (Dec NATF) | 224 | 86 | 149 | 2 | TBD
Section 9 – Settlement & Billing (Nov NATF) | 410 | 0 | 0 | 0 | TBD
Section 16.11 – Financial Security for Counter Parties (Dec NATF) | 200 | 109 | 9 | 1 | TBD
Section 17 – Market Monitoring & Data Collection (Dec NATF) | 25 | 3 | 21 | 1 | TBD
Total | 3972 | 800 | 1266 | 274 | TBD
Business Owner proposes solution (Procedure, Protocol, or Requirements Change) which is checked against project scope, schedule, budget.
If there’s an impact, it will go through nodal change control process.
5 November 2009
Technical Advisory Committee

## Slide 16: Full Trace Report
What It Will Show:
  Protocol item and how it is covered by
    Functional Requirement
    Business Procedure Title
    EMIL Item
    Other document (Operating Guide or handbook)
What It Will Not show:
  Detail design information
  Test case/script information
    How are these covered?
    Will share overview/summary at December TAC meeting
5 November 2009
Technical Advisory Committee

## Slide 17: Full Trace Report
Technical Advisory Committee
What if there is an alignment item?
What is the process?
5 November 2009

## Slide 18: Full Trace Report
What is the expectation of the web ex meetings?
  Review of progress of all tier 1 sections (slide 10)
  Review of how to read the report
  Review of in-progress categories
  Review of alignment items and next steps
  Questions from MPs on specific items within a section
Questions about a research item or alignment item should be forwarded via e-mail to NodalMarketTransition@ercot.com. Subject line “Protocol Traceability Question”
5 November 2009
Technical Advisory Committee

## Slide 19: Reading a Trace Report
5 November 2009
Technical Advisory Committee

## Slide 20: Reading a Trace Report
5 November 2009
Technical Advisory Committee

## Slide 21: Protocol Traceability Effort Update
Tier 1 Sections |  |  |  | 
 | PTE Traced Items | Full Trace Report | Research Items | PTE Alignment Items
Section 7 – Congestion Revenue Rights | 481 | Posted 10/27 | 68 | 1
Research Item Review | 
# | Category / details
15 | Research needed with business owner. Includes identification of business procedure or report/extract and updates to CRR Business Requirements.
7 | Pending action by PTE team – review of answers provided by business owners
46 | Removing as result of NPRR195 being passed at BOD on 10/20
68 | Total above
Alignment Item Review |  |  | 
# | Category (Procedure, Protocol, Requirement) | Explanation | Change Control # / details
1 | Procedure | CRR Handbook – assigned, due 12/31/09 | n/a
5 November 2009
Technical Advisory Committee
Notes: <number>

## Slide 22: Next Steps
Questions about a research item or alignment item should be forwarded via e-mail to NodalMarketTransition@ercot.com. Subject line “Protocol Traceability Question”
Planned dates for Web Ex review
  Nov 30 – 9:30 am – 3:30pm – sections 3, 4, 5, 7, 9
  Dec 18 – 9:30 am – 3:30pm – sections 6, 8, 16.11, 17
  If needed Dec 22 – 9:30 am – 3:30pm
5 November 2009
Technical Advisory Committee
Notes: <number>

## Slide 23: Participant Readiness Touch Points
2009/2010
Technical Advisory Committee
5 November 2009
Meetings
Training
Outreach
Market trials
February
January
December
November
ERCOT & MP metrics
8 site visits
2 site visits
Metrics mapped to future phases
Bi-weekly calls
2.1 environment closed
Sandbox decommissioned
MP Handbooks
  SCED/LFC
  CRR
Bi-weekly calls
Voluntary MP connectivity testing
Voluntary market web services/UI re-qualification
NATF 12/8
Nodal 101
LSE 201
Generation 101, 201
Basic Training
Economics of LMP
Transmission 101
Settlement Workshop
Nodal 101
LSE 201
Generation 101, 201
Economics of LMP
Transmission 101
Settlement Workshop
Nodal 101
LSE 201
Generation 101, 201
CRR – online
Settlement Workshop
9 site visits
Initiate Phase 3 metrics
MRS #2
Start weekly calls
Mandatory QSE/CRRAH re-qualification begins
NATF 1/5
  MP Handbooks
  DAM/RUC
  Outage Scheduler
  COMS
Weekly calls
Phase 3 Market Trials initiates
QSE OS qualification
Nodal 101
LSE 201
Basic Training
Generation 101, 201
CRR – instructor-led
Settlement Workshop
Operations Seminar
Economics of LMP
NATF 2/2
7 site visits
Notes: <number>

## Slide 24: Market Participant Site Visits
Technical Advisory Committee
5 November 2009
7 Outreach Site Visits have been completed
Entity | Date
NRG TEXAS POWER | TBD
DIRECT ENERGY LP | 5-Jan
CPS ENERGY | 6-Jan
BRAZOS ELECTRIC | TBD
BTU (Bryan Texas Utilities) SERVICES | 13-Jan
TOPAZ POWER MANAGEMENT | 19-Jan
OCCIDENTAL | 20-Jan
SHELL ENERGY | 21-Jan
TENASKA POWER SERVICES | 26-Jan
OPTIM ENERGY | 27-Jan
APX | 3-Feb
NEXTERA ENERGY | 11-Feb
WIND PANEL (Houston) | 16-Feb
RETAIL PANEL (Houston) | 17-Feb
TRI-EAGLE ENERGY | 18-Feb
XTEND ENERGY LP | 2-Mar
EC AND R QSE | 9-Mar
Entity | Date
LOWER COLORADO RIVER AUTHORITY | 9-Oct
CALPINE CORP | 14-Oct
AUSTIN ENERGY | 20-Oct
CITY OF GARLAND | 21-Oct
GDF SUEZ ENERGY MARKETING | 29-Oct
ANP FUNDING | 3-Nov
LUMINANT ENERGY | 5-Nov
INVENERGY WIND DEVELOPMENT | 10-Nov
EXELON | 11-Nov
AMERICAN ELECTRIC POWER SERVICE | 12-Nov
CONSTELLATION ENERGY | 17-Nov
PSEG ENERGY RESOURCES | 18-Nov
FULCRUM POWER | 2-Dec
EAGLE ENERGY PARTNERS I LP | 3-Dec
STEC | 9-Dec
BP ENERGY COMPANY | 10-Dec
Confirmed Completed

## Slide 25: Readiness Scorecard Approach
Market Participant Readiness
2 Metrics initiate in November
  Telemetry Performance
  Resource Registration
<number>
http://scorecard.ercot.com
(example)
5 November 2009
Technical Advisory Committee
ERCOT Readiness Metrics
2 Metrics initiate in November
  Nodal Procedures
  Internal Nodal Training

## Slide 26: Resource Registration Updates and Progress
5 November 2009
2009
MAR APR MAY JUN JUL AUG SEP OCT NOV DEC
Private Use Network Transmission Data Collection
June Window - Non-Wind Transmission / Planning / Protection Data Collection
- Iteration 1
- Iteration 2
- Iteration 3
- Iteration 1
- Iteration 2
- Iteration 3
Private Use Network Planning and Protection Data Collection
September Window - Wind / All Remaining Sites Transmission / Planning / Protection Data Collection
- Iteration 1
- Iteration 2
- Iteration 3
Resource Node and Meter Mapping Verification
SEM GO-LIVE 8/31
EIS 1.19 to EDS 8/10
85% Prod Quality
95% Prod Quality
98% Prod Quality
85% Prod Quality
95% Prod Quality
98% Prod Quality
85% Prod Quality
95% Prod Quality
Final RARF Iterations
Kick Off Market Call
Technical Advisory Committee

## Slide 27: Resource Registration Updates and Progress
Technical Advisory Committee
RARF September Window Iteration 3: November 2-16
  Transmission assets owned by Resource Entities
  To date: 202 RARF sites; 145 accepted (72%)
  93 total RARF sites in September window
  42 RARFs submitted
  37 RARFs passed screening process
Resource Node Identification and Verification
  Dependent on accurate transmission asset registration.
  Begin before end of November
5 November 2009

## Slide 28: Resource Registration Escalations
Technical Advisory Committee
The following Resource Entities are not meeting the timeline for Registration Activities for transmission assets.
EC AND R PANTHER CREEK WIND FARM I AND II LLC (SOUTH)
MCADOO WIND ENERGY LLC
NAVASOTA ODESSA ENERGY PARTNERS LP
NAVASOTA WHARTON ENERGY PARTNERS LP
SCURRY COUNTY WIND LP
SNYDER WIND FARM LLC
STANTON WIND ENERGY LLC
TICONA POLYMER INC
TURKEY TRACK WIND ENERGY LLC
RARFs to confirm transmission assets not submitted since start of September Iterations
RARFs remaining to be corrected from June submissions
GREGORY POWER PARTNERS LP
THE DOW CHEMICAL CO
UNION CARBIDE CORP
If Resource Registration metric were turned on today:
10 Red
3 Amber
93 Green
5 November 2009

## Slide 29
Questions ?

## Slide 30
Appendix
Notes: <number>

## Slide 31: Program Risk: Reconciling Protocols, Systems and Market Expectations
Technical Advisory Committee
5 November 2009
Risk: Reconciling Protocols, Systems and Market Expectations |  |  |  | Experience with deploying nodal markets by other ISOs has shown that expectations of the market participants are often missed, despite best efforts at defining tariffs or protocol requirements. ERCOT needs to assume such a risk exists for this nodal implementation as well. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Assess maturity and readiness of software in the initial nodal release, focusing on new/tailored capability for Texas Nodal. |  |  |  | B. Day K. Farley | 12/22/09 (revised) | 11/02/09 – SMEs are working with business owners on research and alignment items. NATF web ex for 11/30/09 and 12/18/09 to review full trace reports with Market Participants.
2. Add team members to the nodal program with Texas market experience to ensure readiness for Market Trials. SMEs to discussion alignment issues with ERCOT business owners. SMEs to report the results of the assessment to the ERCOT business owners for resolution. |  |  |  | B. Day K. Farley | Ongoing | 11/02/09 – Work is underway to trace protocols, requirements and business processes alignment analyses are in progress.
3. Keep the oversight groups apprised of progress. |  |  |  | M. Cleary | Ongoing | 11/02/09 – status reports provided to program, NATF, TAC, Special Nodal Committee monthly.
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 32: Program Risk: Integration Testing
Technical Advisory Committee
5 November 2009
Risk: Integration Testing |  |  |  | Continued risk around technology delivery of business systems integration due to complexity and continuing maturing of application and data dependencies. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
Planned Integration Test phases and associated functional and technology components. Created effort-based testing delivery work plan to prioritize and align deliverables to key external milestones. Instituted daily PMO meetings to manage and mitigate day-to-day risks to scope and schedule deliverables. |  |  |  | PMO | Ongoing | 9/2/09 – Planning of Test phases and associated work plan has been completed Execution of work plan, with specific focus on January Market Trials functionality, has begun
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 33: Program Risk: Reconciling Protocols, Systems and Market Expectations
Technical Advisory Committee
5 November 2009
Risk: Reconciling Protocols, Systems and Market Expectations |  |  |  | Experience with deploying nodal markets by other ISOs has shown that expectations of the market participants are often missed, despite best efforts at defining tariffs or protocol requirements. ERCOT needs to assume such a risk exists for this nodal implementation as well. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Assess maturity and readiness of software in the initial nodal release, focusing on new/tailored capability for Texas Nodal. |  |  |  | B. Day K. Farley | 12/22/09 (revised) | 11/02/09 – SMEs are working with business owners on research and alignment items. NATF web ex for 11/30/09 and 12/18/09 to review full trace reports with Market Participants.
2. Add team members to the nodal program with Texas market experience to ensure readiness for Market Trials. SMEs to discussion alignment issues with ERCOT business owners. SMEs to report the results of the assessment to the ERCOT business owners for resolution. |  |  |  | B. Day K. Farley | Ongoing | 11/02/09 – Work is underway to trace protocols, requirements and business processes alignment analyses are in progress.
3. Keep the oversight groups apprised of progress. |  |  |  | M. Cleary | Ongoing | 11/02/09 – status reports provided to program, NATF, TAC, Special Nodal Committee monthly.
Potential Milestone Impact: Market Trials
Notes: <number>

## Slide 34: ERCOT-Wide Risk: Data Center Expansion Capacity Concerns
Risk: Data Center Expansion Capacity Space Concerns |  |  |  | Data center capacity, space, and power may be inadequate for Nodal Go-Live, unless plans for expansion are adequate. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Establish an Information Lifecycle Management approach to manage the life cycle of data being managed. |  |  |  | D. Forfia | Implementation expected Q1 2010 for Retail Applications | ERCOT project PR 90006_01 Commercial Systems Information Lifecycle Management Project will be presenting as an update during the October Board of Directors Meeting, and will request Execution and Funding approval at the November Board of Directors Meeting.
2. Expand current data center space, and build out new data center, to increase ERCOT data center capacity. |  |  |  | D. Forfia | Complete | Taylor capacity risk fully mitigated. Capacity sufficient for Go-Live. Austin capacity constraint will continue until Met facility is replaced.
3. Validate and monitor Nodal data capacity assumptions for Go-Live |  |  |  | D. Forfia | Ongoing | Status reports are provided to the Board of Directors quarterly in executive sessions.
Potential Milestone Impact: Nodal Go-Live
5 November 2009
Technical Advisory Committee
Notes: <number>
<number>
<number>

## Slide 35: Program Risk: Internet Explorer 6 Upgrade
Risk: Internet Explorer 6 Upgrade |  |  |  | Nodal Integration testing for the Market Participant (MP) User Interfaces and MIS reporting is using Internet Explorer (IE) version 6. MPs have requested ERCOT support a newer version, IE7. In addition, IE8 is also available. If the Nodal Market-Facing application requires certification against other IE versions, there will be internal and external costs associated with re-testing and updating the web-user interfaces. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
Currently the ERCOT Enterprise Architecture team is researching to assess impact. |  |  |  | S. Catoe | Complete | 9/30/09 – Zonal analysis is complete and Corporate analysis is at 50 percent. Currently working on estimates to conduct impact analysis.
Nodal Impact assessment to be completed in parallel with Integration Testing over the next several weeks. |  |  |  | T. Baum | 12/31/09 | Resource assignments will be assigned and load balanced within current Phase 3 Integration Testing activities.
Determine implementation timelines based on current resource plan. Complete Nodal Change Request. |  |  |  | TBD | 12/31/09 | 
Potential Milestone Impact: Phase 2 Market Connectivity
5 November 2009
Technical Advisory Committee
Notes: <number>
<number>
<number>