|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for October 2009 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 222 active generation interconnection requests totaling over 77,000 MW. This includes over 44,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $1,031.70 Million - Transmission Projects approved in 2009 total $284.4 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.2 Billion - Transmission Projects energized in 2009 total about $416 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	3

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	7

2.	Regional Planning Group Project Reviews	9

3.	Other Notable Activities	9

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Pearsall Gas Engine Plant Phase 1 (09INR0079a) in Frio County for 100 MW

## Dansby Unit 3 – Gas (09INR0072) in Brazos County for 48 MW

## Nueces Bay Repowering - Gas (09INR0039) in Nueces County for 701 MW (includes NB7 return to service)

## Langford Wind Power (10INR0026) in Tom Green County for 150 MW

## Lorraine Windpark (09INR0047) in Mitchell County for 251 MW

## The total installed wind capacity is now 8,916 MW, of which 7,393 MW (83%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements – none for October

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 224 active generation interconnection or change requests |  |  |  |  |
| As of September 30, 2009 | North | South | West | Total |
| Security Screening Study | 5 | 9 | 11 | 25 |
| SSS Completed | 6 | 8 | 13 | 27 |
| Full Interconnect Study | 25 | 22 | 84 | 131 |
| FIS Completed | 3 | 11 | 2 | 16 |
| Interconnect Agreement Completed | 7 | 9 | 7 | 23 |
| Capacity under Interconnection Agreements | 4,487 | 1,996 | 1,177 | 7,660 |
| Capacity for Grid, MW | 21,575 | 21,813 | 34,278 | 77,636 |
| Wind Capacity, MW | 4,415 | 8,241 | 31,998 | 44,654 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,554 | 16,650 |
| Gas-CT |  |  | 379 | 1,029 |
| Total Gas | 1,279 | 12,467 | 3,933 | 17,679 |
| Nuclear |  |  | 5,986 | 5,986 |
| Coal | 15 | 3,712 | 2,958 | 6,685 |
| Wind | 7,922 | 30,041 | 6,691 | 44,654 |
| Solar | 544 | 459 |  | 1,003 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 176 | 1,200 |  | 1,376 |
| Grand Total | 9,994 | 47,929 | 19,713 | 77,636 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of October 31, 2009 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | FT | MWForGrid | Change From Last Report |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0028 | V H Braunig 6 | IA | Bexar | South | Oct-09 | Gas-CT | 185 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Nov-09 | Coal | 750 | Date |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Feb-10 | Gas-CC | 50 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Apr-10 | Biomass | 45 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | May-10 | Wind | 150 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | May-10 | Coal | 855 |  |
| 09INR0079b | Pearsall Expansion Phase 2 | IA | Frio | South | Jun-10 | Gas-CT | 100 | Date/MW |
| 09INR0045 | Sand Hill Peakers | IA | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Dec-10 | Wind | 136 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Dec-10 | Coal | 263 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 06INR0022c | Penascal Wind Farm 2 | IA | Kenedy | South | Dec-10 | Wind | 202 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Dec-11 | Wind | 100 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0026 | Sterling Energy Center | IA | Sterling | West | Jun-12 | Wind | 300 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 200 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 08INR0040 | Lenorah Project | IA | Martin | West | Sep-12 | Wind | 251 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
|  |  |  |  |  |  | Total | 19,713 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 09INR0073 | Scurry | 200 | TBD | Wind |
| 09INR0077 | Reagan | 500 | Dec-09 | Wind |  | 09INR0051 | Borden | 249 | Dec-09 | Wind |
| 08INR0022 | Floyd | 100 | Dec-09 | Wind |  | 08INR0023 | Floyd | 100 | Dec-09 | Wind |
| 09INR0058 | Howard | 250 | Dec-09 | Wind |  | 08INR0056 | Nolan | 149 | Dec-09 | Wind |
| 11INR0012 | Duval | 400 | Dec-09 | Wind |  | 08INR0039 | Hamilton | 90 | Dec-09 | Wind |
| 11INR0013 | Mills | 150 | Dec-09 | Wind |  | 08INR0012b | San Patricio | 151 | Dec-09 | Wind |
| 09INR0054 | Stonewall | 149 | Dec-09 | Wind |  | 09INR0065 | Webb | 150 | Dec-09 | Wind |
| 09INR0061 | Kent | 258 | Dec-09 | Wind |  | 10INR0011 | Johnson | 275 | Jan-10 | Gas |
| 10INR0048 | Hardeman | 1,000 | Jan-10 | Wind |  | 11INR0033a | Cameron | 200 | Jan-10 | Wind |
| 10INR0024 | Briscoe | 2,940 | Jan-10 | Wind |  | 10INR0045 | Webb | 734 | Apr-10 | Wind |
| 10INR0046 | Jim Hogg | 264 | Apr-10 | Wind |  | 09INR0070 | Reagan | 42 | May-10 | Wind |
| 10INR0023 | Haskell | 386 | May-10 | Wind |  | 09INR0069 | Reagan | 36 | May-10 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 10INR0062a | Pecos | 50 | May-10 | Wind |
| 09INR0018 | Concho | 249 | May-10 | Wind |  | 09INR0035 | Concho | 750 | May-10 | Wind |
| 10INR0079 | Nolan | 60 | May-10 | Wind |  | 10INR0016 | Childress | 150 | May-10 | Wind |
| 07INR0032 | Tom Green | 249 | May-10 | Wind |  | 10INR0069 | Rusk | 13 | May-10 | Coal |
| 09INR0082 | Webb | 150 | May-10 | Wind |  | 09INR0081 | Rusk | 18 | Jun-10 | Coal |
| 10INR0035 | Harris | 416 | Jun-10 | Gas |  | 10INR0029 | Hood | 810 | Jun-10 | Gas |
| 10INR0070 | Hunt | 50 | Jul-10 | Gas |  | 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0013 | Upton | 400 | Jul-10 | Wind |  | 10INR0071 | Matagorda | 88 | Sep-10 | Wind |
| 09INR0074 | Motley | 70 | Oct-10 | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 10INR0081a | Clay | 30 | Oct-10 | Wind |  | 10INR0041 | Floyd | 135 | Oct-10 | Wind |
| 10INR0039 | Dickens | 200 | Nov-10 | Wind |  | 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |
| 10INR0032 | Navarro | 775 | Dec-10 | Gas |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 08INR0062 | Archer | 249 | Dec-10 | Wind |  | 07INR0015 | Foard | 180 | Dec-10 | Wind |
| 07INR0035 | Tom Green | 270 | Dec-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |  | 08INR0061 | Hardeman | 200 | Dec-10 | Wind |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 09INR0076 | Jackson | 300 | Dec-10 | Wind |
| 10INR0042 | Mason | 170 | Dec-10 | Wind |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 10INR0033 | Armstrong | 399 | Dec-10 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 07INR0026 | Baylor | 400 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 10INR0060 | Willacy | 401 | Dec-10 | Wind |  | 10INR0059 | Zapata | 251 | Dec-10 | Wind |
| 09INR0041 | Mitchell | 300 | Dec-10 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 08INR0014 | Webb | 183 | Mar-11 | Wind |  | 11INR0050 | Crosby | 149 | Mar-11 | Wind |
| 11INR0037 | Smith | 50 | May-11 | Biomass |  | 11INR0046 | Brazoria | 300 | May-11 | Gas |
| 11INR0028 | Grimes | 1,280 | May-11 | Gas |  | 11INR0048 | Harris | 300 | May-11 | Gas |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0061 | Presidio | 90 | May-11 | Solar |
| 11INR0060 | Tom Green | 90 | May-11 | Solar |  | 09INR0075 | Kinney | 248 | May-11 | Wind |
| 10INR0009 | Castro | 300 | May-11 | Wind |  | 10INR0062b | Pecos | 50 | May-11 | Wind |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 11INR0057 | Cameron | 144 | Jun-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 640 | Aug-11 | Gas |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 11INR0008a | Roberts | 1,000 | Sep-11 | Wind |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |  | 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0067 | Cameron | 78 | Dec-11 | Wind |
| 06INR0022d | Kenedy | 200 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 11INR0049 | Wharton | 275 | May-12 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 10INR0062c | Pecos | 201 | May-12 | Wind |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 10INR0022 | Harris | 3,500 | Jun-12 | Gas |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 12INR0002 | Briscoe | 750 | Jul-12 | Wind |
| 08INR0041 | Coke | 200 | Oct-12 | Wind |  | 12INR0016 | Nueces | 1,200 | Nov-12 | Other |
| 08INR0044 | Concho | 200 | Nov-12 | Wind |  | 08INR0019a | Gray | 250 | Nov-12 | Wind |
| 08INR0019b | Gray | 250 | Nov-12 | Wind |  | 08INR0019c | Gray | 250 | Nov-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 12INR0018 | Gray | 600 | Dec-12 | Wind |
| 06INR0022f | Kenedy | 200 | Dec-12 | Wind |  | 08INR0054 | Comanche | 401 | Dec-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0006 | Gray | 750 | Oct-13 | Wind |
| 06INR0022e | Kenedy | 200 | Dec-13 | Wind |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0005 | Matagorda | 1,200 | Jul-14 | Coal |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# American Electric Power Service Corporation submitted a project to construct several improvements in the Corpus Christi area.  The estimated completion date of this project is June 2012 and estimated cost is $ 100.2 M.   The ERCOT Independent Review has been completed and the project will be presented to TAC and the ERCOT Board of Directors in November.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Luminant Energy has submitted the Comanche Peak Area Congestion Mitigation Plan project to loop the future Parker to Everman 345 kV CREZ line into the Comanche Peak 345 kV switch station.  Luminant Energy’s estimated completion date for this project is April 2010 and the estimated cost is $3 M.  This project is in ERCOT Independent Review.

# Brazos Electric Cooperative has submitted a project to rebuild the Kruegerville to Frisco 138 kV line.  The estimated cost of this project is $19.7 M and it is expected to be completed by the end of 2010.  This project is in the comment period.

# Luminant Energy submitted a proposal to either accelerate the Waco West to Waco Atco 138 kV line rebuild that is currently scheduled to be completed by the fall of 2010 or to open the line in order to prevent congestion.  This project is in the comment period.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints – October, 2009

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearances/Reason |
| --- | --- | --- | --- | --- |
| Oak Creek-Ballinger 138kV | Miles-Rowena 69kV | $2,950,839 | Yellow Jacket (08TPIT0135) | High wind generation |
|  | DFW Security | $2,754,979 |  |  |
|  | Capacity Shortage | $2,311,036 |  |  |
| Graham-Long Creek 345kV | San Angelo Power Station -Shrew Tap | $2,035,161 | San Angelo Power Station, to Menard 138 kV line improvements (09TPIT0212) | High wind generation Outage: Comanche Peak SES to Johnson Switch 345 kV |
| Abilene-Mulberry Creek-Bitter Creek | Trent-Merkel 69kV | $1,085,179 | Abilene So. – Leon (TPIT0054) | Outage: Bluff Creek - Abilene South 138 kV |
| Twin Butte-San Angelo Red Creek 345kV | Twin Butte 345/138kV Autotransformer | $ 919,814 |  | High wind generation |
| Whitney Bus SE Edinburg-Azteca BOMSW#1/Autotransformer-1H LEG-Watermill Pueblo-Rosita Creek | Various Outages | $ 797,670 |  |  |
| Morgan Creek SES-Eskota Switch 138kV | Eskota Switch 138/69kV Autotransformer | $ 532,079 |  | Outage: Abilene South to Potter 138 kV |
| San Angelo Red Creek-Comanche Switch 345kV | San Angelo Concho-Veribest 69kV | $ 184,175 | Abilene So. – Leon (TPIT0054) | Outage: Bluff Creek - Abilene South 138 kV |
| Tradinghouse-Venus 345kV | Elm Mott-Rogers Hill | $ 168,124 | Elm Mott-Wach Northcrest (10TPIT0091) | Outages: Whitney 138 kV bus Bosque SW - Whitney 138 kV |

Inter-zonal Congestion Costs – last 13 months

# Other Notable Activities

# The initial reliability analysis and the congestion analysis of the 2009 Five-Year Transmission Plan is nearly complete.  Projects to eliminate unserved energy and reduce congestion in 2010-2014 have been identified.  The final steps in the assessment are to create a security constrained AC case for each study year and to document the results of the analysis.

# Voltage Ride Through Study Update:

# The analysis of the engineering study results has been included in a Phase I draft report documentation. This Phase I draft report is near completion.

# WGRs data submission of VRT capability data continues, together with validation of data received. WGRs with no response to the second reminder email have been put in direct contact with ERCOT in order to facilitate timely data collection for Phase II.  Preparation of PSSe v.31 compatible models has started.

- The West-to-North Stability Limit study Phase II Update: The planning study to test the effect of Power System Stabilizers (PSS) on the W-N Stability Limit is now well under way. The study runs are nearing completion and should be done by mid- second week of November. The full analysis of results and compilation of the report will be completed in the time that remains within the original time-frame set for the project.

# The ERCOT TPIT update for November 2, 2009 is in progress.  This update will be posted December 1, 2009.