## Slide 1: MARS Taskforce
RMS Update November 11, 2009
Notes: <number>

## Slide 2: October 14th RMS Meeting
The implementation of PR80027 Advanced Metering Interim Settlements Solution was scheduled for deployment the weekend of 11/14/2009-11/15/2009 with a contingency weekend of 12/11/2009-12/12/2009.
Due to an outage that occurred in the integration testing environment on October 7, 2009, the project testing was interrupted. The testing environment required reconstruction and the testing of project functionality and integration had to be re-planned.
With this unexpected change to the critical list of tasks and schedule required to implement the AMS project, ERCOT needed to provide the market with alternative options for implementing the AMS Project.
<number>
Notes: <number>

## Slide 3: What are the Options?
Option 1:
  11/14/2009
    Extract Scheduler changes for Supplemental AMS Interval Data Extract to support MPs having 7 days to schedule to receive extract prior to implementation
  11/21/2009-11/22/2009
    AMS LSE Interval Data Loading functionality
    AMS load and AMS DG Data Aggregation functionality
    Supplemental AMS Interval Data Extract
    Provide ESIIDs where AMS interval data not loaded for a trade date – Web Service
  12/6/2009
    Extract Scheduler changes for Supplemental IDR Required Interval Data Extract to support MPs having 7 days to schedule to receive extract prior to implementation
  12/13/2009
    ESIID Service History & Usage Extract (727) changes to remove interval data
    Supplemental IDR Required Interval Data Extract
    All remaining ESIID Market Data Transparency web service changes
  ***Note: Based on current timelines provided by the TDSPs for sending AMS LSE files to ERCOT with a 11/21-11/22 implementation, the first AMS LSE file would be sent to ERCOT the week of 12/4/09***
<number>
Notes: <number>

## Slide 4: What are the Options?
Option 2:
  12/6/2009
    Extract Scheduler changes for Supplemental IDR Required Interval Data Extract & Supplemental AMS Interval Data Extract to support MPs having 7 days to schedule to receive extract prior to implementation
  12/12/2009 - 12/13/2009
    AMS LSE Interval Data Loading functionality
    AMS load and AMS DG Data Aggregation functionality
    ESIID Service History & Usage Extract (727) changes to remove interval data
    Supplemental IDR Required Interval Data Extract
    Supplemental AMS Interval Data Extract
    All remaining ESIID Market Data Transparency web service changes
    ***Note: Based on current timelines provided by the TDSPs for sending AMS LSE files to ERCOT with a 12/12-12/13 implementation, the first AMS LSE file would be sent to ERCOT 12/20/2009***
<number>
Notes: <number>

## Slide 5: October 20th MARS Conference Call
The Market agreed with Option 1 as the new implementation schedule along with the list of tasks since it:
  Provides the least risk to ERCOT because it provides ERCOT with an implementation schedule where new functionality is implemented in phases verses all critical tasks being implemented on 12/12 as shown in Option 2.
  Avoids the extended system change/enhancements black-out dates that ERCOT and some TDSPs may have in place for the last two weeks of the year.
  Allows ERCOT and TDSPs to have some experience with production LSE files for several weeks prior to end of year system change/enhancements black out dates.
<number>
Notes: <number>

## Slide 6
ERCOT’s AMS Project
11/09/09 Status Report
6
Execution Milestones | Baseline Date | Revised Date | Status
Technical Architecture Complete | 05/15/2009 | - | Complete
Development Complete | 07/24/2009 | - | Complete
Detailed Designs Complete | 08/11/2009 | - | Complete
pTest Complete | 08/11/2009 | - | Complete
Market Test Complete | 11/06/2009 | - | On Schedule
iTest Complete for Implementation 1 – 11/21 | 11/06/2009 | 11/13/2009 | On Schedule for revised date
Go Live – Implementation 1 | 11/14/2009 | 11/21/2009 | On Schedule for revised date
iTest Complete for Implementation 2 – 12/13 | 11/06/2009 | 11/25/2009 | On Schedule for revised date
Go Live – Implementation 2 | n/a | 12/13/2009 | On Schedule for revised date
Stabilization Complete | 03/19/2010 |  | 
Project Complete | 05/21/2010 |  | 
Notes: <number>

## Slide 7: Project 80027 - Update Market Testing
Scope of Market Testing:
  TDSP submits Advanced Metering LSE interval data file submission and ERCOT returns a file-level acknowledgement
Target Dates for Market Testing:
  October 19 – November 6, 2009
TDSP Testing with ERCOT:
  Testing completed with CenterPoint the week of October 23
  Testing completed with Oncor the week of October 30
<number>
Notes: <number>

## Slide 8: October 28, 2009 MARS Taskforce WebEx
With the new implementation schedule also meant that:
  The 814_20 submission schedule needed to be revised by Oncor and CenterPoint Energy
    Oncor’s first 814_20s should flow to ERCOT on 12/4/09
    CenterPoint’s first 814_20s should flow to ERCOT on 12/3/09
Oncor and CenterPoint will be delivering their LSE files to ERCOT on different dates that are driven by the scheduled meter reading date for the cycles and to allow transaction processing timelines to complete.
  CRs were concerned about any delays that would be above what was absolutely necessary
  The taskforce requested that an expanded timeline document would be useful that would include when the LSE file will be sent to ERCOT by Oncor and CenterPoint
    ERCOT took the action item to draft the expanded timeline matrix.
<number>
Notes: <number>

## Slide 9: October 28, 2009 MARS Taskforce WebEx
Thanks to ERCOT for their hard work and quickly identifying a market need, the Taskforce reviewed a Frequently Asked Questions (FAQ) document to assist market participants with questions on this new market process and where to find AMS information:
  http://www.ercot.com/committees/board/tac/rms/marstf/
<number>
Notes: <number>

## Slide 10: Next Steps for MARS
  The MARS Taskforce agreed that project updates for the month of November will be provided through the Commercial Operations meeting on November 10, 2009 and the Retail Market Subcommittee meeting on November 11, 2009 rather than through a formal MARS Taskforce meeting.
  Communicate to the Market via email the final 814_20/LSE timeline matrix that was developed in collaboration with ERCOT, Oncor and CenterPoint.
    Hopefully this matrix will address CRs concerns that were discussed during the last MARS Taskforce meeting on October 28, 2009, if not then a MARS conference call will be scheduled.
  The MARS Taskforce will re-evaluate when our next meeting date should be scheduled following project implementation go-live and once there is actual AMS production data that can be discussed and reviewed by the team.
<number>
Notes: <number>

## Slide 11: Questions?
Notes: <number>

## Slide 12: To All Veterans WE THANK YOU!!!
Notes: <number>