## Slide 1
TAC
December 3, 2009
Meeting Update
<number>

## Slide 2: TX Nodal Implementation
<number>
Phase | When | Scope | Status
2.1: Market Connectivity MILESTONE COMPLETE | Oct. 28 | MP interface testing (API, Market Manager UI) Market System Rules Validation (Phase 1) | Connectivity testing began as scheduled Up to 16 MPs testing market submissions daily Some technical issues on market side Few functional issues
3: Real-Time Markets | Mid January-Early February | MMS-SCED execution SCED results, report publishing CRR auction execution (CRR UI) OS submissions (API, OS UI) | Planning complete Integrated testing under way (CRR, OS, SCED) Running Real-Time operating scenarios twice weekly
4: DAM/RUC | Late March-Early April | MMS-DAM, DRUC, HRUC, SCED execution Market results, report publishing Initial S&B execution Outage, CRR integration | Planning in progress Integrated testing under way Executing DAM mechanics
5: Full Functionality | Late April-Early May | Run full nodal systems | Planning in progress Internal DST test Nov. 1
Parking Deck items will be managed through ERCOT PMO via current Change Management process 10 open items; 3 ranked by PRS |  |  | 

## Slide 3: PRS
Approved by TAC
  PRR832, Deletion of Schedule Control Error (SCR) Posting Requirement
  PRR839, Revised Resource Category Generic Fuel Costs - Urgent
  PRR840, Update Trading Hub Conversion for 2010 Congestion Zones – Urgent
  NPRR196, Synchronization of Nodal Protocols with PRR827, Find Transaction and Find ESI ID Functions on the MIS
Tabled at TAC
  PRR833, Primary Frequency Response Requirement from Existing WGRs
  NPRR091, Scarcity Pricing and Mitigated Offer Cap During the Period Commencing on the Nodal Market Implementation Date and Continuing for a Total of 45 Days
  NPRR146, ICCP Telemetry Information Submittals
  NPRR153, Generation Resource Fixed Quantity Block
  NPRR164, Resubmitting Ancillary Service Offers in SASM
  NPRR169, Clarify the Calculation and Posting of LMPs for the Load Zone and LMPs for each Hub
    Changed priority level from “high-medium” to “high-high”
Previously Approved, but Tabled at TAC – sent to BOD
  NPRR196, Synchronization of Nodal Protocols with PRR827, Find Transaction and Find ESI ID Functions on the MIS
<number>

## Slide 4: ROS
Approved as modified by TAC
  OGRR226, Generation Resource Response Time Requirement
  OGRR237, Clarify the WGR Voltage Ride-Through Requirement – Urgent
<number>

## Slide 5: COPS
Approved by TAC
  Revised COPS Procedures
<number>

## Slide 6: RMS
Approved by TAC
  RMGRR081, Texas New Mexico Power Updates to Processes and Contact Information
<number>

## Slide 7: Other Business
U.S. House of Representatives Committee on Agriculture
  Sent all RTOs and ISOs letter for preliminary investigation into FTRs (TCR)
  Letter is posted on TAC site as background material for Dec 3 meeting
Possible Webcast of Stakeholder Committees
  Discussion around transparency vs. costs
  Discussion around alternatives like WebEx
    Not only Texas Admin can provide this service
<number>

## Slide 8
Questions ?
<number>