## Slide 1: MARS TASKFORCE 2009 ACCOMPLISHMENTS & 2010 GOALS
RMS Update December 9, 2009
<number>
Notes: <number>

## Slide 2: ACCOMPLISHMENTS:
Developed Retail Market Guide Revision section “7.15 Advanced Meter Interval Data File Format and Submission” that details processes for AMS “Provisioned” meters , TDSP’s FTP site and ERCOT Enhanced LSE file .
  RMGRR075 was approved by RMS (May 09) and TAC (June 09), currently awaiting ERCOT’s system implementation
In collaboration with TTPT, the MARS Taskforce agreed to the test script for testing LSE Files sent by TDSPs to ERCOT and ERCOT returns a file-level acknowledgement
  Oncor and CenterPoint Energy successfully completed LSE file testing in October 2009
<number>
Notes: <number>

## Slide 3: ACCOMPLISHMENTS
Developed many documents to assist the market with new and revised extracts, user guides, reporting and Frequently Asked Questions (FAQs)
  Draft_Supplemental_IDR_Required_Interval_Data_Extract__User_G
  ESIID Join Diagram v01
  ESIID Service History Usage Extract User Guide
  ESIID_Extract_DDL_v.08.sql
  Interval Data LSE Activity Report
  Market Data Transparency Quick Reference Guide
  Market Data Transparency Technical Files
  Market Data Transparency User Guide
  PR80027_Advanced_Metering_Interim_Settlement_Solution__FAQs
<number>
Notes: <number>

## Slide 4: ACCOMPLISHMENTS:
To satisfy AMIT BR-004 of the Interim Settlement Solution until the Texas Web Portal is available, both Oncor and CenterPoint Energy successfully implemented FTP sites providing 15 minute interval data for AMS meters already deployed and provisioned via the approved LSE file format developed by the MARS Taskforce.
Throughout the past year the taskforce provided both COPS and RMS monthly AMS Project 80027 status reports that included the critical dates, tasks and milestones.
<number>
Notes: <number>

## Slide 5: ACCOMPLISHMENTS:
After an unanticipated project testing delay created by a power outage on October 7, 2009 at ERCOT’s Austin test facilities, the MARS Taskforce quickly discussed the issue at hand and agreed to a two-phased implementation schedule for the Interim Settlement Solution as follows:
    Architecture Completed - 05/15/2009
    Development Completed- 07/15/2009
    Detailed Design Completed- 08/11/2009
    GO-Live Implementation 1 11/21/2009 (Completed)
    GO-Live Implementation 2 12/13/2009 (Scheduled)
<number>
Notes: <number>

## Slide 6: 2010 GOALS
Monitor system performance and LSE file activities throughout:
    System Stabilization Complete 03/19/2010
    Project Completion schedule 05/21/2010
Quickly develop a market resolution for any issues as they are identified after production implementation.
With the implementation of the Market’s Interim Settlement Solution, RMGRR075 documenting LSE files and processes and PRR 766 providing market protocol requirements, the MARS Taskforce will require RMS’ assistances and guidance to determine the taskforce’s next steps for 2010.
<number>
Notes: <number>

## Slide 7: MERRY CHRISTMAS & THE HAPPIEST OF NEW YEAR FROM MARS
<number>
Notes: <number>