## Slide 1: MARS Taskforce
COPS Update December 8, 2009
Notes: <number>

## Slide 2: Option 1 Tasks and Status Report?
Option 1:
  11/14/2009 (COMPLETED)
    Extract Scheduler changes for Supplemental AMS Interval Data Extract to support MPs having 7 days to schedule to receive extract prior to implementation
  11/21/2009-11/22/2009 (COMPLETED)
    AMS LSE Interval Data Loading functionality
    AMS load and AMS DG Data Aggregation functionality
    Supplemental AMS Interval Data Extract
    Provide ESIIDs where AMS interval data not loaded for a trade date – Web Service
  12/6/2009 (COMPLETED)
    Extract Scheduler changes for Supplemental IDR Required Interval Data Extract to support MPs having 7 days to schedule to receive extract prior to implementation
  12/13/2009
    ESIID Service History & Usage Extract (727) changes to remove interval data
    Supplemental IDR Required Interval Data Extract
    All remaining ESIID Market Data Transparency web service changes
  ***Note: Based on current timelines provided by the TDSPs for sending AMS LSE files to ERCOT with a 11/21-11/22 implementation, the first AMS LSE file would be sent to ERCOT the week of 12/4/09***
<number>
Notes: <number>

## Slide 3
ERCOT’s AMS Project
12/07/09 Status Report
6
Execution Milestones | Baseline Date | Revised Date | Status
Technical Architecture Complete | 05/15/2009 | - | Complete
Development Complete | 07/24/2009 | - | Complete
Detailed Designs Complete | 08/11/2009 | - | Complete
pTest Complete | 08/11/2009 | - | Complete
Market Test Complete | 11/06/2009 | - | Complete
iTest Complete for Implementation 1 – 11/21 | 11/06/2009 | 11/13/2009 | Complete
Go Live – Implementation 1 | 11/14/2009 | 11/21/2009 | Complete
iTest Complete for Implementation 2 – 12/13 | 11/06/2009 | 12/09/2009 | On Schedule for revised date
Go Live – Implementation 2 | n/a | 12/13/2009 | On Schedule for revised date
Stabilization Complete | 03/19/2010 |  | 
Project Complete | 05/21/2010 |  | 
Notes: <number>

## Slide 4: TDSPs and ERCOT Action Item
With ERCOT’s new implementation schedule also meant that:
  The 814_20 submission schedule needed to be revised for Oncor and CenterPoint Energy and an expanded timeline needed to be developed to address market questions/concerns of when to expect 814_20 transactions, LSE files would be sent to ERCOT by TDSPs and finally when those ESI IDs would be settled based upon the 15 minute data.
  Thanks to Oncor, CenterPoint Energy and ERCOT for working so diligently to finalize this information.
<number>
Notes: <number>

## Slide 5: Next Steps for MARS Taskforce
  The MARS Taskforce agreed that project updates for the month of December will be provided through the Commercial Operations meeting on December 8, 2009 and the Retail Market Subcommittee meeting on December 9, 2009 rather than through a formal MARS Taskforce meeting due to so many production activities are scheduled for November/December.
  The MARS Taskforce will re-evaluate when our next meeting date should be scheduled following project implementation Go-Live of Phase I and II and once there is actual AMS production data that can be discussed and reviewed by the team.
<number>
Notes: <number>

## Slide 6: Questions?
Notes: <number>