|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for November 2009 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 228 active generation interconnection requests totaling almost 78,000 MW. This includes over 45,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - ERCOT is currently tracking 228 active generation interconnection requests totaling almost 78,000 MW. This includes over 45,000 MW of wind generation. - Regional Planning is currently reviewing proposed transmission improvements with a total of $1,031.95 Million - Transmission Projects approved in 2009 total $405.1 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.5 Billion - Transmission Projects energized in 2009 total about $538.6 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	4

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	7

2.	Regional Planning Group Project Reviews	10

3.	Other Notable Activities	11

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## JK Spruce (09INR0002) Coal in Bexar County for 750 MW

## The total installed wind capacity remains at 8,916 MW, of which 7,393 MW (83%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements

- Papalote Creek Wind Farm Phase II (08INR0012b) for 198 MW in San Patricio County

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 228 active generation interconnection or change requests |  |  |  |  |
| As of November 30, 2009 | North | South | West | Total |
| Security Screening Study | 9 | 10 | 4 | 23 |
| SSS Completed | 6 | 8 | 17 | 31 |
| Full Interconnect Study | 25 | 22 | 87 | 134 |
| FIS Completed | 3 | 11 | 2 | 16 |
| Interconnect Agreement Completed | 7 | 10 | 7 | 24 |
| Capacity under Interconnection Agreements | 4,487 | 2,194 | 1,177 | 7,858 |
| Capacity for Grid, MW | 21,841 | 21,649 | 34,448 | 77,938 |
| Wind Capacity, MW | 4,681 | 8,787 | 32,198 | 45,666 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,554 | 16,650 |
| Gas-CT |  |  | 379 | 1,029 |
| Total Gas | 1,279 | 12,467 | 3,933 | 17,679 |
| Nuclear |  |  | 5,986 | 5,986 |
| Coal | 15 | 3,712 | 2,208 | 5,935 |
| Wind | 7,476 | 31,301 | 6,889 | 45,666 |
| Solar | 544 | 459 |  | 1,003 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 216 | 1,200 |  | 1,416 |
| Grand Total | 9,588 | 49,189 | 19,161 | 77,938 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of November 30, 2009 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change From Last Report |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Dec-09 | Nuclear | 86 | Date |
| 09INR0028 | V H Braunig 6 | IA | Bexar | South | Dec-09 | Gas-CT | 185 | Date |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Feb-10 | Gas-CC | 50 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Apr-10 | Biomass | 45 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | May-10 | Coal | 855 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | May-10 | Wind | 150 |  |
| 09INR0079b | Pearsall Expansion | IA | Frio | South | Jun-10 | Gas-CT | 100 |  |
| 09INR0045 | Sand Hill Peakers | IA | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Dec-10 | Coal | 263 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 08INR0012b | Papalote Creek Phase 2 | IA | San Patricio | South | Dec-10 | Wind | 198 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Dec-10 | Wind | 136 |  |
| 06INR0022c | Penascal Wind Farm 2 | IA | Kenedy | South | Dec-10 | Wind | 202 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Dec-11 | Wind | 100 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 200 |  |
| 09INR0026 | Sterling Energy Center | IA | Sterling | West | Jun-12 | Wind | 300 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 08INR0040 | Lenorah Project | IA | Martin | West | Sep-12 | Wind | 251 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
|  |  |  |  |  |  | Total | 19,161 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11INR0013 | Mills | 150 | Dec-09 | Wind |  | 09INR0077 | Reagan | 500 | Dec-09 | Wind |
| 09INR0058 | Howard | 250 | Dec-09 | Wind |  | 09INR0061 | Kent | 258 | Dec-09 | Wind |
| 09INR0051 | Borden | 249 | Dec-09 | Wind |  | 09INR0054 | Stonewall | 149 | Dec-09 | Wind |
| 08INR0039 | Hamilton | 90 | Dec-09 | Wind |  | 08INR0056 | Nolan | 149 | Dec-09 | Wind |
| 08INR0022 | Floyd | 100 | Dec-09 | Wind |  | 08INR0023 | Floyd | 100 | Dec-09 | Wind |
| 10INR0048 | Hardeman | 1,000 | Jan-10 | Wind |  | 10INR0011 | Johnson | 275 | Jan-10 | Gas |
| 10INR0024 | Briscoe | 2,940 | Jan-10 | Wind |  | 11INR0033a | Cameron | 200 | Jan-10 | Wind |
| 10INR0062a | Pecos | 50 | May-10 | Wind |  | 10INR0079 | Nolan | 60 | May-10 | Wind |
| 09INR0070 | Reagan | 42 | May-10 | Wind |  | 10INR0054 | Palo Pinto | 36 | May-10 | Wind |
| 10INR0023 | Haskell | 386 | May-10 | Wind |  | 09INR0069 | Reagan | 36 | May-10 | Wind |
| 09INR0035 | Concho | 750 | May-10 | Wind |  | 10INR0016 | Childress | 150 | May-10 | Wind |
| 07INR0032 | Tom Green | 249 | May-10 | Wind |  | 09INR0018 | Concho | 249 | May-10 | Wind |
| 09INR0081 | Rusk | 18 | Jun-10 | Coal |  | 10INR0069 | Rusk | 13 | May-10 | Coal |
| 10INR0070 | Hunt | 50 | Jul-10 | Gas |  | 10INR0029 | Hood | 810 | Jun-10 | Gas |
| 10INR0052a | Knox | 21 | Jul-10 | Wind |  | 10INR0057 | Taylor | 200 | Jul-10 | Wind |
| 10INR0071 | Matagorda | 88 | Sep-10 | Wind |  | 10INR0013 | Upton | 400 | Jul-10 | Wind |
| 09INR0074 | Motley | 70 | Oct-10 | Wind |  | 10INR0081a | Clay | 30 | Oct-10 | Wind |
| 10INR0015 | Mitchell | 350 | Oct-10 | Wind |  | 10INR0041 | Floyd | 135 | Oct-10 | Wind |
| 10INR0039 | Dickens | 200 | Nov-10 | Wind |  | 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |
| 10INR0080 | Presidio | 144 | Dec-10 | Solar |  | 10INR0032 | Navarro | 775 | Dec-10 | Gas |
| 10INR0060 | Willacy | 401 | Dec-10 | Wind |  | 10INR0077 | Callahan | 101 | Dec-10 | Wind |
| 10INR0051 | Brazoria | 200 | Dec-10 | Wind |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 10INR0042 | Mason | 170 | Dec-10 | Wind |  | 09INR0076 | Jackson | 300 | Dec-10 | Wind |
| 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |  | 10INR0033 | Armstrong | 399 | Dec-10 | Wind |
| 08INR0061 | Hardeman | 200 | Dec-10 | Wind |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 07INR0035 | Tom Green | 270 | Dec-10 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0026 | Baylor | 400 | Dec-10 | Wind |
| 09INR0041 | Mitchell | 300 | Dec-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 11INR0048 | Harris | 300 | May-11 | Gas |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0061 | Presidio | 90 | May-11 | Solar |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 10INR0009 | Castro | 300 | May-11 | Wind |  | 10INR0062b | Pecos | 50 | May-11 | Wind |
| 11INR0057 | Cameron | 144 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 11INR0054 | San Patricio | 161 | Jun-11 | Wind |
| 11INR0006 | Lamar | 579 | Jul-11 | Gas |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |  | 11INR0040 | freestone | 640 | Aug-11 | Gas |
| 11INR0008a | Roberts | 1,000 | Sep-11 | Wind |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |  | 10INR0081b | Clay | 19 | Oct-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |
| 11INR0043 | Coke | 300 | Dec-11 | Wind |  | 11INR0067 | Cameron | 78 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 09INR0048 | Jack | 150 | Dec-11 | Wind |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 11INR0049 | Wharton | 275 | May-12 | Gas |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 10INR0062c | Pecos | 201 | May-12 | Wind |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 10INR0022 | Harris | 3,500 | Jun-12 | Gas |
| 12INR0027 | Gray | 200 | Oct-12 | Wind |  | 12INR0002 | Briscoe | 750 | Jul-12 | Wind |
| 08INR0041 | Coke | 200 | Oct-12 | Wind |  | 12INR0026 | Randall | 400 | Oct-12 | Wind |
| 08INR0019b | Gray | 250 | Nov-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 08INR0019c | Gray | 250 | Nov-12 | Wind |  | 08INR0019a | Gray | 250 | Nov-12 | Wind |
| 12INR0018 | Gray | 600 | Dec-12 | Wind |  | 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |
| 08INR0054 | Comanche | 401 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 06INR0022e | Kenedy | 200 | Dec-13 | Wind |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 14INR0005 | Matagorda | 1,200 | Jul-14 | Coal |
| 09INR0073 | Scurry | 200 | TBD | Wind |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# American Electric Power Service Corporation submitted a project to construct several improvements in the Corpus Christi area.  The estimated completion date of this project is June 2012 and estimated cost is $ 100.2 M.   The ERCOT Independent Review has been completed and the project was endorsed by the ERCOT Board of Directors in November.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Luminant Energy has submitted the Comanche Peak Area Congestion Mitigation Plan project to loop the future Parker to Everman 345 kV CREZ line into the Comanche Peak 345 kV switch station.  Luminant Energy’s estimated completion date for this project is April 2010 and the estimated cost is $3 M.  This project is in ERCOT Independent Review.

# Brazos Electric Cooperative has submitted a project to rebuild the Kruegerville to Frisco 138 kV line.  The estimated cost of this project is $19.7 M and it is expected to be completed by the end of 2010.  The comment period for this project has been completed and an RPG acceptance letter has been sent to Brazos Electric Cooperative.

# Luminant Energy submitted a proposal to either accelerate the Waco West to Waco Atco 138 kV line rebuild that is currently scheduled to be completed by the fall of 2010 or to open the line in order to prevent congestion.  This project is in study mode.

# Luminant Energy submitted a proposal to uprate the Bell County to Salado 138 kV line by operating it at an elevated temperature.  This project is in study mode.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints – October, 2009 – DATA PENDING

| Contingency | Binding Element | Estimated Costs | Transmission Project |
| --- | --- | --- | --- |
| RENNER SWITCH - CARROLLTON EAST 138KV | HEBRON TMPP - AUSTIN RANCH 138KV | $ 1,925,064 | 06TPIT0037 Carrollton East - Renner 138kV line |
|  | Capacity Shortage | $ 1,622,568 |  |
| Oak Creek – Ballinger 138kV | Abilene South – Ballinger 69kV | $ 819,234 | Ballinger to Abilene South 69kV, rebuild (08TPIT0080) |
| Temple Pecan Creek - Tradinghouse & Temple Switch - Lake Creek SES | San Angelo Power Station -Shrew Tap | $ 370,342 | Yellow Jacket Phase Shifting Transformer addition (08TPIT0135) |
| Garfield - Onion Creek & Hicross AEN 138kV | Lytton Springs 345/138kV Autotransformer #4 | $ 338,471 | Lytton Springs Autotransformer, addition (10TPIT0058) |
| Tradinghouse SES - Venus Switch 345kV | Rogers Hill TU - Elm Mott 138kV | $ 327,011 | Elm Mott – Waco Northcrest 138kV, upgrade (10TPIT0091) |
| Dilley Switch - San Miguel 138kV | Derby - Pearsall 69kV | $ 199,939 | Pearsall to Dilley 69 kV Line Upgrade (09TPIT0189) |
| Everman Switch - Sherry Switch 345kV | Everman Switch - Oak Hill 2 Tap 138kV | $ 129,597 |  |
| Hillje - Holman 345kV | Columbus - Stafford Hill 69kV | $ 79,526 |  |
| North Denton 138/69kV Autotransformer | North Denton 138/69kV Autotransformer | $ 69,064 |  |

Inter-zonal Congestion

# Other Notable Activities

2009 Five-Year Transmission Plan Update:

The 2009 Five-Year Transmission Plan is nearly complete.  Projects to eliminate unserved energy and reduce congestion in 2010-2014 have been identified.  The final steps in the assessment are to create a security constrained AC case for each study year and to document the results of the analysis.

Voltage Ride Through Study Update:

The Phase I report for public dissemination is being reviewed by System Planning.  As part of Phase II, WGRs data submission of VRT capability data continues, together with validation of data received. WGRs with no response to the second reminder email have been put in direct contact with ERCOT in order to facilitate timely data collection for Phase II. For each wind farm, an aggregation model is being developed by the consultant.  Validation of PSSe v.31 compatible models as needed for Phase III is almost completed.

West-to-North Stability Limit study Phase II Update:

With the revisions from the revised Operations Planning W-N stability limit study applied, the Planning study to test the effect of Power System Stabilizers (PSS) on the W-N Stability Limit is now nearing completion. The study runs and the full analysis of results have been completed and System Planning is currently reviewing the draft of the report.

The ERCOT TPIT update for November 2009 has been completed and was posted December 1, 2009.