## Instructions
Assumptions:
TDSP reads NIDR meters M-F based on public metering schedules
CNP sends 867_03 data T-Sat
ONCOR sends 867_03 data M-Sat
TDSP sends LSE files M-Sun
If the LSE file beats the 814_20 to ERCOT, the LSE data will reject for not having the correct Profile Code and the TDSP will need to resend.
ONCOR will send the LSE file 6 days after the operating day for all provisioned AMS ESIIDs. If the 814_20 to change the profile code is loaded in ERCOT's system prior to ERCOT receiving the LSE file, it will attempt to load into ERCOT.
ONCOR will complete their backlog footprint as of Wed, 1/6/2010.
Directions on how to use the AMS Transition Timeline Tabs:
Row 1 - Header row explaining each column's contents
Row 1 - dates from E1-BP1 represent the task day; if you read from the task day down the column, then you are reading a list of events that occur on that day
Row 1 - greyed out days are blackout days for sending 814_20s or retail outage weekends
Col B - dates represent the Operating Day, which is the effective date of 814_20 and first date for which LSE data will exist for settlement purposes
For each operating day listed in column B, read the row across to see the date on which each task for that operating day will occur
If LSE received on or before day 8 and processed before 5:30PM, data should be used in initial settlement
If LSE received after day 8 or on day 8 and not processed before 5:30PM, data will not be used in initial settlement

## CNP AMS Transition Timeline
CNP Meter Cycle | Operating day Effective date of 814_20 and First day of LSE data | # of days after Op day to LSE file | Mon, 11/30 | Tues, 12/1 | Wed, 12/2 | Thurs, 12/3 | Fri, 12/4 | Sat, 12/5 | Sun, 12/6 | Mon, 12/7 | Tues, 12/8 | Wed, 12/9 | Thurs, 12/10 | Fri, 12/11 | Sat, 12/12 | Sun, 12/13 | Mon, 12/14 | Tues, 12/15 | Wed, 12/16 | Thurs, 12/17 | Fri, 12/18 | Sat, 12/19 | Sun, 12/20 | Mon, 12/21 | Tues, 12/22 | Wed, 12/23 | Thurs, 12/24 | Fri, 12/25 | Sat, 12/26 | Sun, 12/27 | Mon, 12/28 | Tues, 12/29 | Wed, 12/30 | Thurs, 12/31 | Fri, 1/1 | Sat, 1/2 | Sun, 1/3 | Mon, 1/4 | Tues, 1/5 | Wed, 1/6 | Thurs, 1/7 | Fri, 1/8 | Sat, 1/9 | Sun, 1/10 | Mon, 1/11 | Tues, 1/12 | Wed, 1/13 | Thurs, 1/14 | Fri, 1/15 | Sat, 1/16 | Sun, 1/17 | Mon, 1/18 | Tues, 1/19 | Wed, 1/20 | Thurs, 1/21 | Fri, 1/22 | Sat, 1/23 | Sun, 1/24 | Mon, 1/25 | Tues, 1/26 | Wed, 1/27 | Thurs, 1/28 | Fri, 1/29 | Sat, 1/30 | Sun, 1/31 | Mon, 2/1
814_20 Counts |  |  |  | 2000 | 2000 | 11560 | 16773 | 17511 |  | 2238 | 2000 | 2000 | 8388 | 3852 |  |  | 8038 | 2000 | 8772 | 2000 | 2145 | 2000 |  | 5185 | 2000 | 11595 | [5 empty] | 2000 | 7096 | 2000 | Tues, 1/5: 3000; Wed, 1/6: 2505 | 5680 | 5796 | 3911 |  |  | 3000 | 7198 | 3614 | 3000 | 4778 |  | 1362 | 3000 | 3000 | 3000 | 3000 |  |  | 3832 | 3000 | 3000 | 3664
09 | 11/30 | 5 | T - read mtr | T- process mtr | T-send 867_03 | E - send Act Rpt | T - send 814_20 | E - send 814_21 | T - send LSE
10 | 12/1 | 5 |  | T - read mtr | T- process mtr | T-send 867_03 | E - send Act Rpt | T - send 814_20 | E - send 814_21 | T - send LSE
11 | 12/2 | 6 |  |  | T-read meter | T-process meter | T - send 867_03 | E- send Act Rpt |  | T - send 814_20 | E - send 814_21 | T-send LSE
12 | 12/3 | 5 |  |  |  | T-read mtr | T - process meter | T - send 867_03 | E - send Act Rpt | T - send 814_20 | E - send 814_21 | T-send LSE
13 | 12/4 | 7 |  |  |  |  | T - read mtr |  |  | T - process mtr | T - send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
14 | 12/5 | 5 | [7 empty] | T - read mtr | T - process mtr | T-send 867_03 | E - send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
15 | 12/8 | 7 | [8 empty] | T - read mtr | T-process | T-send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21 | T-send LSE
16 | 12/9 | 6 | [9 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21 | T-send LSE
17 | 12/10 | 7 | [10 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
18 | 12/11 | 5 | [11 empty] | T-read mtr |  |  | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
19 | 12/12 | 5 | [14 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
20 | 12/15 | 5 | [15 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
21 | 12/16 | 6 | [16 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21 | T-send LSE
01 | 12/17 | 5 | [17 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
02 | 12/18 | 13 | [18 empty] | T-read mtr |  |  | T-process | T-send 867_03 | E-send Act Rpt | [6 empty] | T-send 814_20 | E-send 814_21 | Fri, 1/1: T-send LSE
03 | 12/19 | 10 | [21 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | [5 empty] | T-send 814_20 | E-send 814_21 | Fri, 1/1: T-send LSE
04 | 12/22 | 9 | [22 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  |  |  |  | T-send 814_20 | E-send 814_21 | Fri, 1/1: T-send LSE
05 | 12/23 | 10 | [23 empty] | T-read mtr |  |  |  |  | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | Fri, 1/1: E-send 814_21; Sat, 1/2: T-send LSE
06 | 12/24 | 5 | [28 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | Fri, 1/1: T-send 814_20; Sat, 1/2: E-send 814_21; Sun, 1/3: T-send LSE
07 | 12/29 | 7 | [29 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21 | T-send LSE
08 | 12/30 | 6 | [30 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21 | T-send LSE
09 | 12/31 | 8 | [31 empty] | T-read mtr | Mon, 1/4: T-process; Tues, 1/5: T-send 867_03; Wed, 1/6: E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
10 | 1/1 | 5 | [32 empty] | Mon, 1/4: T-read mtr; Tues, 1/5: T-process; Wed, 1/6: T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
11 | 1/5 | 5 | [32 empty] | Tues, 1/5: T-read mtr; Wed, 1/6: T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
12 | 1/6 | 6 | [32 empty] | Wed, 1/6: T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21 | T-send LSE
13 | 1/7 | 5 | [38 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
14 | 1/8 | 7 | [39 empty] | T-read mtr |  |  | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
15 | 1/9 | 5 | [42 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
16 | 1/12 | 5 | [43 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
17 | 1/13 | 6 | [44 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21 | T-send LSE
18 | 1/14 | 5 | [45 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
19 | 1/15 | 7 | [46 empty] | T-read mtr |  |  | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
20 | 1/16 | 5 | [49 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
21 | 1/19 | 7 | [50 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21 | T-send LSE
01 | 1/20 | 6 | [51 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21 | T-send LSE
02 | 1/21 | 7 | [52 empty] | T-read mtr | T-process | T-send 867_03 |  | E-send Act Rpt |  | T-send 814_20 | E-send 814_21 | T-send LSE
03 | 1/22 | 7 | [53 empty] | T-read mtr 1/21 |  |  | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
04 | 1/23 | 5 | [56 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
05 | 1/26 | 5 | [57 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20 | E-send 814_21 | T-send LSE
06 | 1/27 | … | [58 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt |  | T-send 814_20
07 | 1/28 | … | [59 empty] | T-read mtr | T-process | T-send 867_03 | E-send Act Rpt | T-send 814_20
08 | 1/29 | … | [60 empty] | T-read mtr |  |  | T-process
T-read mtr

## ONCOR AMS Transition Timeline
ONCOR Meter Cycle | Operating day Effective date of 814_20 and First day of LSE data | # of days after Op day that the 814_20 is sent to ERCOT | Mon, 11/30 | Tues, 12/1 | Wed, 12/2 | Thurs, 12/3 | Fri, 12/4 First 814-20's cycle 2 for Oncor footprint | Sat, 12/5 | Sun, 12/6 Oncor Sends All LSE data DAILY with 6 day lag | Mon, 12/7 | Tues, 12/8 | Wed, 12/9 | Thurs, 12/10 | Fri, 12/11 | Sat, 12/12 | Sun, 12/13 | Mon, 12/14 | Tues, 12/15 | Wed, 12/16 | Thurs, 12/17 | Fri, 12/18 | Sat, 12/19 | Sun, 12/20 | Mon, 12/21 | Tues, 12/22 | Wed, 12/23 | Thurs, 12/24 | Fri, 12/25 | Sat, 12/26 | Sun, 12/27 | Mon, 12/28 | Tues, 12/29 | Wed, 12/30 | Thurs, 12/31 | Fri, 1/1 | Sat, 1/2 | Sun, 1/3 | Mon, 1/4 | Tues, 1/5 | Wed, 1/6 AMS BackLog Migration Completed in Oncor footprint
814_20 Counts |  |  |  |  | 7000 | 7000 | 30000 | 31000 |  | 53000 | 7000 | 30000 | 7000 | 30000 | 8000 |  | 53000 | 7000 | 53000 | 30000 | 30000 | 31000 |  | 53000 | 7000 | 30000 |  |  |  |  | 7000 | 7000 | 53000 | 30000 |  |  |  | 53000 | 7000 | 53000
02 | 11/30 | 4 | T - read & process mtr | T-send 867_03 | E - send Act Rpt |  | T - send 814_20 | E - send 814_21
03 | 12/1 | 4 |  | T - read & process mtr | T-send 867_03 | E - send Act Rpt |  | T - send 814_20 | E - send 814_21
04 | 12/2 | 5 |  |  | T-read & process mtr | T - send 867_03 | E- send Act Rpt |  |  | T - send 814_20 | E - send 814_21
05 | 12/3 | 4 |  |  |  | T-read & process mtr | T - send 867_03 | E - send Act Rpt |  | T - send 814_20 | E - send 814_21
06 | 12/4 | 5 |  |  |  |  | T-read & process mtr | T - send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21
07 | 12/7 | 4 | [7 empty] | T - read & process mtr | T-send 867_03 | E - send Act Rpt |  | T-send 814_20 | E-send 814_21
08 | 12/8 | 6 | [8 empty] | T - read & process mtr | T-send 867_03 | E-send Act Rpt |  |  |  | T-send 814_20 | E-send 814_21
09 | 12/9 | 5 | [9 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21
10 | 12/10 | 6 | [10 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  |  | T-send 814_20 | E-send 814_21
11 | 12/11 | 5 | [11 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21
12 | 12/14 | 4 | [14 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21
13 | 12/15 | 4 | [15 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21
14 | 12/16 | 5 | [16 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21
15 | 12/17 | 4 | [17 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  | T-send 814_20 | E-send 814_21
16 | 12/18 | 5 | [18 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  | T-send 814_20 | E-send 814_21
17 | 12/21 | 9 | [21 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt | [6 empty] | T-send 814_20 | E-send 814_21
18 | 12/22 | 8 | [22 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt | [5 empty] | T-send 814_20 | E-send 814_21
19 | 12/23 | 8 | [23 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt | [5 empty] | T-send 814_20 | E-send 814_21
20 | 12/28 | 7 | [28 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  |  |  | T-send 814_20 | E-send 814_21
21 | 12/29 | 6 | [29 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  |  | T-send 814_20 | E-send 814_21
01 | 12/30 | 7 | [30 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  |  |  | T-send 814_20
02 | 12/31 | 6 | [31 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt |  |  |  | T-send 814_20
03 | 1/4 | … | [35 empty] | T-read & process mtr | T-send 867_03 | E-send Act Rpt
04 | 1/5 | … | [36 empty] | T-read & process mtr | T-send 867_03
05 | 1/6 | … | [37 empty] | T-read & process mtr
Note on T11: cmeiners: shifted to avoid exceeding ERCOT's limits for 814_20s
Note on AI20: cmeiners: Shifted to avoid exceeding ERCOT's the acceptable volumes of 814_20s
Note on AO23: cmeiners: Shifted to avoid exceeding ERCOT's acceptable volume of 814_20s
Note on AO24: cmeiners: shifted to avoid exceeding ERCOT's limit for 814_20s

## Guidelines for Submission
Rules for Submission of Large Volume of Transactions
Block out all maintenance and release windows
Block out ERCOT holidays
Block out Tuesday or Wednesday, if possible.
Rate of Submission:
During the week
Prior to 5 PM
Submit transactions at a rate of once an hour
In bundles that are no more than 33,000 transactions at a time
OR
After 5 PM
No restrictions as to rate or number of transactions
On weekends
No restrictions as to rate or number of transactions
Note: Per Diana Ott - annual validation should be completed by 11/13.
All TDSPs aside from Oncor have confirmed they can be done by then except for Oncor as of 11/14.

## schedule of 814_20 volumes
|  | November |  |  |  | December |  |  |  | January
|  | Oncor | CenterPoint | Total Expected |  | Oncor | CenterPoint | Total Expected |  | Oncor | CenterPoint | Total Expected
Tues | 3 |  |  |  | 1 |  | 2000 | 2000
Wed | 4 |  |  |  | 2 | 7000 | 2000 | 9000
Thurs | 5 |  |  |  | 3 | 7000 | 11560 | 18560
Fri | 6 |  |  |  | 4 | 30000 | 16773 | 46773 | 1 |  | New Year's Weekend
Sat | 7 |  |  |  | 5 | 31000 | 17511 | 48511 | 2
Sun | 8 |  |  |  | 6 |  |  |  | 3
Mon | 9 |  |  |  | 7 | 53000 | 2238 | 55238 | 4 | 53000 |  | 53000
Tues | 10 |  |  |  | 8 | 7000 | 2000 | 9000 | 5 | 7000 | 3000 | 10000
Wed | 11 |  |  |  | 9 | 30000 | 2000 | 32000 | 6 | 53000 | 2505 | 55505
Thurs | 12 |  |  |  | 10 | 7000 | 8388 | 15388 | 7 | 7000 | 5680 | 12680
Fri | 13 |  |  |  | 11 | 30000 | 3852 | 33852 | 8 | 7000 | 5796 | 12796
Sat | 14 |  |  |  | 12 | 8000 | December Retail Release |  | 9 | 8000 | 3911 | 11911
Sun | 15 |  |  |  | 13 |  |  |  | 10
Mon | 16 |  |  |  | 14 | 53000 | 8038 | 61038 | 11 | 7000 |  | 7000
Tues | 17 |  |  |  | 15 | 7000 | 2000 | 9000 | 12 | 7000 | 3000 | 10000
Wed | 18 |  |  |  | 16 | 53000 | 8772 | 61772 | 13 | 7000 | 7198 | 14198
Thurs | 19 |  |  |  | 17 | 30000 | 2000 | 32000 | 14 | 7000 | 3614 | 10614
Fri | 20 |  |  |  | 18 | 30000 | 2145 | 32145 | 15 | 7000 | 3000 | 10000
Sat | 21 | PR80027 Go Live |  |  | 19 | 31000 | 2000 | 33000 | 16 | 8000 | 4778 | 12778
Sun | 22 |  |  |  | 20 |  |  |  | 17
Mon | 23 |  |  |  | 21 | 53000 | 5185 | 58185 | 18 | 7000 | 1362 | 8362
Tues | 24 |  | 2000 | 2000 | 22 | 7000 | 2000 | 9000 | 19 | 7000 | 3000 | 10000
Wed | 25 |  | 2000 | 2000 | 23 | 30000 | 11595 | 41595 | 20 | 7000 | 3000 | 10000
Thurs | 26 | Thanksgiving Weekend |  |  | 24 | Christmas Weekend |  |  | 21 | 7000 | 3000 | 10000
Fri | 27 |  |  |  | 25 |  |  |  | 22 | 7000 | 3000 | 10000
Sat | 28 |  |  |  | 26 |  |  |  | 23 | 8000 | January Retail Release
Sun | 29 |  |  |  | 27 |  |  |  | 24
Mon | 30 |  |  |  | 28 | 7000 |  | 7000 | 25 | 7000 | 3832 | 10832
Tues |  |  |  |  | 29 | 7000 | 2000 | 9000 | 26 | 7000 | 3000 | 10000
Wed |  |  |  |  | 30 | 53000 | 7096 | 60096 | 27 | 7000 | 3000 | 10000
Thurs |  |  |  |  | 31 | 30000 | 2000 | 32000 | 28 | 7000 | 3664 | 10664