GENERATION INTERCONNECTION OR

CHANGE REQUEST PROCEDURE

Date Implemented

Version 4.10.3

Document Revisions

| Date | Version | Description | Author(s) |
| --- | --- | --- | --- |
| 12/2/2009 | 2.0 | Modified Procedure document as developed through RPG | ERCOT/RPG |

Table of Contents

1	INTRODUCTION	1

1.1	Purpose	1

1.2	Applicability	1

1.3	Effective Date	2

1.4	Modification and Approval Process	2

2	INTERCONNECTION PROCESS AND PROCEDURES	2

2.1	Generation Interconnection or Change Request (GINR) Application	2

2.1.1	Submitting Generation Interconnection or Change Request to ERCOT	2

2.1.2	Interconnection Request Screening Study Fees	3

2.1.3	Where to Submit Data and Fees	3

2.1.4	Unique Project Identification	4

2.2	Full Interconnection Study Request	4

2.2.1	Submitting FIS Request to ERCOT	4

2.2.2	FIS Request Application Fees	5

2.2.3	Where to Submit Data	5

2.2.4	Use of the Resource Asset Registration Form	5

2.3	Modifications to Request	6

3	STUDY PROCESSES AND PROCEDURES	7

3.1	Security Screening Study	7

3.2	Full Interconnection Study	8

3.2.1	TSP Communication	8

3.2.2	Full Interconnection Study Process Overview	8

3.2.3	Full Interconnection Study Elements	9

3.2.4	Economic Study	12

3.2.5	FIS Study Report and Follow-up	12

3.2.6	Proof of Site Control	13

3.2.7	Confidentiality	13

3.3	Interconnection Agreement	14

3.3.1	Standard Generation Interconnection Agreement	14

3.3.2	Other Arrangements for Transmission Service	15

3.3.3	Provisions for Municipals and Cooperatives	15

4	INTERCONNECTION DATA, FEES, AND TIMETABLES	15

4.1	Generation Plant Data Requirements	15

4.1.1	Application and Security Screening Study	16

4.1.2	Full Interconnection Study	16

4.1.3	Prior to Start of Construction	17

4.1.4	Prior to Commercial Service	17

4.1.5	During Continuing Operations	17

4.2	Interconnection Study Fees	17

4.2.1	Security Screening Study Fee	17

4.2.2	Stability Modeling Fee	18

4.2.3	Full Interconnection Study Fee/Cost	18

4.3	Interconnection Process Timetables	18

4.4	GENERAL AND TECHNICAL STANDARDS	20

4.4.1	Transformer Tap Position	20

APPENDIX A	21

4.5	GENERATION ENTITY INFORMATION SHEET	22

APPENDIX B	23

4.6	GENERATOR INTERCONNECTION REQUEST SCREENING STUDY DATA SHEET	23

# INTRODUCTION

## Purpose

The primary purpose of the ERCOT Generation Interconnection or Change Request Procedure (Procedure) is to define the requirements and processes used to facilitate new or modified generation interconnections with the transmission system of the Electric Reliability Council of Texas (ERCOT).  The activities outlined in this Procedure are expected to:

- Determine the facilities required to directly interconnect new or modified generation to the ERCOT System;

- Ensure that the interconnection of the new or modified generation is accomplished in a manner that maintains the reliability of the ERCOT System and its compliance with the North American Electric Reliability Corporation (NERC) Reliability Standards, ERCOT Protocols and Operating Guides;

- Increase the quality of communications between the generating entity (GE), transmission service provider (TSP), and ERCOT;

- Provide for the best available information on future capacity additions for use in identifying, forecasting, and analyzing both short- and long-range ERCOT capabilities, demands, and reserves; and,

- Provide for accurate and appropriate data to aid ERCOT Staff and stakeholders in identifying and developing potential transmission improvement projects to alleviate expected transmission constraints in order to maintain the reliability of the ERCOT System.

The requirements and procedures in this Procedure conform to all applicable rules, standards, protocols, and guides of the Public Utility Commission of Texas (PUCT), NERC, and ERCOT.  In the event of a conflict between this Procedure and those applicable rules, standards, protocols, and guides of the PUCT, NERC and ERCOT, then such rules, standards, protocols and guides will take precedence over the Procedure.

## Applicability

The requirements in this Procedure are applicable, in general, to the following:

- New generating Resources or storage devices, with an aggregate power output (gross generating unit output minus auxiliary Load directly related to the generating unit) of 10 MW or greater, planning to interconnect to transmission in the ERCOT System.

- Existing generating Resources interconnected in the ERCOT System that are seeking to:

  - upgrade the rated capacity of the Resource by 10 MW or greater within a single year,

  - re-power the Resource, or

  - change the physical or electrical interconnection of the Resource.

Interconnection requirements for on-site distributed generation are not subject to this Procedure but are addressed in PUCT Substantive Rules §25.211 (Interconnection of On-Site Distributed Generation) and §25.212 (Technical Requirements for Interconnection and Parallel Operation of On-Site Distributed Generation).

## Effective Date

This Procedure and modifications thereto will become effective upon approval and will apply to all future and current interconnection requests that have not yet signed an Interconnection Agreement (IA) by the date of this approval.

## Modification and Approval Process

Modifications to this Procedure will be proposed by ERCOT, presented to the Regional Planning Group (RPG) and Technical Advisory Committee (TAC) for comment prior to approval, and approved by the ERCOT CEO.

# INTERCONNECTION PROCESS AND PROCEDURES

The ERCOT interconnection process is designed in accordance with PUCT Substantive Rule §25.198 (Initiating Transmission Service) which delegates to ERCOT the responsibility for implementing the transmission interconnection process.

## Generation Interconnection or Change Request (GINR) Application

Any generating entity (GE) seeking an interconnection to the ERCOT System, as applicable in Section 1, Applicability, must submit the following to ERCOT:

- a generation entity information sheet (Appendix A),

- a generation interconnection request screening study data form (Appendix B), and

- the appropriate fee (as detailed in Section 4.2.1).

### Submitting Generation Interconnection or Change Request to ERCOT

All GINR Applications and supporting data submittals shall be delivered to ERCOT by standard mail, facsimile (fax), or Internet email. Applications and supporting data shall be sent as discrete file attachments.  The application with signature may be in PDF form if desired but the supporting data shall be sent as a Microsoft Excel file attachment so that data may be easily extracted to reduce transcription errors.

In order to clearly identify GINR Applications, it is important that GENERATION INTERCONNECTION REQUEST is the first line of the address field or is in the subject field of an email request.

The GE shall include in the GINR Application all information necessary to allow for timely development, design, and implementation of any electric system improvements or enhancements required by ERCOT and the TSP to reliably meet the interconnection requirements of the proposed generation.  This information shall be of sufficient detail for use in establishing transfer capabilities, operating limits (including stability), and planning margins to provide both reliability and operating efficiency as well as facilitating coordinated planning for future transmission system additions.

ERCOT Staff will notify the GE within 7 business days through telephone call or email if the generation interconnection request application fails to include the applicable fees or the information that is necessary to perform the initial screening interconnection studies.  If the applicant fails to respond to ERCOT’s inquiries within 10 business days, the GINR will be deemed incomplete and rejected. ERCOT shall notify the applicant if such condition occurs.

Once the application has been deemed materially complete, ERCOT Staff will date-stamp the application, add the interconnection request to the ERCOT interconnection list, and notify the GE of receipt of the completed application within 10 business days.  The GE should note that the date stamp is not a reservation of transmission capacity, either planned or unplanned.

An ERCOT Staff engineer will be assigned to oversee the interconnection study process and answer questions concerning the interconnection screening study and process.   Once assigned, this engineer will contact the GE and will be the primary ERCOT contact for interconnection studies.  If during the course of the studies, additional information is needed by ERCOT from the GE, ERCOT will immediately notify the GE and the GE will have 10 business days to answer the request for additional information without impacting the study timeline.

Prior to the initial contact from this engineer, GEs should direct questions concerning this Procedure to GINR@ercot.com.  The GE should contact their ERCOT Wholesale Services client representative for all queries that are not related to the interconnection studies.

If a generation facility that uses the same physical transmission interconnection is to be built in stages with in-service dates more than one year apart, the stages should be treated as separate interconnection requests but may be included in the same study.

### Interconnection Request Screening Study Fees

In order to consider the GINR, a security screening study fee   must be remitted to ERCOT along with the generation interconnection request application as explained in detail in Section 4.2.1.    The security screening study fee is non-refundable.  The GE may choose to wire money to ERCOT to comply with the fee requirements.

For instructions on how to wire the funds to ERCOT, send an email to GINR@ercot.com requesting the account and wiring information.  For security purposes, this information has not been included in this Procedure nor is it posted on an ERCOT website.

If submitting the payment via standard mail, please make the check payable to Electric Reliability Council of Texas, Inc.  Please contact GINR@ercot.com to alert ERCOT to this method of submission for the application.

### Where to Submit Data and Fees

All standard mail submissions for the application, data, or fees shall be sent to the following address:

GENERATION INTERCONNECTION REQUEST

ATTN: Manager, Regional Planning

ERCOT, INC.

2705 WEST LAKE DRIVE

TAYLOR, TEXAS 76574-2136

Submission of the application and data via email shall be addressed to GINR@ercot.com. All data for studies shall be submitted electronically.

### Unique Project Identification

ERCOT Staff will assign a unique name to all GINRs according to the following convention:

yrINRxxxxp

where:

yr is the calendar year the generation is anticipated to be online (08, 09, 10)

INR indicates interconnection request

xxxx is a sequence number beginning with 0001 (reset for each year)

p is an optional, sequential alphabetical identifier beginning with ‘a’ to be used for phased projects

It is vital that all correspondence relating to a specific GINR, security screening or full interconnection study reference this unique project identification number once it has been assigned by ERCOT.

## Full Interconnection Study Request

Any GE seeking a Full Interconnection Study (FIS) for interconnection to the ERCOT System, as applicable in Section 1, Applicability, must submit the following to ERCOT:

- a notice to proceed with the FIS,

- the Resource Asset Registration Form (RARF) excel spreadsheet with applicable information required for interconnection studies as described in the RARF instructions (the RARF is located in the Resource Asset Registration Forms zip file located at http://www.ercot.com/gridinfo/generation/index).

- a stability modeling fee (as detailed in Section 4.2.2), and

- proof of site control (see Section 3.2.6)

In addition, there will be a FIS fee/cost paid directly to the TSP(s) (see Section 4.2.3).

### Submitting FIS Request to ERCOT

All FIS requests and supporting data submittals shall be delivered to ERCOT by Internet email. The supporting data shall be sent as discrete file attachments.

In order to clearly identify the GINR, it is important that the associated project INR number is referenced in the subject field of all communications.

The GE shall include in the FIS request all information necessary to allow for timely development, design, and implementation of any electric system improvements or enhancements required by ERCOT and the TSP to reliably meet the interconnection requirements of the proposed generation.  This information shall be of sufficient detail for use in establishing transfer capabilities, operating limits (including stability), and planning margins to provide both reliability and operating efficiency as well as facilitating coordinated planning for future transmission system additions.

Upon receipt of the FIS request, the assigned ERCOT Staff engineer will continue to be the primary ERCOT contact for the GE, ensuring RARF data is communicated to the TSP. The engineer will initiate a meeting between the TSP(s) and the GE. If during the course of the studies, additional information is needed from the GE, ERCOT will immediately notify the GE and the GE will have 10 business days to answer the request for additional information without impacting the study timeline.

### FIS Request Application Fees

When a FIS is requested, a stability modeling fee must be remitted to ERCOT as explained in detail in Section 4.2.2.  The stability modeling fee is non-refundable.  The GE may choose to wire money to ERCOT to comply with the fee requirements.

For instructions on how to wire the funds to ERCOT, send an email to GINR@ercot.com requesting the account and wiring information.  For security purposes, this information has not been included in this document nor is it posted on an ERCOT website.

If submitting the payment via standard mail, please make the check payable to Electric Reliability Council of Texas, Inc.  Please contact GINR@ercot.com to alert ERCOT to this method of submission for the application.

### Where to Submit Data

Submission of the data via email shall be addressed to GINR@ercot.com. All design data shall be submitted electronically.

### Use of the Resource Asset Registration Form

The GE shall use the RARF in order to facilitate data submittal for the planning studies and to reduce duplication/redundancy of forms. Key portions of the workbook include, but are not limited to, the following tabs:

- Site Information

- Unit Information

- Reactive Capability

- Planning

- Protection

- Subsynchronous Resonance

The RARF and all updates shall be submitted by the GE and sent to the assigned ERCOT Staff engineer and to GINR@ercot.com. While the TSP may request information necessary to perform the FIS from the GE directly, and the GE must provide this information to the TSP in order to facilitate the completion of the FIS in a timely manner, the GE must also contemporaneously submit to ERCOT an update to the RARF containing the information.  ERCOT will forward this information along with a change report to the TSP(s) for use with the FIS.  The planning submittals of the RARF are considered planning data and should accurately reflect the design of the facility. Please note this process does not meet the RARF submittal requirements contained in the ERCOT Protocols, but the use of this format is intended to facilitate the preparation of the data required for that process and the continuity of data between the interconnection study process and the data submitted for Resource registration.

## Modifications to Request

The GE shall maintain communication with ERCOT Staff and the TSP at all stages of the generation interconnection process.  The GE must also notify both ERCOT and the TSP of any changes that would affect the technical attributes and/or timeline of the project, including, but not limited to, capacity, in-service date, changes in location, changes in generator type, interconnection agreement execution, air permit acquisition, etc. as soon as these changes are known.   The GE shall maintain the RARF with the most up-to-date design information and shall submit the updated information to ERCOT and the TSP.   All changes of ownership must be communicated to ERCOT and the TSP when the ownership transfer occurs during the interconnection process and should include evidence of the ownership change such as a purchase/sale agreement.

If, after receipt of the updated RARF, ERCOT or the TSP determines that changes to the project (submitted after the application was deemed complete) are sufficiently substantive to warrant new studies, then ERCOT may require updated studies to be performed before the generator is allowed to interconnect to the ERCOT System.  If these changes are submitted prior to completion of the FIS, the updated studies may be included as a part of the FIS.  If the changes are submitted after the completion of the FIS, or if the requested capacity increases by more than 20%, ERCOT shall require the GE to submit a new request for the additional capacity or to submit a new request for the entire project.  ERCOT may, at its discretion, require the GE to submit a new request for significant capacity decreases or capacity increases of less than 20%, particularly if other changes to the request are also made, such as changes to the in-service date.  ERCOT’s determination of whether new studies are needed in no way affects the ongoing obligations of the GE and TSP to comply with NERC Standards, and ERCOT Protocols and Operating Guides.

The obligation to maintain the RARF with the most up-to-date design information and to notify ERCOT and the TSP of such changes continues even after an interconnection agreement is signed.  If ERCOT reasonably believes that the changes might affect the reliable operation of the ERCOT System, then the generator may not be allowed to connect to the ERCOT System until studies can be completed to evaluate the effect of the changes.  If these additional studies show a negative impact on the ERCOT System, the generator may not be allowed to connect until these negative impacts are rectified.

In addition, the GE shall notify ERCOT of the status of all applicable air permits with the initial interconnection application. The GE shall provide status updates to ERCOT and the TSP when a permit for the project has been issued by the Texas Commission on Environmental Quality (TCEQ). The GE shall also notify ERCOT if permits delay the FIS as well as when it has given the TSP the notice to proceed with the FIS.  The GE has an on-going obligation to provide timely updates to ERCOT and the TSP regarding changes to any information submitted as part of the generator interconnection process.

# STUDY PROCESSES AND PROCEDURES

## Security Screening Study

For each proposed generation interconnection or change project, ERCOT Staff will conduct a steady-state security screening study (including power flow and transfer studies) based on the expected in-service year to identify potential generation dispatch limitations based on the site proposed by the GE.  The security screening study is a high level review of the project and generally includes a number of initial assumptions from both ERCOT and the GE.  In accordance with PUCT Substantive Rule §25.198 (Initiating Transmission Service), ERCOT will establish the scope of the security screening study, not the GE.

The results of this study will provide an indication of the level at which the generator can expect to operate simultaneously with other known generation in the area before significant transmission additions or enhancements may be required.  During the course of this study, ERCOT Staff may consult with the affected TSP(s), if needed, to ensure the most efficient means of assuring the feasibility of transmission service is identified and examined.

During the security screening study phase of the interconnection process, and in accordance with the ERCOT Protocols, all data, documents, and other information required by ERCOT from a GE related to a request for generation interconnection are considered “protected information” to the extent that such information is not otherwise publicly available.  As a result, ERCOT Staff shall not publicly release any of the “protected” data, documents, or other information during the screening study phase except to TSPs.  Information about generation interconnections in the security screening study phase will only be released publicly in aggregated amounts.

Upon completion of the security screening study, ERCOT Staff will present the GE with a preliminary report indicating future transmission additions or enhancements that may be required to obtain the full transfer of the proposed new or modified generation at the specified in-service year.  ERCOT will also inform the GE about any additional transmission system improvements estimated to be required for the continued security and reliability of the ERCOT system.  This report does not imply any commitment by ERCOT or any TSP to recommend or construct these transmission additions or enhancements.

Following the presentation of the security screening study results, the GE must determine whether it wants to continue the interconnection process by formally requesting a full interconnection study or to withdraw its GINR.  Should the GE decide to go forward with the project represented by this unique project number, the GE must notify ERCOT in writing within 180 calendar days of its desire to pursue a full interconnection study.  ERCOT Staff will notify the TSP(s) and will begin initiation and coordination of the full interconnection study only after receiving this notification from the GE.

Unless ERCOT receives notice from the GE of its decision to go forward with the proposed project, ERCOT will not initiate a full interconnection study.  Such notice must be received in writing by ERCOT within 180 calendar days following completion of the security screening study.

Should the GE decline to notify ERCOT of their intent to initiate a full interconnection study within the 180 calendar days, ERCOT will consider the interconnection request cancelled and no longer valid.  Subsequently, should the GE wish to proceed after the initial 180-day period,  ERCOT will consider the original security screening study invalid and the process must begin again starting with a new request for a security screening study and payment of the appropriate fee.  The GE will also be required to provide to ERCOT any updates or changes in the project’s generation plant data.

## Full Interconnection Study

A Full Interconnection Study (FIS) consists of the set of steady-state, dynamic, short-circuit, and facility studies that are necessary to determine any facilities that are required to reliably interconnect new or modified generation to the ERCOT System.  The FIS is not intended to determine the deliverability of power from the plant to market or the facilities required to ensure that the plant does not experience any congestion-related curtailment.  To initiate the FIS, the GE must notify ERCOT in writing of its desire to pursue a FIS within 180 calendar days of the completion of its Security Screening Study.  The GE must also provide the appropriate stability modeling fee and proof of site control.

The GE can decide to request a FIS at any time after the initial GINR  application is deemed complete by ERCOT and is not dependent on the completion of the Security Screening Study.  Requesting both studies at the same time may shorten the overall time to complete the generation interconnection process due to overlap of work on both studies.

### TSP Communication

A confidential email list, known as the Transmission Owner Generation Interconnection email list, will be set up to facilitate communication of confidential generation interconnection-related information among TSP(s) and ERCOT Staff.  Membership to this email list will be limited to ERCOT Staff and appropriate TSP personnel.

### Full Interconnection Study Process Overview

Within five (5) business days of receiving notice to proceed with a FIS, proof of site control and correct fee(s) from the GE, ERCOT will designate a TSP to lead the FIS and contact that TSP to schedule a FIS scope meeting.   ERCOT will select the lead TSP based upon its preliminary analysis with respect to the most likely point of interconnection.   For GEs that have previously developed generation projects in ERCOT with a particular TSP, the FIS scope meeting may be skipped if the GE, ERCOT, and the TSP(s) agree to do so.  In these cases the timeline for the GE and TSP to reach agreement on the FIS scope will start on the date the TSP(s) was notified of the GEs decision to proceed with a FIS.

At the same time ERCOT will send notification of the project FIS to all other TSP(s) via the confidential Transmission Owner Generation Interconnection email list.  It is the responsibility of each TSP to determine if the proposed project may have a material impact on their transmission facilities and to what extent they should participate in the FIS.  Each TSP desiring to participate in the FIS should notify the lead TSP.  The lead TSP will have the responsibility to involve all other TSP(s) that have expressed an interest in the FIS as appropriate for their expressed level of involvement to the extent that such involvement is reasonable.

At the FIS scope meeting the GE will present the proposed interconnection or change request and ERCOT will review the results of the security screening study.  The lead TSP will facilitate a general discussion of the preliminary study scope of work for the FIS.

The GE and the TSP(s) must reach agreement on the FIS scope within sixty (60) calendar days of the FIS scope meeting.  The assistance of more than one TSP may be required in areas where transmission facilities are provided by multiple TSP(s).  In these cases it may be necessary for the GE to execute study agreements with multiple TSP(s).

The FIS scope agreement shall include all assumptions, timetables, study cost estimates and payment schedules, and the determination of all requirements for interconnection.  The GE and the TSP(s) have flexibility in reaching agreement on the scope of the FIS, as long as the scope includes at least all studies needed to meet the requirements of this Procedure.  The GE and the TSP(s) shall consider the ERCOT security screening study and other preliminary studies and documents provided by the GE when developing the FIS scope.  The FIS can be divided into several distinct study phases such that notice to proceed from the GE is required before starting each phase.

The TSP(s) shall send the FIS scope to the confidential Transmission Owner Generation Interconnection email list for review and comment by ERCOT and other TSP(s).  Comments must be made within ten (10) business days.

If the GE can not agree to the FIS study scope within the 60-day period, ERCOT will attempt to mediate an agreement but if unsuccessful will consider whether the GE’s interconnection request should be terminated.  If the request is terminated, and if the GE subsequently determines to move forward with the interconnection, ERCOT shall require the GE to begin the interconnection process again, including a new security screening study and payment of the appropriate fee(s).

### Full Interconnection Study Elements

The FIS consists of a series of distinct study elements.  Some of the elements may or may not be necessary for the TSP(s) to undertake and complete depending upon the provisions of the interconnection study scope agreement.  The primary purpose of the FIS is to determine the most effective and efficient manner in which to satisfy the desire of the GE’s interconnection request while continuing to maintain the reliability of the ERCOT System by meeting all NERC Reliability Standards, ERCOT Protocols and Operating Guides that would be affected by the interconnection and operation of the proposed generation.  The scenarios and base cases being used for these studies to determine potential transmission limitations will be documented in the FIS study scope.

Each generation resource that requires a separate physical transmission interconnection will be treated as an individual study to be analyzed separately from all other such requests unless otherwise agreed to by the GE in the interconnection study scope agreement

The FIS process includes developing and analyzing various computer model simulations of the existing and proposed ERCOT generation/transmission system.  The results from these simulations will be utilized by the TSP(s) to determine the impact of the proposed interconnection.

The TSP(s) will also examine normal transmission operations as well as potentially adverse, or contingency, conditions in order to identify and analyze the reliability and effectiveness of various interconnection design alternatives in alleviating or mitigating any undesirable performance of the interconnection under a variety of operating conditions.

In comparing interconnection alternatives, the TSP(s) will consider such information as interconnection cost and construction schedule, impact to short- and long-range reliability, operational flexibility, and compatibility with future transmission plans for each alternative.  The TSP(s) are not bound to only study interconnection alternatives suggested by the GE  The study should include analysis demonstrating the adequate reliability of any temporary interconnection configurations.

The TSP(s) may reserve the right to update the final FIS report in the event that changes occur to the ERCOT grid (i.e. new generation additions not originally considered execute interconnect agreements) after the report is completed and before the interconnect agreement is executed.

All studies undertaken will be performed in compliance with all applicable PUCT Substantive Rules, ERCOT Protocols and Operating Guides, NERC Reliability Standards, good utility practice, and the guidelines below unless otherwise directed by ERCOT Staff.

Steady-State and Transfer Analysis.   The steady-state interconnection study base case shall be created from the most recently approved ERCOT Steady-State Working Group (SSWG) base case.  TSP(s) or ERCOT Staff may, at their discretion, remove any future (currently non-existing) transmission facility from the steady-state interconnection study base case that may significantly affect the interconnection study results and has not already undergone appropriate RPG review.  In addition, ERCOT Staff, and TSP(s) may request that generation resources proposed in other prior generation interconnection requests be included in the steady-state interconnection study base case if deemed appropriate.  ERCOT Staff may request a list of the interconnection requests included in the FIS by the TSP.

Using the steady-state interconnection study base case, the TSP(s) shall perform contingency analyses as required by the NERC Reliability Standards, ERCOT Protocols and Operating Guides and identify any additional transmission facilities that may be necessary to ensure that expected system performance conforms to these standards.  All facilities necessary to accommodate the proposed generation will be determined and clearly identified in the report for this part of the FIS.  Any other facility that cannot be constructed or otherwise completed in time to accommodate the initial commercial operations date of the generation will be identified and communicated to the GE along with any likely limitations of generation output that may result.

Loss-of-generation analyses shall assume that the lost generation will be replaced from all remaining ERCOT units in proportion to their nominal capacity (i.e., inertial response) and respecting generation limits.

The lead TSP is responsible for completing an analysis of any contingency events or outages anticipated to result in a violation of the NERC Reliability Standards, ERCOT Protocols and Operating Guides, regardless of which TSP owns the facilities involved.  The results of this analysis will be shared with those TSP(s) that have facilities involved in planning criteria violations and they will be responsible for attempting to verify the validity of the anticipated violations.

System Protection (Short-Circuit) Analysis.  The full interconnection study scope agreement will specify locations where available short-circuit fault duty will be identified, calculated, and documented.  If any of the required generator interconnect-associated transmission system improvements result in transmission facility (ies) violating the TSP’s short-circuit criteria, the TSP shall plan to provide facilities to address such violations.  The TSP will determine the maximum available fault currents at the interconnection substation for determining switching device interrupting capabilities and later for protective relay setting purposes.

Dynamic and Transient Stability (Unit Stability, Voltage, Subsynchronous Resonance) Analysis.  At the discretion of the TSP(s) or ERCOT Staff, transient stability studies will be performed  if necessary to meet NERC Reliability Standards, ERCOT Protocols and Operating Guides applicable for the generator and for the ERCOT System. If the TSP(s) in charge of these stability studies decides not to conduct the studies, the TSP must provide a written justification in lieu of the study report.  When performing such studies, all existing or committed generation in the area of study will normally be represented at full net output or better model (some combined cycle units or coal plants might be modeled at full gross output together with its auxiliary load).  Any resulting increase in generation will be balanced as addressed in the interconnection study scope agreement.

Stability study base cases shall be formed from the latest available approved ERCOT SSWG base cases consistent with the most recently approved ERCOT Dynamics Working Group (DWG) stability data base. The initial transmission configuration in the area of study included in a stability study base case shall be identical to that used in the steady-state studies of the same period.  Any previously identified transmission improvements that will not be in service prior to the in-service date of the generation under study shall not be included in the stability study base case.

Transient stability studies will analyze the performance of the proposed generation interconnection and the ERCOT System in terms of angular stability, voltage stability and excessive frequency excursions.  Additional studies may include small signal stability, voltage stability, subsynchronous resonance or critical clearing time analyses where the number of cycles for which a transmission line can sustain a fault without causing loss of synchronism of any of the generators is compared to the response of the protection systems.  Such studies should incorporate reasonable conservative assumptions regarding plant operating conditions.  Proposed analyses shall be identified and defined in the full interconnection study scope agreement.

All stability studies shall be performed in accordance with ERCOT’s Planning Criteria, and the results shall identify any additional transmission facility(ies) or other action(s) necessary to ensure conformance to that standard.

Facility Study.  At a minimum, the facility study provides complete details and estimated cost of the facility requirements for the direct interconnection of the proposed generation project to the TSP.

Results of the facility study will provide conceptual design descriptions, construction milestones, and detailed cost estimates for all direct interconnection-related transmission and substation facilities proposed to be installed in accordance with the findings and recommendations of the FIS.

### Economic Study

ERCOT Staff is required to perform an independent economic analysis of the transmission projects that are identified through this process as being needed for the direct connection of the proposed generation facility and which are expected to cost more than $25 million. This economic analysis is performed only for informational purposes; as such, no ERCOT endorsement will be provided.

At the point in the FIS that the lead TSP determines that it will recommend direct interconnection facilities for the proposed generation project which have an estimated cost expected to exceed $25 million, the lead TSP will communicate this finding, within 10 business days of such determination, to ERCOT Staff and other TSP(s) via the confidential Transmission Owner Generation Interconnection email list.  This communication will include all available information upon which that finding is based, including but not limited to: a description of the direct interconnection facilities; information necessary to modify a powerflow case to include those facilities (idev or similar format); any information obtained from the generation project that would be helpful in modeling the generator for the study; and, the estimated cost of the facilities.  ERCOT will request, and the proposed generator will provide, information necessary to represent the costs of the proposed generation facility in the economic study.

ERCOT will generally complete this economic study within 90 calendar days, and will inform the TSP(s) and GE if additional time is required.  ERCOT will provide the results of the economic study to the TSPs via the Transmission Owner Generation Interconnection email list and the proposed generator when it is complete.

### FIS Study Report and Follow-up

The TSP(s) will present a preliminary report of their findings and recommendations for each of the study elements to ERCOT Staff and other TSP(s) via the confidential Transmission Owner Generation Interconnection email list and to the GE.  Any questions, comments, proposed revisions, or clarifications by any party shall be made in writing to the TSP within ten (10) business days after the issuance of each study report, which may cover one or more study elements. After considering the information received from ERCOT and other TSPs, the study element(s) report will be deemed complete and a final report shall be provided to the GE, ERCOT, and all TSP(s).   The 10 business day review period will be used by the ERCOT Staff to determine if any transmission upgrades proposed and clearly identified in the Steady-State Study Report need to be submitted to the RPG review process.  Refer to Section 25 of the ERCOT Protocols for more information on the process to review transmission upgrades that are unrelated to the direct connection of new or modified generation.

Upon the transmittal of the last study element report, the TSP issuing such report will indicate that such study element report is the final report to be issued associated with the entire full interconnection study.  At the end of the 10 business day review period following the issuance of the final full interconnection study element report, the full interconnection study will be deemed complete and the GE and TSP will have the specified amount of time to complete an interconnection agreement as detailed in this document. If an economic study of the direct connection facilities is required, pursuant to Section 3.2.4, Economic Study, and has not yet been completed, the GE and TSP(s) may mutually decide whether that study must be completed before the FIS is deemed complete.

Should the GE wish to proceed with the proposed generation interconnection, the GE must execute an interconnection agreement with the respective TSP within 180 calendar days following the completion of the FIS (includes all major study element reports).

If, during the time after this FIS is completed and before the interconnection agreement is executed changes occur that substantially differ from the assumptions used for the FIS, ERCOT and the TSP(s) shall determine the impact of the changes on the results of the FIS.  All changes should be submitted to ERCOT on the RARF for a change comparison. If the proposed direct interconnection is negatively affected by the changes, the TSP(s) will work with the GE on a refresh of the FIS.

### Proof of Site Control

Before ERCOT will proceed with the initiation of a full interconnection study, the GE must submit to ERCOT proof of site control.  To establish proof of site control, the GE must demonstrate through an affiliated company, through a trustee, or directly in its name that:

- The GE is the owner in fee simple of the real property to be utilized by the facilities for which any new generation interconnection is sought, or

- The GE holds a valid written leasehold interest in the real property to be utilized by the facilities for which new generation interconnection is sought, or

- The GE holds a valid written option to purchase or obtain a leasehold interest in the real property to be utilized by the facilities for which new generation interconnection is sought, or

- The GE holds a duly executed written contract to purchase or obtain a leasehold interest in the real property to be utilized by the facilities for which new generation interconnection is sought.

The GE must notify ERCOT of any substantive change in status of the arrangement used to demonstrate site control.

The GE must maintain site control throughout the duration of the FIS and until execution of an interconnection agreement.  Otherwise, ERCOT will consider the request for interconnection withdrawn as of the date of the loss of site control unless the applicant can show within 30 calendar days that it has re-established site control or has established control of a new site that would not result in any material modification of any interconnection study requested under the current application.

### Confidentiality

Once a FIS is requested by the GE, in accordance with Protocol 1.3.1.2, the following information about the potential project will become public:

1.	INR Number

2.	Facility nameplate capacity

3.	Anticipated in-service date

4.	Facility fuel type

5.	County where facility located

All other data, documents or other information regarding the generation interconnection request (including the identity of the GE) will remain protected information until ERCOT receives written notice from the GE that this information may be made public or until a Standard Generation Interconnection Agreement (SGIA) is executed.  Since the FIS scope agreement contains possibly confidential cost estimates and represents an agreement between the GE and the lead TSP, it will remain as protected information and will not be released to parties other than those who are members of the confidential Transmission Owner Generation Interconnection email list except as required in a court of law or by regulatory authorities having jurisdiction.  Once classified as a public project through one of these steps, ERCOT will post the project description, all generation interconnection study reports, the results of the economic analysis of direct interconnection facilities costing over $25 million, and any information developed throughout the interconnection study process about transmission improvement projects that may be submitted for RPG review as a result of the new generation on the ERCOT website.

The lead TSP will notify the RPG email list within ten business days of the signing of an Interconnection Agreement where the cost of the direct interconnection facilities is greater than $25 million.

## Interconnection Agreement

### Standard Generation Interconnection Agreement

Should the GE decide to proceed with the construction and completion of the proposed generation project and interconnection within the 180-day period following the completion of the FIS, they will execute an interconnection agreement with their respective TSP as a condition for obtaining transmission service.  This is in accordance with PUCT Substantive Rule §25.195 (Terms and Conditions for Transmission Service).  The GE and the TSP shall use the PUCT’s Standard Generation Interconnection Agreement (SGIA).   A template of the SGIA can be found on the ERCOT website.

Before an SGIA is signed, all studies included in the FIS scope must be completed, or a plan to meet and maintain compliance with all NERC Reliability Standards, ERCOT Protocol and Operating Guide requirements related to the interconnection by the time that the generation facility is energized must be developed and documented.  The completion of an SGIA in no way affects the generator’s ongoing obligation to comply with NERC Standards, and ERCOT Protocols and Operating Guides.

While ERCOT is the proper entity for a GE to request a generation interconnection or change process, the actual negotiation of the interconnection agreement shall be conducted directly between the GE and the TSP.  ERCOT is not a party to the interconnection agreement and will not participate in these negotiations, nor will ERCOT arrange interconnection agreements.

The signed interconnection agreement will be transmitted to ERCOT by the TSP within 10 business days of the execution of the interconnection agreement.  TSP(s) are also required to submit this signed interconnection agreement to the PUCT within 30 days of its execution.  The PUCT may post it through their filing system as open information, unless good cause has been shown for portions of the filings to be confidential. (PUCT Substantive Rules 25.195(e)) The GE should also provide ERCOT with the status of its air permits, when it receives a permit for its project, and when it gives the TSP the notice to proceed.

### Other Arrangements for Transmission Service

In certain situations, the GE and the TSP may make alternative arrangements under which the TSP agrees to begin design or construction of facilities prior to the execution of the interconnection agreement.  In other instances, a notice to proceed may not be issued until some time after the interconnection agreement is signed.  Documentation of any alternative arrangements of this type should be transmitted to ERCOT by the TSP within 10 business days of execution of such agreement.

### Provisions for Municipals and Cooperatives

While all other provisions of this interconnection process shall apply, municipal utilities or generation and transmission cooperatives developing generation projects that will interconnect to their own transmission systems are exempt from the requirement for an executed interconnection agreement.  A letter from a duly authorized official from the municipal utility or cooperative confirming the entity’s intent to construct and operate the generation project will be deemed by ERCOT to be sufficient as a public commitment by the municipal utility or cooperative and will have the same impact as an interconnection agreement for all purposes.

Municipal utility or cooperative generation projects that are proposed to interconnect with the facilities of a different TSP, other than the municipal utility or cooperative that is developing the generation project, will be required to execute an interconnection agreement as discussed in this document.

# INTERCONNECTION DATA, FEES, AND TIMETABLES

## Generation Plant Data Requirements

The GE is required to submit the most current “actual” facility information (generation, substation, and transmission/subtransmission if applicable) or best available “expected” performance data regarding the physical and electrical characteristics of its proposed facilities (in sufficient detail to provide a basis for modeling) to the point of interconnection with a TSP with its initial GINR Application.

Failure to supply the required data will result in delays in ERCOT processing the interconnection application and studies.  Recommendations resulting from these studies that are based on outdated, false, or bad data may adversely affect the safety and reliability of the ERCOT system and can result in damage to generation or transmission equipment.  Ongoing data updates and reviews are also necessary throughout the interconnection process and service life of the generating plant to ensure the adequacy, reliability, and safety of the ERCOT system is maintained over the long term as soon as such updates become available. It must be realized by current and future owners/operators of the generating plant that ERCOT protocols and NERC standards require timely data updates and submission.  Failure to comply could result in financial penalties for entities not in compliance.

In an effort to produce the best available security screening and full interconnection studies, ERCOT suggests that GEs begin collecting all appropriate engineering and equipment data from manufacturers as soon as the GE selects its major equipment for the proposed project.  While the following list is not intended to supersede the GE’s ongoing obligation to provide and update all information associated with the proposed facility as soon as the information is known, the following checklist is intended to list the minimum data and information to be provided to ERCOT at each step of the process:

### Application and Security Screening Study

- Generation entity information sheet (Appendix A)

- Generation interconnection screening study request data form (Appendix B)

### Full Interconnection Study

- Updates to above information

- Applicable information required for interconnection studies as described in the RARF instructions in all tabs applicable to the resource type within the RARF excel spreadsheet located in the Resource Asset Registration Forms zip file located at http://www.ercot.com/gridinfo/generation/index.

- Provision of the appropriate dynamic model for the facility.  Some standard dynamic model forms are available within the Resource Modification Forms zip file located at http://www.ercot.com/gridinfo/generation/index

- dynmodel_StandardGenerator011508.zip has forms for generator, exciter, governor, power system stabilizer, other models for standard generators.

- dynmodel_CombinedCycleGovernor.zip has forms for the governor models of Combined Cycle units

- dynmodel_WindTurbine011609.doc has information about existing wind turbine models at ERCOT.

- If alternative models are required to appropriately represent the proposed generating facility, that alternative model may be provided by the GE, subject to verification by the lead TSP and ERCOT.

- In order to perform stability (transient and voltage) analyses, the GE shall provide unit stability information and data to the TSP(s) and ERCOT.  See the ERCOT Dynamics Working Group Procedural Manual for more detail and GE dynamics data requirements.

Data submitted for transient stability models shall be compatible with ERCOT standard models (Siemens/PTI PSS/E and Powertech Labs Inc TSAT, VSAT and SSAT).  If there is no compatible model(s), the GE is required to work with a consultant or software vendor to develop and supply accurate/appropriate models along with other associated data.  These models shall be incorporated into the standard model libraries of both software packages.  It is recommended that generation owners and developers encourage manufacturers and software vendors to work together to develop and maintain these important models.

### Prior to Start of Construction

- Any significant design changes in the generator(s) or main power transformer(s) to ensure compatibility with the existing transmission system.

### Prior to Commercial Service

- Registration and official RARF submittal

- Updates to RARF information based on “as-built” or “as-tested” data in all cases

- Proof of meeting ERCOT requirements (reactive, low-voltage ride-through standards, stability models, PSS)

### During Continuing Operations

The GE shall provide ERCOT and the TSP with any equipment data changes which result from equipment replacement, repair, or adjustment.  Unless otherwise required in the ERCOT Protocols or Operating Guides, the GE shall provide such data to ERCOT and the TSP no later than 60 days prior to the date of the actual change in equipment characteristics or during annual data update filings whichever occurs first.  This requirement shall also apply to all future owners throughout the service life of the project/plant.

## Interconnection Study Fees

PUCT Substantive Rule §25.198 (Initiating Transmission Service) states in part that the customer requesting transmission service shall be responsible for all costs associated with the completion of the security screening and full interconnection studies.

### Security Screening Study Fee

The ERCOT security screening study fee is a non-refundable fee ranging from $1,000 to $5,000 depending on the additional installed capacity associated with each specific interconnection request.  ERCOT has determined that basing this fee on additional installed capacity is reasonable because additional installed capacity generally determines the amount of work necessary to complete the study.  The appropriate security screening study fee must be remitted for each generation interconnection request (i.e., each individual interconnection location, in-service date, and additional plant capacity at this specific interconnection location) at the time the application is submitted to ERCOT.   The check should be made payable to Electric Reliability Council of Texas, Inc.

| Total Plant Capacity, MW | Screening Study Fee |
| --- | --- |
| 10 to 74 | $1,000 |
| 75 to 149 | $2,000 |
| 150 to 249 | $3,000 |
| 250 to 499 | $4,000 |
| 500 or greater | $5,000 |

### Stability Modeling Fee

The ERCOT stability modeling fee is a non-refundable stability modeling fee of $15 per megawatt of additional installed capacity and is paid directly to ERCOT when a full interconnection study is requested.  This fee will reimburse ERCOT for the development of stability software models for each proposed generation unit and allow for continually updating current models as new equipment changes are made.  The check should be made payable to Electric Reliability Council of Texas, Inc.  Payment of the stability modeling fee to ERCOT does not release the GE from their obligation to provide ERCOT accurate and appropriate stability software models and data (including load) for each of their proposed generation plants.

### Full Interconnection Study Fee/Cost

The full interconnection study fee/cost is paid directly to the TSP(s) completing the studies associated with the FIS.  The fee/cost will be agreed on and specified in the study scope agreement. The TSP(s) will directly invoice the GE for the reasonable costs associated with undertaking and completing the FIS.

ERCOT recommends that the GE and the TSP provide for a payment methodology and cancellation provision in the full interconnection study scope agreement.  If the GE cancels the generating project during the term of the full interconnection study, the GE is required to immediately notify ERCOT and the lead TSP.  The lead TSP should immediately notify any other TSPs that may be participating in the study, via the Transmission Owner Generation Interconnection email list.  The GE is responsible for all costs associated with any work performed or non-cancelable commitments made prior to notifying ERCOT and the TSP(s) of the termination date of the project.  ERCOT highly recommends the TSP(s) receive the study fee before proceeding with work.

## Interconnection Process Timetables

PUCT Substantive Rule §25.198 (Initiating Transmission Service) provides deadlines for ERCOT and TSP(s) to complete and report on the required interconnection studies provided that the GE submits all required data and appropriate fee(s).  Therefore, it is vital that the GE ensure that ERCOT Staff and the TSP(s) performing these studies receive all required data in order to establish reasonable study models and assumptions that provide meaningful results and recommendations for interconnecting the proposed generating project.

Because the full interconnection study is generally the “critical” path item in the generation interconnection process, ERCOT recommends that a timetable for the FIS be developed and included in the study scope agreement.  In addition, major improvements to the transmission system resulting from interconnection requests should be identified as early in the process as possible so project validity can be considered before the parties go forward with extensive interconnection studies.  Once the FIS is underway, the parties may determine that an adjustment to the original estimated completion date is necessary.  Should this schedule adjustment become necessary, the parties are to provide notice to ERCOT and the TSP(s) as soon as practicable, indicating the revised expected completion date.

The following timetable complies with PUCT Substantive Rule §25.198 (Initiating Transmission Service).   It is intended to serve as a guideline only and the times stated are not requirements unless stated elsewhere in this document. If the number of days shown is less than 30, these are business days; if 30 days and over, these are calendar days.

| TASK | Responsible Entity | Time Required to Complete (Days)) |
| --- | --- | --- |
| Acknowledgement of Generation Interconnection Request Application | ERCOT | 1 to 10 |
| Notification of Additional Information Needed to Complete Application | ERCOT | 1 to 15 |
| Perform Security Screening Study (after application deemed complete) | ERCOT | 10 to 90 |
| Decision to Pursue Full Interconnection Study (following issuance of Screening Study by ERCOT) | GE | up to 180 |
| Develop Scope Agreement for Full Interconnection Study (following GE’s notification to ERCOT of desire for Full Interconnection Study and remittance of appropriate fees) | ERCOT, TSP(s), GE | up to 60 |
| Perform Full Interconnection Study (following agreement on scope) | TSP(s) | 40 to 300 |
| Steady State and Transfer Analysis |  | 10 to 90 |
| System Protection Analysis (following Steady State Analysis) |  | 10 to 30 |
| Dynamic and Transient Stability Analysis (following System Protection Study) |  | 10 to 90 |
| Facility Study |  | 10 to 90 |
| Study Report Review and Acceptance (following issuance of Full Interconnection Study) | ERCOT, TSP(s), GE | 10 to 15 |
| Negotiate and Execute Interconnection Agreement (following acceptance of Full Interconnection Study) | TSP and GE | 180 |

## GENERAL AND TECHNICAL STANDARDS

In addition to requirements under the NERC Reliability Standards, ERCOT Protocols and Operating Guides contain provisions that apply to generation interconnections.  As of the effective date of this Procedure, such provisions include, but are not necessarily limited to:

- Protocol 1.3.1

- Protocol 12.2 and 12.3

- Protocol 6.5.7

- Protocol 6.7.6

- Protocol 6.10.3

- Operations Guide 2.2.4

- Operations Guide 3.1.4

- Operations Guide 7.2.2

- Operations Procedure Steady State Voltage Control Procedures

### Transformer Tap Position

The GE will contact the TSP providing the interconnection before the main power transformers are placed into service and will work with the TSP to select the tap position on the main power transformers, and the GE will confirm the use of this tap position with the TSP and ERCOT.  The main power transformer will be considered the step-up to transmission level voltage of the interconnection.

# APPENDIX A

GENERATION ENTITY INFORMATION SHEET

## GENERATION ENTITY INFORMATION SHEET

PLEASE PRINT CLEARLY – FORM MUST BE SIGNED AND SUBMITTED WITH REQUEST

Transmission Customer (Generating Entity):

Contact Person:

Title:

Company:

Mailing Address:

City:  		State:		ZIP:

Company Internal Mail Code(s):

Telephone Number:	(      )	Facsimile (FAX) Number:	(       )

Internet email Address:

Requested Transmission Energization Date (MM/DD/YYYY):

Generation In-Service (MM/DD/YYYY): Start  		through

____________________________________________ (generating entity) is, or will be upon commencement of service, an eligible customer.  An eligible customer is any of the following: the transmission provider (for all uses of its transmission system) and any electric utility, federal power marketing agency, exempt wholesale generator, qualifying facility, or power marketer.  An eligible customer may designate an agent to represent it in arranging for interconnection.

Accurate/appropriate information and test data about generator step-up transformers, all generator data including data for stability studies (transient, voltage, etc.) and sub-synchronous resonance data will be provided to ERCOT and interconnected TSP before the generation goes into commercial operation.  I understand that all of this data will become public and added to the ERCOT databases (including power flow base cases, stability, system protection, Capacity, Demand, and Reserve Report, etc) when an interconnection agreement is signed.  This data shall be reviewed and updated when the plant goes into commercial operation.  In addition, any updates to this information will be provided within 60 days to ERCOT and the TSP as changes or upgrades are made during the life of the plant.  This requirement also applies to all future owners of this project/plant.

The generating entity and any future owners of the plant agree to comply with these data requirements along with all applicable ERCOT and NERC requirements, including, without limitation, those contained in the ERCOT Protocols and ERCOT Operating Guides.  It is understood and agreed that such requirements are subject to change from time to time, and such changes shall automatically become applicable based upon the effective date of the approved change.

Authorized Signature:  		Date:

Name printed or typed:

By:

# APPENDIX B

## GENERATOR INTERCONNECTION REQUEST SCREENING STUDY DATA SHEET

See Excel Spreadsheet titled “Generation Interconnection Request Screening Study Forms”. Fill out the appropriate tab for your generation type. {Post and Add Link Here when approved}

# Footnotes

Unless noted otherwise, capitalized terms contained herein shall have the meaning ascribed to them in the ERCOT Protocols.

As defined in PUCT Substantive Rule  §25.211(c)(10)

ERCOT Protocols Section 1.3.1.1 (10)