| NPRR Number | 164 | NPRR Title | Resubmitting Ancillary Service Offers in SASM |
| --- | --- | --- | --- |
| Impact Analysis Date |  | January 12, 2009 |  |
| Cost/Budgetary Impact |  | Incremental cost to the Nodal program is in the $100k to $250k range. Additional Nodal program cost of $6M-$8M if required for Nodal Go-Live due to extension of Market Management System (MMS) release by four weeks. |  |
| Estimated Project Time Requirements (Unless otherwise indicated, project time requirements begin upon project initiation.) |  | Implementing the requirements of this Nodal Protocol Revision Request (NPRR) will require an additional four weeks of MMS development. |  |
| ERCOT Staffing Impacts (across all areas) |  | No ERCOT staff impacts post-Nodal Go-Live. |  |
| ERCOT Computer System Impacts |  | The ERCOT MMS system will be modified to implement this NPRR. |  |
| ERCOT Business Function Impacts |  | Existing business processes can support this NPRR. |  |
| Grid Operations & Practices Impacts |  | No impacts to grid operations and practices. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

To be implemented as a post Nodal Go-Live effort.

Evaluation of Interim Solutions (e.g., manual workarounds)

To be determined.

Feasibility of Implementation

Impact on Resource Availability: Impact to Other Projects: Nodal MMS resources are currently completing existing functionality and fixing known defects. The functionality of the Ancillary Service Offers resubmission rules at issue in NPRR164 is very complex and will require extensive testing. Incorporating this new functionality prior to Nodal Go-Live will detract resources from the current defect correction effort. Furthermore, introducing this new and complex functionality may introduce new defects that would need to be addressed; thereby exacerbating the impact to the effort to complete the existing functionality and address any defects with the existing functionality.

Comments

MMS5 is on the Nodal critical path and a delay of any duration will impact the final Nodal Go-Live date. Considering the risks that NPRR164 poses to the Nodal project, ERCOT recommends that NPRR164 be deferred until after Nodal Go-Live.