## Slide 1: MARS Taskforce
COPS Update January 12, 2010
Notes: <number>

## Slide 2
ERCOT’s AMS Project
1/12/09 Status Report
6
Execution Milestones | Baseline Date | Revised Date | Status
Technical Architecture Complete | 05/15/2009 | - | Complete
Development Complete | 07/24/2009 | - | Complete
Detailed Designs Complete | 08/11/2009 | - | Complete
pTest Complete | 08/11/2009 | - | Complete
Market Test Complete | 11/06/2009 | - | Complete
iTest Complete for Implementation 1 – 11/21 | 11/06/2009 | 11/13/2009 | Complete
Go Live – Implementation 1 | 11/14/2009 | 11/21/2009 | Complete
iTest Complete for Implementation 2 – 12/13 | 11/06/2009 | 12/09/2009 | Complete
Go Live – Implementation 2 | n/a | 12/13/2009 | Complete
Stabilization Complete | 03/19/2010 |  | 
Project Complete | 05/21/2010 |  | 
Notes: <number>

## Slide 3: Post Implementation Progress Report (01/10/10)
Number of 814_20’s successfully processed by ERCOT to change profile for an AMS “Provisioned” meter (Oncor & CenterPoint)
    ~490,000
Number of ESI ID’s settled by ERCOT using 15-minute interval data
    ~460,000
Number of transactions received by ERCOT
    >20,000,000 with ~11,000,000 loaded in ERCOT systems
<number>
Notes: <number>

## Slide 4: Next Steps for MARS Taskforce
  Meeting on Tuesday, January 12, 2010 at 1:30PM following COPS.
    Agenda:
      Project Progress Report
      Provide 814_20 & Settlement numbers successfully processed to date
      814_20 TDSP Backlog numbers
      Discuss System/Processes Performance to date
    Review New and/or Changes to:
      Extracts
      Reports
      Web Services
      Other documentation
Refresher/follow-up review of Extracts, Reports, and Web Service changes will also be scheduled and placed on the Settlement Extract Working Group meeting agenda.
Monitor system performance and LSE file activities throughout:
    System Stabilization Period Complete 03/19/2010
    Project Completion Scheduled 05/21/2010
Quickly develop a market resolution for all issues as they are identified following production implementation.
<number>
Notes: <number>

## Slide 5: Questions?
Notes: <number>