## Slide 1: MARS Taskforce
RMS Update January 13, 2010
Notes: <number>

## Slide 2
ERCOT’s AMS Project
1/12/09 Status Report
6
Execution Milestones | Baseline Date | Revised Date | Status
Technical Architecture Complete | 05/15/2009 | - | Complete
Development Complete | 07/24/2009 | - | Complete
Detailed Designs Complete | 08/11/2009 | - | Complete
pTest Complete | 08/11/2009 | - | Complete
Market Test Complete | 11/06/2009 | - | Complete
iTest Complete for Implementation 1 – 11/21 | 11/06/2009 | 11/13/2009 | Complete
Go Live – Implementation 1 | 11/14/2009 | 11/21/2009 | Complete
iTest Complete for Implementation 2 – 12/13 | 11/06/2009 | 12/09/2009 | Complete
Go Live – Implementation 2 | n/a | 12/13/2009 | Complete
Stabilization Complete | 03/19/2010 |  | 
Project Complete | 05/21/2010 |  | 
Notes: <number>

## Slide 3: Post Implementation Progress Report (01/10/10)
Number of 814_20’s successfully processed by ERCOT to change profile for an AMS “Provisioned” meter (Oncor & CenterPoint)
    ~490,000
Number of ESI ID’s settled by ERCOT using 15-minute interval data
    ~460,000
Number of transactions received by ERCOT
    >20,000,000 with ~11,000,000 loaded in ERCOT systems
<number>
Notes: <number>

## Slide 4: Post Implementation Progress Report (01/11/10)
Oncor has cleared their backlog of 814_20s to change profiles for AMS “Provisioned” meters.
CenterPoint Energy is still working to clear backlog of 814_20 transactions to change profiles for AMS “Provisioned” meters.
    CenterPoint Energy has a balance of 9,448 currently in backlog
<number>
Notes: <number>

## Slide 5: Where can you find AMS Interim Settlement info?
User Guides
  ESIID Join Diagram
  ESIID Service History & Usage Extract User Guide
  Interval Data LSE Activity Reports User Guide
  Interval Data LSE Error Code Table
  Interval Data LSE File Specification
  Market Data Transparency Quick Reference Guide
  Market Data Transparency User Guide
  MarkeTrak User Guide
  Supplemental AMS Interval Data Extract
  Supplemental IDR Required Interval Data Extract
  ***Documentation found at http://www.ercot.com/services/mdt/userguides/index
XSDs and DDLs
  Market Data Transparency XSD
    http://www.ercot.com/services/mdt/xsds/
  ESIID Extract DDL
    http://www.ercot.com/services/mdt/ddls/
<number>
Notes: <number>

## Slide 6: Read, Communicate & Spread the Word
Make sure you read all documentation and reference market notices – spread the word internally and to other MPs!
Market participants with system issues:
  File a Help Desk ticket and notify their ERCOT Account Manager. The issue will be assigned to the appropriate group at ERCOT and the market participant will receive a response from the resolution group and/or their ERCOT Account Manager.
Market participants with questions regarding data:
  Send email to their ERCOT Account Manager. The question will either be answered by the ERCOT Account Manager or sent to the appropriate group at ERCOT for response.
<number>
Notes: <number>

## Slide 7: Next Steps for MARS Taskforce
  Met on Tuesday, January 12, 2010 at 1:30PM following COPS.
Refresher/follow-up review of Extracts, Reports, and Web Service changes will also be scheduled and placed on the Settlement Extract Working Group meeting agenda.
Monitor system performance and LSE file activities throughout:
  System Stabilization Period Complete 03/19/2010
  Project Completion Scheduled 05/21/2010
Quickly develop a market resolution for all issues as they are identified following production implementation.
<number>
Notes: <number>

## Slide 8: Questions?
Notes: <number>

## Slide 9: SMART Meter Texas SMT Newsflash
<number>
The Present
Coming to a home or business near you!!!!
Notes: <number>

## Slide 10: Announcement!!!
Smart Meter Texas (SMT)
  Release 1 January 31, 2010
  Competitive Retailer Companies Orientation
    Date: Wednesday, January 20, 2010
    Time: 9:00 AM to 4:00 PM
    Where: CenterPoint Energy Tower Auditorium 1111 Louisiana, Houston, TX 77002
    No RSVP Required
  ***SAVE THIS DATE ***
<number>
Notes: <number>

## Slide 11: SMT Orientation
This Orientation is for Competitive Retailer (CR) Companies ONLY.
The CR attendees should include:
  the person responsible for defining how the SMT will be set-up for your company, the person you will assign as the SMT Administrator (that will authenticate users to the system), and the person who will train other users. The Orientation will provide information required for understanding SMT functions and training users within your own Company’s organization.
<number>
Notes: <number>

## Slide 12: SMT Orientation Agenda
This day of orientation for future Portal Administrators will provide:
  A live demo of portal functionality to be available on January 31, 2010
  Introduction to Administrator roles, rights and responsibilities and help tools
  Discussion on decisions and technical information required by Competitive Retailers prior to their first use
  Questions and Answers
<number>
Notes: <number>

## Slide 13: Questions?
<number>
Notes: <number>