|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for December 2009 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 229 active generation interconnection requests totaling over 77,000 MW. This includes almost 46,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total of $798.0 Million - Transmission Projects approved in 2009 total $405.1 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.5 Billion - Transmission Projects energized in 2009 total about $538.6 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	4

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	7

2.	Regional Planning Group Project Reviews	9

3.	Other Notable Activities	9

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Oak Grove II (09INR0006b) Coal in Robertson County for 855 MW

## The total installed wind capacity remains at 8,916 MW, of which 7,393 MW (83%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements  - none

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 229 active generation interconnection or change requests |  |  |  |  |
| As of December 31, 2009 | North | South | West | Total |
| Security Screening Study | 6 | 5 | 6 | 17 |
| SSS Completed | 9 | 11 | 18 | 38 |
| Full Interconnect Study | 24 | 23 | 87 | 134 |
| FIS Completed | 3 | 12 | 2 | 17 |
| Interconnect Agreement Completed | 6 | 10 | 7 | 25 |
| Capacity under Interconnection Agreements | 3,632 | 1,444 | 1,177 | 6,253 |
| Capacity for Grid, MW | 19,706 | 22,650 | 34,836 | 77,192 |
| Wind Capacity, MW | 4,681 | 8,808 | 32,348 | 45,837 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,554 | 16,650 |
| Gas-CT |  |  | 379 | 1,029 |
| Total Gas | 1,279 | 12,467 | 3,933 | 17,679 |
| Nuclear |  |  | 5,986 | 5,986 |
| Coal | 15 | 3,712 | 2,208 | 5,935 |
| Wind | 7,476 | 31,301 | 6,889 | 45,666 |
| Solar | 544 | 459 |  | 1,003 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 216 | 1,200 |  | 1,416 |
| Grand Total | 9,588 | 49,189 | 19,161 | 77,938 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of December 31, 2009 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change From Last Report |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Jan-10 | Nuclear | 86 |  |
| 09INR0028 | V H Braunig 6 | IA | Bexar | South | Jan-10 | Gas-CT | 185 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Jan-10 | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Jan-10 | Wind | 194 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Feb-10 | Gas-CC | 50 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Apr-10 | Biomass | 45 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | May-10 | Wind | 150 |  |
| 09INR0079b | Pearsall Expansion | IA | Frio | South | Jun-10 | Gas-CT | 100 |  |
| 09INR0045 | Sand Hill Peakers | IA | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Dec-10 | Coal | 263 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 08INR0012b | Papalote Creek Phase 2 | IA | San Patricio | South | Dec-10 | Wind | 198 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Dec-10 | Wind | 136 |  |
| 06INR0022c | Penascal Wind Farm 2 | IA | Kenedy | South | Dec-10 | Wind | 202 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Dec-11 | Wind | 100 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 200 |  |
| 09INR0026 | Sterling Energy Center | IA | Sterling | West | Jun-12 | Wind | 300 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 08INR0040 | Lenorah Project | IA | Martin | West | Sep-12 | Wind | 251 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
|  |  |  |  |  |  | Total | 18,306 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 09INR0073 | Scurry | 200 | TBD | Wind |
| 11INR0013 | Mills | 150 | TBD | Wind |  | 08INR0039 | Hamilton | 90 | TBD | Wind |
| 11INR0012 | Duval | 400 | TBD | Wind |  | 09INR0065 | Webb | 150 | TBD | Wind |
| 09INR0077 | Reagan | 500 | TBD | Wind |  | 09INR0061 | Kent | 258 | TBD | Wind |
| 09INR0058 | Howard | 250 | TBD | Wind |  | 09INR0054 | Stonewall | 148.5 | TBD | Wind |
| 09INR0051 | Borden | 249 | TBD | Wind |  | 08INR0056 | Nolan | 149 | TBD | Wind |
| 08INR0023 | Floyd | 100 | TBD | Wind |  | 08INR0022 | Floyd | 100 | TBD | Wind |
| 10INR0011 | Johnson | 275 | Jan-10 | Gas |  | 11INR0033a | Cameron | 200 | Jan-10 | Wind |
| 10INR0048 | Hardeman | 1000 | Jan-10 | Wind |  | 10INR0024 | Briscoe | 2940 | Jan-10 | Wind |
| 10INR0046 | Jim Hogg | 264 | Apr-10 | Wind |  | 10INR0045 | Webb | 734 | Apr-10 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 10INR0079 | Nolan | 60 | May-10 | Wind |
| 10INR0062a | Pecos | 49.5 | May-10 | Wind |  | 09INR0070 | Reagan | 42 | May-10 | Wind |
| 09INR0069 | Reagan | 36 | May-10 | Wind |  | 10INR0023 | Haskell | 386 | May-10 | Wind |
| 10INR0016 | Childress | 150 | May-10 | Wind |  | 09INR0035 | Concho | 750 | May-10 | Wind |
| 09INR0018 | Concho | 249 | May-10 | Wind |  | 07INR0032 | Tom Green | 249 | May-10 | Wind |
| 10INR0069 | Rusk | 13 | May-10 | Coal |  | 09INR0081 | Rusk | 18 | Jun-10 | Coal |
| 10INR0029 | Hood | 810 | Jun-10 | Gas |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |  | 10INR0070 | Hunt | 50 | Jul-10 | Gas |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0013 | Upton | 400 | Jul-10 | Wind |  | 10INR0071 | Matagorda | 88 | Sep-10 | Wind |
| 10INR0089 | Harris | 40 | Oct-10 | Other |  | 10INR0081a | Clay | 30.4 | Oct-10 | Wind |
| 09INR0074 | Motley | 70 | Oct-10 | Wind |  | 10INR0041 | Floyd | 135 | Oct-10 | Wind |
| 10INR0015 | Mitchell | 350 | Oct-10 | Wind |  | 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |
| 10INR0032 | Navarro | 775 | Dec-10 | Gas |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 10INR0042 | Mason | 170 | Dec-10 | Wind |  | 10INR0060 | Willacy | 400.5 | Dec-10 | Wind |
| 10INR0059 | Zapata | 250.7 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 09INR0076 | Jackson | 300 | Dec-10 | Wind |  | 10INR0077 | Callahan | 101 | Dec-10 | Wind |
| 10INR0056 | Borden | 249 | Dec-10 | Wind |  | 10INR0033 | Armstrong | 399 | Dec-10 | Wind |
| 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 08INR0061 | Hardeman | 200 | Dec-10 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 07INR0035 | Tom Green | 270 | Dec-10 | Wind |  | 07INR0026 | Baylor | 400 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 09INR0041 | Mitchell | 300 | Dec-10 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 08INR0014 | Webb | 183 | Mar-11 | Wind |  | 11INR0050 | Crosby | 149 | Mar-11 | Wind |
| 11INR0037 | Smith | 50 | May-11 | Bio |  | 11INR0048 | Harris | 300 | May-11 | Gas |
| 11INR0046 | Brazoria | 300 | May-11 | Gas |  | 11INR0058 | Pecos | 135 | May-11 | Solar |
| 11INR0060 | Tom Green | 90 | May-11 | Solar |  | 11INR0061 | Presidio | 90 | May-11 | Solar |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 09INR0075 | Kinney | 248 | May-11 | Wind |
| 10INR0062b | Pecos | 49.5 | May-11 | Wind |  | 10INR0009 | Castro | 300 | May-11 | Wind |
| 09INR0050 | Fannin | 1200 | Jun-11 | Gas |  | 11INR0057 | Cameron | 165 | Jun-11 | Wind |
| 11INR0054 | San Patricio | 161 | Jun-11 | Wind |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 640 | Aug-11 | Gas |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |  | 11INR0008a | Roberts | 1000 | Sep-11 | Wind |
| 10INR0081b | Clay | 19.2 | Oct-11 | Wind |  | 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |
| 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 11INR0043 | Coke | 300 | Dec-11 | Wind |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 12INR0021 | Edwards | 165 | Jan-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 11INR0049 | Wharton | 275 | May-12 | Gas |  | 09INR0031 | Ector | 275 | May-12 | Gas |
| 10INR0062c | Pecos | 201 | May-12 | Wind |  | 12INR0006 | Limestone | 875 | Jun-12 | Coal |
| 10INR0022 | Harris | 3500 | Jun-12 | Gas |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0002 | Briscoe | 750 | Jul-12 | Wind |  | 12INR0027 | Gray | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0016 | Nueces | 1200 | Nov-12 | Other |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 08INR0019b | Gray | 250 | Nov-12 | Wind |  | 08INR0019a | Gray | 250 | Nov-12 | Wind |
| 08INR0019c | Gray | 250 | Nov-12 | Wind |  | 08INR0054 | Comanche | 401 | Dec-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 12INR0018 | Gray | 600 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1100 | Dec-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 08INR0042 | Coke | 200 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0006 | Gray | 750 | Oct-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 06INR0022e | Kenedy | 200 | Dec-13 | Wind |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0005 | Matagorda | 1200 | Jul-14 | Coal |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 16INR0002 | Brazoria | 1000 | Mar-16 | Other |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Luminant Energy has submitted the Comanche Peak Area Congestion Mitigation Plan project to loop the future Parker to Everman 345 kV CREZ line into the Comanche Peak 345 kV switch station.  Luminant Energy’s estimated completion date for this project is April 2010 and the estimated cost is $3 M.  This project is in ERCOT Independent Review.

# Luminant Energy submitted a proposal to either accelerate the Waco West to Waco Atco 138 kV line rebuild that is currently scheduled to be completed by the fall of 2010 or to open the line in order to prevent congestion.  This project is in study mode.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints & Capacity Shortages– December, 2009

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
|  | Capacity Shortage | $ 5,030,182 |  |  |
|  | Voltage Stability - Valley | $ 1,474,934 |  |  |
| Graham-Long Creek 345kV | Abilene South – Putnam 69kV | $ 1,140,114 | Ballinger to Abilene South 69kV, rebuild (08TPIT0080) | High West to North flow. |
|  | RPRS | $ 596,305 |  |  |
|  | DFW Security | $ 338,471 |  |  |
| Abilene Mulberry Creek & Long Creek – Sweetwater Cogen 345kV | Anson – Radium 69kV | $ 328,924 |  | High West to North flow. |
| Graham – Long Creek – Cook Field 345kV | SAPS-Shrew | $ 323,352 | Yellow Jacket Phase Shifting Transformer addition (08TPIT0135) | High West to North flow. |
| Austrop - Daffin & Decker 138kV | Austrop – Decker 138kV | $ 288,131 |  | Outage: Hicross AEN - Garfield AEN, Hicross AEN - Pilot Knob 138kV |
|  | Voltage - DFW | $ 285,761 |  |  |
| Abilene South - Eskota Switch 138kV | Trent – Merkel 69kV | $ 273,154 |  | High wind generation |

Inter-zonal Congestion

# Other Notable Activities

Five-Year Transmission Plan Update:

The 2009 Five-Year Transmission Plan report is under review by ERCOT System Planning.  Work on the 2010 Five-Year Transmission Plan has just begun.

Voltage Ride Through Study Update:

As part of Phase II, WGRs data submission of VRT capability data continues, together with validation of data received. WGRs with no response to the second reminder email have been put in direct contact with ERCOT in order to facilitate timely data collection for Phase II. For each wind farm, an aggregation model is being developed by the consultant.  Validation of PSSe v.31 compatible models for Phase III is almost complete.

West-to-North Stability Limit study Phase II Update:

The West-North Stability Limit - Phase II simulation runs are complete. The draft report is being reviewed and finalized by ERCOT System Planning.  A presentation to the Regional Planning Group at the January meeting is being prepared.

The ERCOT TPIT update for November 2009 has been completed and was posted December 1, 2009.