## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
January 21, 2010
Notes: <number>

## Slide 2: PMO Update - Agenda
  Specific Project Update
    PR90011 AMS Meter Flag (PRR805)
      Gated to Planning last week
      Projected gate to Execution on 2/26/2010
      Go-Live date to be determined on gate to Execution
  2009 Project Spending Update
    As of 12/10/2009
  2010 Project Budgets by Program Area
  Recent Project Implementations
    December 2009
Notes: <number>

## Slide 3: 2009 Project Spending Update – Preliminary Actuals – 1/11/2010
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 1,145,000 | $ 4,139,299 | $ 4,524,223
IO | $ 4,995,000 | $ 2,511,000 | $ 2,275,758
MO | $ 520,000 | $ 722,351 | $ 722,351
RO | $ 3,390,000 | $ 4,100,864 | $ 4,100,864
SO | $ 1,350,000 | $ 998,639 | $ 923,784
Released but Not Yet Reallocated | $ 0 | $ 0 | $ 0
Subtotal | $ 11,400,000 | $ 12,472,153 | $ 12,546,980
Met Center Replacement | $ 20,000,000 | $ 19,789,767 | * $ 13,097,667
Data Center Expansion | $ 6,750,000 | $ 5,888,080 | $ 5,888,254
Grand Total | $ 38,150,000 | $ 38,150,000 | $ 31,532,701
Adjustments in project forecasts
Minor Cap funding of Oracle License Cost
MO/RO True-up w/Met Center
* Note: Unspent funds on the Met Center project will carry forward to 2010

## Slide 4: 2010 Project Spending Update – 1/20/2010
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 1,150,000 | $ 1,150,000 | $ 1,150,000
IO | $ 1,450,000 | $ 1,450,000 | $ 1,450,000
MO | $ 1,500,000 | $ 1,297,649 | $ 1,297,649
RO | $ 1,900,000 | $ 1,892,118 | $ 1,892,118
SO | $ 150,000 | $ 144,068 | $ 144,068
Minor Cap | $ 750,000 | $ 750,000 | $ 750,000
Released but Not Yet Reallocated | $ 0 | $ 5,932 | $ 0
Subtotal | $ 6,900,000 | $ 6,689,767 | $ 6,683,835
Met Center Replacement | $ 31,900,000 | $ 32,110,233 | $ 31,900,000
Data Center Hardware | $ 7,500,000 | $ 7,500,000 | $ 7,500,000
Grand Total | $ 46,300,000 | $ 46,300,000 | $ 46,083,835
Adjustments in project forecasts
Transfer between MO/RO and Met Center

## Slide 5: PMO Update - YTD 2009 Project Implementations
January 2009
  RO PR-70007_01 MarkeTrak Enhancements (SCR749)
  CO PR-80003_01 Employee Performance Management
  CO PR-80038_01 ACL Audit Exchange
  CO PR-80036_01 ERCOT / TRE Accounting Structure
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0217/20090217_FA_Meeting_Materials.pdf (p. 83)
February 2009
  CO PR-60058_01 Microsoft Project Server Upgrade
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0317/20090317_FA_Meeting_Materials.pdf (p. 44)
March 2009
  CO PR-70046_01 SEM Enhancement
  IO PR-80026_01 Enterprise Visibility
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0422/20090422_FA_Meeting_Materials.pdf (p. 69)
Notes: <number>

## Slide 6: PMO Update - YTD 2009 Project Implementations
April 2009
  None
May 2009
  CO PR-80016_01 Security Configuration Management
  RO PR-80040_01 TIBCO Siebel Integration Enhancements
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0616/20090616_FA_Meeting_Materials.pdf (p. 25)
June 2009
  IO PR-80044_01 Tape Hardware Backup Replacement
    Replacement of aging tape backup system
    Enhanced speed and capacity; power and space reduction in data center
  SO PR-90022_01 Zonal AWS Wind Gen Forecast for QSEs
    SCR754 / PRR763
    Replace ERCOT email delivery of AWS forecast to QSEs with a more secure and programmatic mechanism
Notes: <number>

## Slide 7: PMO Update - YTD 2009 Project Implementations
July 2009
  CO PR-70034_01 Vendor Contract Information Database Enhancements
    Phase 2 of an effort to allow better management and reporting of vendor contracts by ERCOT’s Legal Department
  CO PR-80042_01 Cyber-Security Project
    Upgrade and enhance ERCOT cyber-security capability
  CO PR-90023_01 Single Time Entry
    Eliminate dual entry of project time reporting into project management system and time reporting system
August 2009
  CO PR-80016_01 Cyber-Security Project
    Upgrade and enhance ERCOT cyber-security capability
  RO PR-90024_01 POLR Rule and Expedited Switch
    Expedited Switch portion of project implemented on 8/16
    Effective 10/24/09, the switch cancellation and notification window is shortened from 5 business days to 2 business days prior to Scheduled Meter Read Date
Notes: <number>

## Slide 8: PMO Update - YTD 2009 Project Implementations
September 2009
  SO PR-60084_01 Mid Term Load Forecast
    Provide accurate Mid Term Load Forecasting tool to the System Operators.
    Provide ERCOT the ability to compare more than one forecast and give the flexibility to select from more than one source.
  SO PR-90001_01 Reliability Assessment Tool
    Develop a reliability assessment tool to evaluate the reliability risk level in a quantitative way using probabilistic methods and provide the operations floor with a usable tool to advise when additional resources are needed to maintain operational reliability.
  SO PR-90020_01 OOME Reliability Tool
    Develop an OOME tool which will immediately send electronic OOME deployments to sets of units either up or down when the operator needs to quickly alter flow to specific areas.
  CO PR-80047_01 TCC1 Data Center Expansion
    Expand the current 3000 sq ft data center to the adjoining 2000 sq ft of raised floor.
    Data center is to be ready for occupancy no later than 10/01/09 to meet Nodal space requirements.
  RO PR-80031_01 Retail Application Upgrade
    Upgrade critical applications to become current with software versions, vendor support and to gain the efficiencies from the features in the newer releases of the applications.
  RO PR-50061_01 EDW EAI Transition
    Implement data replication from the PaperFree and NAESB source systems to the EIS ISM database environments.
Notes: <number>

## Slide 9: PMO Update - YTD 2009 Project Implementations
October 2009
  SO PR-90021_01 14 Minute Ramp Period
    PRR803
    Supports the PRR proposed by the IMM and advocated by the PUCT to change the ramping period for Balancing Energy Service deployment for Base Power Schedule Calculation and Balancing Energy Power Schedule from ten (10) minutes to fourteen (14) minutes. This will allow more Balancing Energy Services to be deployed and is expected to improve Dispatch efficiency.
  CO PR-80007_01 Procurement Process Flows
    Automate current manual Procurement processes through Lawson.
Notes: <number>

## Slide 10: PMO Update - YTD 2009 Project Implementations
November 2009
  None
December 2009
  CO PR-60075_01 Cyber-Security Project
    Upgrade and enhance ERCOT cyber-security capability
  CO PR-70014_01 Physical Security Project
    Upgrade and enhance ERCOT physical security capability
  CO PR-40029_01 Budgeting Tool
    Implement an automated budgeting and reporting tool
  IO PR-90003_01 Spectel Server Replacement
    Replaced hotline system that was end-of-life (vendor support ended 12/31/2009)
  IO PR-90004_01 Data Storage
    Procure storage to support production growth and the Information Lifecycle Management (ILM) project
Notes: <number>

## Slide 11: PMO Update - YTD 2009 Project Implementations
Unexpected Carryovers into 2010
  SO PR-90002_01 Large Wind Power Production Ramp Forecasting
  CO PR-80047_02 DAM Control Center
  IO PR-90009_01 Infrastructure Monitoring Enhancement (Remedy Phase 3)
  IO PR-90010_01 Monitoring and Reporting Tools
Notes: <number>