## Slide 1: Nodal Program Update
Jim Galvin

## Slide 2: Program Status
ERCOT reports the following for Market Trials 3.0:
  191 of 293 QSEs qualified for Transaction Submittal
  92.5% of Generation qualified
  48 of 80 CRRAH qualified with first mock auction (March mock) February 12th
  Real Time Markets/Outage Scheduler began February 1, with real time LMPs posting every 5 minutes
  March 1 begins 6-month analysis period for LMPs

## Slide 3: Program Status
Market Trial 4.0
  DAM and RUC begin April 1st for market trial operating day April 2
Market Trial 5.0
  Full functionality testing scheduled to begin May 17 (2-week slippage in schedule)
  ERCOT has indicated a mitigation plan is in place to pull back on time through overtime
Key takeaways for successful Market Trials
  Active participation in market execution
  Realistic RT LMPs will require consistent offers from resources
  Outage and CRR testing activity highly encouraged

## Slide 4: Program Status
ERCOT reports that all interfaces are fully functional
Partially Functional Systems
  Energy Management Systems (EMS)
  Network Model Management System (NMMS)
  Market Management System (MMS)
  Commercial Systems (COMS)
  CRR, Outage Scheduler and Web Services
Credit Management System not currently functional

## Slide 5: Integrated Nodal Timeline

## Slide 6: 2010 Market Trials Timeline
Notes: Callout for Go-Live cutover

## Slide 7: Program Status
Nodal Program Issues/Risks
  Completed Reconciliation of Protocols, Systems and MP expectations
  Integration Testing- Complete for Phase 3, 2-week slippage in other phases with mitigation plan in place (Target May 2010)
  Market Interaction and Operating Level agreements
    Establishing thresholds for Network Model Load Frequency, DAM sizing, CRR sizing and reporting
    Phase 3 complete, Phase 4/5 definitions in progress
    On-track (target April/May 2010)
  Credit Management-
    Market reviewing credit concerns
    Target Phase 5 (July 2010)

## Slide 8: Market Readiness
View upcoming training opportunities
  Complete list of Training in next 60-days http://nodal.ercot.com/training/courses/index.html
  3 courses on RT/RUC Settlement Training available at Dallas (GPL), Austin (ERCOT) and Houston (Calpine)
  Basic Training, Economics of LMP, CRR, LSE, Generation courses also scheduled
ERCOT has completed 25-outreach visits with more scheduled including Wind Panel and Retail Panel scheduled in Houston February 16,17