## Slide 1: ERCOT 1/24/10 Production Issue Overview and Lessons Learned
February 10, 2010
RMS
Karen Farley
Manager, Retail Customer Choice
Notes: <number>

## Slide 2: Outline for RMS
Upgrade History
Migration Weekend
Troubleshooting Timeline
Market Impacts
Lessons Learned
Where to find system outage notices
Where to find Help Desk contact information
Notes: <number>

## Slide 3: Upgrade History
Project 80031 Retail Application Upgrades
August release - upgrade of Inovis software for NAESB to v3.2.0
  v3.2.0 failed testing in August – was pulled from the August release
September release - upgrade of Inovis software for NAESB to v3.1.0
  v3.1.0 passed internal testing
  Migrated to production – rolled back to v3.0.2 on 9/27/09
January release – upgrade of Inovis software for NAESB to v3.1.0 patch 28
  v3.1.0 patch 28 was successfully tested in ERCOT CERT environment
    Details on slide 3
  Scheduled to migrate to Production on 1/24/10
Notes: <number>

## Slide 4: Upgrade History
CERT testing criteria – lessons learned from September rollback
  Tested within Flight 1009
  Test with individual MPs that are stand-alone entities
  Test with at least one MP from each Service Provider
  Test with a large file (for example: IDR Historical usage) to ensure there are no encryption / decryption – file size issues existing between ERCOT and MP
Testing Completed for January Release |  | 
v3.1.0 patch 28 | Connectivity Completed | NAESB PGP setting changes would be needed at ERCOT
TDSP | 6 / 6 successful | 2 / 6
Service Providers | 6 / 6 successful | 2 / 6
REPs (no Service Provider) | 7 / 7 successful | 5 / 7
Notes: <number>

## Slide 5: Migration weekend
1/24/10 Release weekend -
  After migration, transactions were flowing with MPs
  Issue - outbound files failed to be decrypted on recipient side
  Experienced intermittent transaction failures with no recognizable pattern
    ~ 273 files had at least 1 NAESB failure
    Many were processed successfully once the needed PGP changes were made
    Some of these failures were due to starting up components in different order
  Issues initially believed to impact a small number of MPs
The ERCOT planned retail release completed at approximately 1:46 PM today, Sunday, January 24, 2010.
Should you have any issues, they can be reported to the ERCOT Help Desk at 512-248-6800 or helpdesk@ercot.com; or contact your ERCOT Account Manager.
Notes: <number>

## Slide 6: Troubleshooting Timeline
1/24/10 Sunday
  Continued to work issues with 2 REPs and 1 Service Provider
  ERCOT contacted impacted parties, 1 was not available until Monday
    Requested re-import of the ERCOT PGP key
    2 completed, 1 remained for Monday
  6:30pm – appeared issues could be resolved without a rollback
1/25/10 Monday
  Larger number of exceptions identified ~ 680 files had at least 1 NAESB failure
    Many were reprocessed successfully after the keys were imported
    ~300+ were due to 1 Service Provider being down (from Sun)
    A small subset may be captured twice as they remained from the previous day and were again reprocessed
  1 REP continued to have issues with larger files, reprocessing appeared to work during lower peak times when files were not pending outbound to the MP
    Some larger files would finish, some would not and then be retried and stay in a pending state, as more files were sent out and then failed, volumes pending increased
  9 separate Help Desk tickets received on 1/25/10
Notes: <number>

## Slide 7: Troubleshooting Timeline
Continued -
1/26/10 Tuesday
  1 Service Provider from Monday believed issues on their side, able to decrypt manually, ERCOT continued to reprocess files to that Service Provider
  12:58 PM - Market Notice sent to inform the Market that ERCOT was experiencing retail transaction processing issues
  Decision made to continue to troubleshoot problems instead of rolling back to previous version
1/27/10 Wednesday
    Continued analysis with vendor – see version comparison on slide 7
Notes: <number>

## Slide 8: Troubleshooting Timeline
Version comparison
Future upgrade release will be discussed in detail at TDTWG and scheduled to be part of a scheduled flight test.
 | Version | Native C PGP | Java PGP
Pre-release | 3.0.2 | X | 
Target version for 1/24/10 release | 3.1.0 patch 28 |  | X
ERCOT rolled back to on 1/28/10 | 3.1.0 patch 18 | X | 
Future release | 3.2.0 patch 16 | X | X
Notes: <number>

## Slide 9: Troubleshooting Timeline
Continued -
1/27/10 Wednesday
  Decision made to roll back to patch 18
  ERCOT tested 3.1.0 patch 18 with impacted MPs in CERT
1/28/10 Thursday
  11:00 AM - ERCOT hosted a Conference Call with the Market to discuss the NAESB issue and the planned emergency outage.
  Continued remainder of CERT testing with impacted MPs
  At 2:00 PM, emergency outage and the patch was released to production successfully and impacted MPs were receiving and decrypting files
Notes: <number>

## Slide 10: Troubleshooting Timeline
Continued –
1/29/10 Friday
  3:00 PM – ERCOT hosted a Conference Call with the Market to discuss the NAESB issue, the Patch that was made to the upgrade, and the plan for supporting the market in identifying the MP’s affected and the transactions affected.
  ERCOT had identified the files that 997s were not received, and after the call, redropped them outbound to the market.
Date received | # of files
1/24/10 | 53
1/25/10 | 173
1/26/10 | 171
1/27/10 | 280
1/28/10 | 65
Total | 742 files
Notes: <number>

## Slide 11: Market Impacts
Delay of transactions to TDSPs and REPs
Transactions out of protocol
Emergency outage to migrate to production
TDSPs requested safety net process be followed, which results in additional manual efforts at TDSPs and REPs
  TDSP #1 – 2816 safety nets (includes both Priority and Standard MVIs)
  TDSP #2 – XXXX (may receive update from TDSP prior to RMS and will update)
MarkeTrak issues – 57 from ERCOT to individual MPs with their details
TRAN TYPE | Count |  | Breakout | 
814s | 22976 See breakout column |  | 814_03s | 2764 * 376 were priority move ins
867s | 14546 |  | 814_24/25s | 699
824s | 78774 |  | 814_21s | 9004
Total | 116296 |  | All other 814s | 2343
 |  |  | Dupes | 8166
Notes: <number>

## Slide 12: Lessons Learned
Communication
Internal breakdown of communications at ERCOT delayed the notification to the market
  Actions
    Release Management – to provide additional details to RCS if there are known issues related to the release or outage and RCS will communicate issues to the Market in the completion email notice.
    RCS - Will follow up with Commercial Operations first thing in the morning on the 1st business day following the release or outage to identify if issues are resolved. If issues persist, RCS will confirm list of MPs that are impacted and send updated market notice.
    RCS will review with TDTWG to determine if market participant production technical contact list from the testing worksheets should be included in Release and Outage notices.
Notes: <number>

## Slide 13: Lessons Learned
Communication (continued)
Help Desk tickets should be tracked to determine scope of impact more quickly
  Actions
    Production support - proactive review of tickets received during window of release and 1 business day after to identify any issues.
    Review release changes with Help Desk to have the correct priority for release related issues.
    Improve clarity in notification and ticket tracking for Level 2 support
Notes: <number>

## Slide 14: Lessons Learned
Communication (continued)
Awareness by Market of ERCOT software upgrade
  Actions
    RCS will review format of Market Notices with CCWG to determine if placement of who to contact in case of issues should be changed.
    RMS review of PPL has been budget focus vs. functionality focus
Risk Management
Review of CERT test issues
  Actions
    ERCOT will integrate flight testing schedule into future Inovis software upgrades
Notes: <number>

## Slide 15: System Outage Notices -
Notes: <number>

## Slide 16: Contact Us -
Help Desk
Notes: <number>

## Slide 17: Questions?
Notes: <number>