## Slide 1: ERCOT Planning Model Activities
February 2010
ROS

## Slide 2
February 11, 2010
Nodal Protocols Section 3.10.
3.10 Network Operations Modeling and Telemetry
(9) ERCOT shall update the Network Operations Model under this Section and coordinate it with the planning models for consistency to the extent applicable.
3.10.2 Annual Planning Model
(1) For each of the next five years, ERCOT shall develop models for annual planning purposes that contain, as much as practicable, information consistent with the Network Operations Model. The “Annual Planning Model” for each of the next five years is a model of the ERCOT power system (created, approved, posted, and updated regularly by ERCOT) as it is expected to operate during peak Load conditions for the corresponding future year.
(2) ERCOT shall perform updates to the ERCOT Annual Planning Models for each of the next five years as follows:
    (a) Annual Planning Model updates are due September 1st; and
    (b) Annual Planning Models are released October15th.
(5) ERCOT shall coordinate updates to the Annual Planning Model with the Network Operations Model to ensure consistency of data within and between the Annual Planning Model and Network Operations Model to the extent practicable.
3.11 Transmission Planning
(4) The data within and between the Annual Planning Model and the Network Operations Model shall be coordinated to ensure consistency within and between the Annual Planning Model and the Network Operations Model.
Nodal Protocol Requirements for Planning
During nodal development protocols were developed to assure consistent data between the operations, planning and CRR models. The protocols are listed below. ERCOT was required by the listed protocols to develop a way to accomplish these goals.

## Slide 3: Planning Model Go-Live
Planning Model Go-Live is the deployment of ERCOT’s NMMS application in ERCOT’s production environment, along with an SSWG approved Year Ahead Planning Model, for use by ERCOT and Market Participants for the generation of Annual Planning Models (from Presentation to ROS February 2009)
ERCOT’s current project schedule shows a go-live with the NMMS tool for Planning Model management on August 20, 2010.
February 11, 2010

## Slide 4
TSP Network Model Synchronization
Before the planning model can be generated from the same system used in real-time operations, the operations model must be corrected and validated. Most of this is being done by the NDSWG and ERCOT. The SSWG must add additional data for the Topology Processor to create a case for Transmission Planners. The TSP Network Model Synchronization activity listed in the following slide represents this activity.
  The synchronization activity was listed on a presentation to ROS on February 12, 2009 as seen on slide.
  The clean-up activity was presented to SSWG at the DSA meeting on June 11, 2009.
  This was also presented at a joint SSWG and NDSG meeting on July 21, 2009.
  Planning Model Go-Live Document SSWG review on September 22, 2009 – finalized the time line on following slide.
  Other meetings/conference calls held on October 7, 2009, December 8, 2009 and January 20, 2010
February 11, 2010

## Slide 5
February 11, 2010
Planning Model Go-Live – Time line below was finalized and by SSWG at the DSB meeting September 22, 2009.
Planning Model Go-Live Time line
  The TSP Synchronization has been extended for planning data through April 30, 2010.

## Slide 6: Flow Chart of Case Building Process
February 11, 2010
ERCOT Planning imports the base case from NMMS (Topology Processor) quarterly (and as needed)
Generation, Load, and Reactive Profiles need to be created by ERCOT and TSP for each case that will be created. These are added to Topology Processor case by Model on Demand (MOD)
Future Topology changes are added to these cases by Planning Model Change Requests – PMCR’s)
Validates these data sets using PSSE
1
2
3
3
4

## Slide 7: CRR Monthly and Annual Models
Nodal Protocols:
3.11.1 Transmission Planning
(4) The data within and between the Annual Planning Model and the Network Operations Model shall be coordinated to ensure consistency within and between the Annual Planning Model and the Network Operations Model.
The Monthly CRR models will be built using the topology processor and data acquired from the operations model.
  First CRR monthly allocation model needed in October 2010 (allocate for Dec 2010)
  First CRR monthly auction model needed in November 2010 (auction for Dec 2010)
  The Annual models will be built using a processed case from topology processor and PMCRs from Model on Demand (MOD).
  First multi-month allocation and auction held in May of 2011 (for June – Dec 2011)
  First Annual allocation and auction held in August-October 2011 (for 2012-2013)
February 11, 2010

## Slide 8: Questions?
???
February 11, 2010