|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for January 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 219 active generation interconnection requests totaling over 73,000 MW. This includes almost 45,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total of $798.0 Million - Transmission Projects approved in 2009 total $405.1 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.5 Billion - Transmission Projects energized in 2009 total about $538.6 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	4

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Other Notable Activities	16

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Comanche Peak 1&2 Upgrade (09INR0015) Nuclear in Somervell County for 86 MW

## VH Braunig (09INR0028) Gas-CT in Bexar County for 185 MW

## The total installed wind capacity remains at 8,916 MW, of which 7,958 MW (89%) is located within the Western Congestion Management Zone.  Realignment of 2010 CM Zones accounted for this increase in percentage.

## New Generation Interconnection Agreements  - none

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 219 active generation interconnection or change requests |  |  |  |  |
| As of January 31, 2010 | North | South | West | Total |
| Security Screening Study | 7 | 6 | 12 | 25 |
| SSS Completed | 7 | 8 | 12 | 27 |
| Full Interconnect Study | 23 | 22 | 86 | 131 |
| FIS Completed | 3 | 11 | 3 | 17 |
| Interconnect Agreement Completed | 6 | 8 | 5 | 19 |
| Capacity under Interconnection Agreements | 3,632 | 1,259 | 626 | 5,517 |
| Capacity for Grid, MW | 19,945 | 19,148 | 34,245 | 73,338 |
| Wind Capacity, MW | 4,681 | 8,211 | 31,980 | 44,872 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,554 | 13,575 |
| Gas-CT |  |  | 194 | 544 |
| Total Gas | 1,879 | 8,492 | 3,748 | 14,119 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal | 15 | 3,712 | 1,353 | 5,080 |
| Wind | 7,476 | 31,258 | 6,138 | 44,872 |
| Solar | 529 | 489 |  | 1,018 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 156 | 1,940 |  | 2,096 |
| Grand Total | 10,113 | 45,941 | 17,284 | 73,338 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of January 31, 2010 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR |  | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change from Last Report |
| 08INR0038 |  | M Bar Wind | PL | Andrews | West | TBD | Wind | 194 | Date |
| 11INR0014 |  | TECO Central Plant | IA | Harris | South | Feb-10 | Gas-CC | 50 |  |
| 08INR0033 |  | Lufkin | IA | Angelina | North | Apr-10 | Biomass | 45 |  |
| 09INR0082 |  | Cedro Hill Wind | IA | Webb | South | May-10 | Wind | 150 |  |
| 09INR0079b |  | Pearsall Expansion | IA | Frio | South | Jun-10 | Gas-CT | 100 |  |
| 09INR0045 |  | Sand Hill Peakers | IA | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 06INR0012b |  | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 |  |
| 05INR0015c |  | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 05INR0015b |  | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 08INR0011 |  | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 |  |
| 04INR0011b |  | Cedar Elm | IA | Shackelford | West | Dec-10 | Wind | 136 |  |
| 09INR0029 |  | CFB Power Plant Units 11&12 | IA | Calhoun | South | Dec-10 | Coal | 263 |  |
| 12INR0003 |  | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 06INR0022c |  | Penascal Wind Farm 2 | IA | Kenedy | South | Dec-10 | Wind | 202 |  |
| 08INR0065 |  | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 10INR0020 |  | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1092 |  |
| 10INR0010 |  | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 |  | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 04INR0011c |  | Cottonwood Wind | IA | Shackelford | West | Dec-11 | Wind | 100 |  |
| 06INR0026 |  | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 09INR0034 |  | Gatesville Wind Farm | PL | Coryell | North | Dec-11 | Wind | 200 | Date |
| 08INR0025 |  | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b |  | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 |  |
| 09INR0007 |  | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 |  | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 |  | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0024 |  | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1001 |  |
| 09INR0037 |  | Scurry County Wind III | PL | Scurry | West | Jun-12 | Wind | 350 | Date |
| 12INR0004 |  | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 09INR0036 |  | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 06INR0006 |  | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1792 |  |
| 15INR0002 |  | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3200 |  |
| 15INR0008 |  | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2700 |  |
| 08INR0012b |  | Papalote Creek Phase 2 | IA | San Patricio | South | Dec-10 | Wind | 198 |  |
| 09INR0026a |  | Sterling Energy Center | XX | Sterling | West | Jun-12 | Wind | 200 |  |
| 09INR0026 |  | Sterling Energy Center | XX | Sterling | West | Jun-12 | Wind | 300 |  |
| 08INR0040 |  | Lenorah Project | XX | Martin | West | Sep-12 | Wind | 251 |  |
|  |  |  |  |  |  |  | Total | 17,284 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 09INR0073 | Scurry | 200 | TBD | Wind |
| 08INR0022 | Floyd | 100 | TBD | Wind |  | 08INR0023 | Floyd | 100 | TBD | Wind |
| 08INR0039 | Hamilton | 90 | TBD | Wind |  | 08INR0056 | Nolan | 149 | TBD | Wind |
| 09INR0051 | Borden | 249 | TBD | Wind |  | 09INR0054 | Stonewall | 148.5 | TBD | Wind |
| 09INR0061 | Kent | 258 | TBD | Wind |  | 09INR0065 | Webb | 150 | TBD | Wind |
| 10INR0048 | Hardeman | 1000 | TBD | Wind |  | 10INR0045 | Webb | 734 | Apr-10 | Wind |
| 10INR0046 | Jim Hogg | 264 | Apr-10 | Wind |  | 09INR0018 | Concho | 249 | May-10 | Wind |
| 09INR0035 | Concho | 750 | May-10 | Wind |  | 07INR0032 | Tom Green | 249 | May-10 | Wind |
| 10INR0016 | Childress | 150 | May-10 | Wind |  | 10INR0023 | Haskell | 386 | May-10 | Wind |
| 09INR0069 | Reagan | 36 | May-10 | Wind |  | 09INR0070 | Reagan | 42 | May-10 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 10INR0062a | Pecos | 49.5 | May-10 | Wind |
| 10INR0079 | Nolan | 60 | May-10 | Wind |  | 10INR0069 | Rusk | 818 | May-10 | Coal |
| 10INR0029 | Hood | 810 | Jun-10 | Gas |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 09INR0081 | Rusk | 818 | Jun-10 | Coal |  | 10INR0013 | Upton | 400 | Jul-10 | Wind |
| 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0070 | Hunt | 50 | Jul-10 | Gas |
| 10INR0015 | Mitchell | 350 | Oct-10 | Wind |  | 09INR0074 | Motley | 70 | Oct-10 | Wind |
| 10INR0041 | Floyd | 135 | Oct-10 | Wind |  | 10INR0081a | Clay | 30.4 | Oct-10 | Wind |
| 10INR0089 | Harris | 40 | Oct-10 | Other |  | 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |
| 07INR0013 | Coke | 200 | Dec-10 | Wind |  | 07INR0015 | Foard | 180 | Dec-10 | Wind |
| 10INR0008 | Pecos | 500 | Dec-10 | Wind |  | 07INR0026 | Baylor | 400 | Dec-10 | Wind |
| 07INR0035 | Tom Green | 270 | Dec-10 | Wind |  | 08INR0061 | Hardeman | 200 | Dec-10 | Wind |
| 08INR0062 | Archer | 249 | Dec-10 | Wind |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 11INR0012 | Duval | 400 | Dec-10 | Wind |  | 10INR0032 | Navarro | 800 | Dec-10 | Gas |
| 10INR0033 | Armstrong | 420 | Dec-10 | Wind |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 09INR0076 | Jackson | 300 | Dec-10 | Wind |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 10INR0056 | Borden | 249 | Dec-10 | Wind |  | 10INR0060 | Willacy | 400.5 | Dec-10 | Wind |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 10INR0082 | Travis | 30 | Dec-10 | Solar |  | 09INR0041 | Mitchell | 300 | Dec-10 | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 10INR0009 | Castro | 300 | May-11 | Wind |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 11INR0037 | Smith | 55 | May-11 | Biomass |
| 10INR0062b | Pecos | 49.5 | May-11 | Wind |  | 11INR0048 | Harris | 300 | May-11 | Gas |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0033a | Cameron | 200 | May-11 | Wind |
| 11INR0033b | Cameron | 200 | May-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 09INR0050 | Fannin | 1200 | Jun-11 | Gas |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 11INR0054 | San Patricio | 161 | Jun-11 | Wind |  | 11INR0057 | Cameron | 165 | Jun-11 | Wind |
| 11INR0065 | Nueces | 240 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 749 | Aug-11 | Gas |  | 11INR0008a | Roberts | 1000 | Sep-11 | Wind |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |  | 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |
| 10INR0081b | Clay | 19.2 | Oct-11 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 06INR0022d | Kenedy | 200 | Dec-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 11INR0013 | Mills | 150 | Dec-11 | Wind |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 11INR0043 | Coke | 300 | Dec-11 | Wind |  | 10INR0071 | Matagorda | 75 | Dec-11 | Wind |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 12INR0034 | Borden | 342 | Dec-11 | Wind |
| 09INR0048 | Jack | 150 | Dec-11 | Wind |  | 09INR0075 | Kinney | 248 | Dec-11 | Wind |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 09INR0031 | Ector | 275 | May-12 | Gas |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 10INR0062c | Pecos | 201 | May-12 | Wind |
| 11INR0049 | Wharton | 275 | May-12 | Gas |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 10INR0022 | Harris | 1380 | Jun-12 | Gas |
| 12INR0002 | Briscoe | 750 | Jul-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 12INR0027 | Gray | 200 | Oct-12 | Wind |
| 08INR0019a | Gray | 250 | Nov-12 | Wind |  | 08INR0019b | Gray | 250 | Nov-12 | Wind |
| 08INR0019c | Gray | 250 | Nov-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 12INR0016 | Nueces | 1200 | Nov-12 | Other |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 08INR0054 | Comanche | 401 | Dec-12 | Wind |  | 08INR0042 | Coke | 200 | Dec-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1100 | Dec-12 | Wind |
| 12INR0018 | Gray | 600 | Dec-12 | Wind |  | 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 10INR0024 | Briscoe | 3000 | Jan-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0006 | Gray | 750 | Oct-13 | Wind |
| 06INR0022e | Kenedy | 200 | Dec-13 | Wind |  | 09INR0077 | Reagan | 500 | Dec-13 | Wind |
| 14INR0002 | Goliad | 756 | Feb-14 | Coal |  | 14INR0003 | Nolan | 850 | Jun-14 | Coal |
| 14INR0005 | Matagorda | 1200 | Jul-14 | Coal |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 16INR0002 | Brazoria | 1000 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Luminant Energy has submitted the Comanche Peak Area Congestion Mitigation Plan project to loop the future Parker to Everman 345 kV CREZ line into the Comanche Peak 345 kV switch station.  Luminant Energy’s estimated completion date for this project is April 2010 and the estimated cost is $3 M.  This project is in ERCOT Independent Review.

# Luminant Energy submitted a proposal to either accelerate the Waco West to Waco Atco 138 kV line rebuild that is currently scheduled to be completed by the fall of 2010 or to open the line in order to prevent congestion.  This project is in study mode.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints & Capacity Shortages– January, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
|  | Capacity Shortage | $ 5,755,464 |  |  |
| Garfield-Onion & Hicross 138kV | Lytton Springs Autos | $ 3,664,450 |  | Outage: Lytton Springs 345kV circuit breakers & 138kV ckt breakers |
|  | Voltage - DFW | $ 2,112,194 |  |  |
| Graham SES – Parker Switch 345kV | Graham Auto | $ 2,073,749 |  | Outage: Jacksboro Switching to Bowman Switch, Jacksboro Switching to West Denton, Willow Creek - Parker Switch, Willow Creek - Wise Tractebel (East Line) 345kV circuits 345 kV |
| Graham SES – Parker Switch 345kV | Leon Switch – Putnam 138kV | $ 2,066,180 |  | Outage: Jacksboro Switching to Bowman Switch, Jacksboro Switching to West Denton, Willow Creek - Parker Switch, Willow Creek - Wise Tractebel (East Line) 345kV circuits 345 kV |
|  | Voltage Stability - Valley | $ 1,586,198 |  |  |
| Dilley Switch – San Miguel Switch 138kV | Derby Sub – Pearsall Switch 69kV | $ 918,930 |  | Outage: Lobo 138kV Low generation |
|  | RPRS | $ 608,489 |  |  |
| Watermill Switch-Limestone | Trinidad-Richland Chambers 345kV | $ 502,968 |  | Outages: both Venus Switch - Big Brown SES 345kV circuits |
| Twin Buttes-San Angelo 345kV | Twin Buttes Auto | $ 489,427 |  | Outage: Divide - Gasconades Creek 345 kV |

Inter-zonal Congestion

# Other Notable Activities

Five-Year Transmission Plan Update:

The 2009 Five-Year Transmission Plan report is under review by the Transmission Owners.  Work on the 2010 Five-Year Transmission Plan has just begun.  The SSWG 2010 Data Set B base cases are being conditioned for starting the 2010 Five-Year Transmission Plan reliability analysis.

Voltage Ride Through Study Update:

Progress continues in collecting wind plant data for Phase II.  For each wind farm, an aggregation model is being developed by the consultant.  Validation of PSSe v.31 compatible models for Phase III is complete.  Next step is to test all models at once within an ERCOT base case.

Voltage Stability Study for 2010 Summer on-peak conditions:

In preparation for the annual NERC Summer Assessment reporting, a voltage stability study was performed on the Five Year Plan’s 2010 AC case to assess the reliability of the network.  The study found that the planning 2010 network model shows sufficient voltage stability margin to NERC B and NERC C contingencies.

CREZ Implementation Technical Conference

ERCOT System Planning hosted a Technical Conference on CREZ implementation issues on January 26, 2010 at the Taylor Operations facility.  Presentations were made on several topics related to the challenges that remain in implementing the CREZ plan.

The meeting was grouped into four general topics.  Dr. Greg Reed presented an introductory discussion of the CREZ project in the context of other large planned transmission improvements and the current status of the CREZ Reactive Study.  This presentation led into the first set of discussions, which were focused on remaining planning-level CREZ issues, including the proposed changes to the NERC TPL standards, implications of wind turbine voltage-ride-through capability, and line transposition strategies.  The second set of discussions was focused on other applications for CREZ lines, such as synchrophasor technologies.  The third set of discussions centered on System Protection issues, included protection for rare fault conditions (such as cross-country faults), protection equipment testing procedures, and advantages from line-differential protection.  The final discussion dealt with current operational issues, specifically the potential causes of recent wind turbine damage in South Texas following a system fault leading to a radial connection on a series compensated circuit.  The final presentation on possible strategies for reactive control of the CREZ system had to be left for a future meeting.

There was general agreement at the end of the meeting that several issues warranted further stakeholder discussion.  Some of these issues will be addressed at the Regional Planning Group meeting on March 12, when ABB representatives will present interim findings from their study.

Presentations from this conference are posted at:

http://www.ercot.com/calendar/2010/01/20100126-TECH