## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
February 18, 2010
Notes: <number>

## Slide 2: PMO Update - Agenda
  2010 Project Spending Update
    As of 2/15/2009
  Nodal Parking Deck
    As of 2/15/2009
  Project Implementations
    January 2010
    Forecast for 2010
Notes: <number>

## Slide 3: 2010 Project Spending Update – 2/15/2010
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 1,150,000 | $ 1,150,000 | $ 946,189
IO | $ 1,450,000 | $ 1,450,000 | $ 1,473,082
MO | $ 1,500,000 | $ 1,297,649 | $ 1,209,953
RO | $ 1,900,000 | $ 1,892,118 | $ 1,869,317
SO | $ 150,000 | $ 144,068 | $ 140,821
Minor Cap | $ 750,000 | $ 750,000 | $ 750,000
Released but Not Yet Reallocated | $ 0 | $ 5,932 | $ 0
Subtotal | $ 6,900,000 | $ 6,689,767 | $ 6,389,362
Met Center Replacement | $ 31,900,000 | $ 38,000,000 | $ 37,588,721
Data Center Hardware | $ 7,500,000 | $ 7,500,000 | $ 7,482,463
Grand Total | $ 46,300,000 | $ 52,189,767 | $ 51,460,546
Carryover of unspent 2009 funds for Met Center Disposition project – authorized by the Board

## Slide 4: Nodal Parking Deck - Approved by Board of Directors
Source Document | Title | Priority | Current Status
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010

## Slide 5: Nodal Parking Deck – Pending Approval
Source Document | Title | Suggested Priority | Current Status
NPRR169 | Clarify the Calculation and Posting of LMPs for the Load Zone and LMPs for each Hub | High | Tabled at BoD TAC approved 1/6/2010
SCR755 | ERCOT.com Website Enhancements | Medium | Pending at BoD TAC approved 1/6/2010
NPRR146 | ICCP Telemetry Information Submittals | TBD | Tabled at TAC PRS approved 2/19/2009
NPRR156 | Transparency for PSS and Full Interconnection Studies | TBD | Tabled at PRS TPTF approved 2/23/2009
NPRR207 | Hour Start Unit Deselection and Half Hour Start Unit RUC Clawback | TBD | Pending at PRS
NPRR211 | Modify RUC Capacity Short Charge to Use Final Energy Trades | TBD | Pending at PRS
SCR756 | Enhancements to the MarkeTrack Application | TBD | Tabled at RMS
SCR757 | Real-Time Wind Production by Zone | TBD | Withdrawn on 2/4/2010

## Slide 6: PMO Update - YTD 2010 Project Implementations
January 2010
  None
February 2010 (projected)
  SO PR-50029-01 Improvements to VSA/DSA Phase II
  SO PR-90002-01 Large Wind Power Production Ramp Forecasting
March 2010 (projected)
  RO PR-90024-01 POLR Rule and Expedited Switch
      POLR Rule portion
  IO PR-90009-01 Monitoring & Reporting Tools
  CO PR-60029-01 Enterprise Records Management Framework
April 2010 (projected)
  RO PR-50088-01 Data Research and Reporting
  MO PR-90006-01 Information Lifecycle Management Phase I
Notes: <number>

## Slide 7: PMO Update - YTD 2010 Project Implementations
May 2010 (projected)
  None
June 2010 (projected)
  None
July -December 2010 (projected)
  CO PR-80001-01 Met Center Disposition
  DC PR-10016-01 Network Gear
Notes: <number>