|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for February 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 219 active generation interconnection requests totaling over 73,000 MW. This includes over 45,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total of $798.0 Million - Transmission Projects approved in 2009 total $405.1 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.5 Billion - Transmission Projects energized in 2009 total about $538.6 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	4

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Other Notable Activities	16

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Sandhill Peakers (09INR0045) Gas Turbines in Travis County for 90 MW

## The total installed wind capacity remains at 8,916 MW, of which 7,958 MW (89%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements  - none

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 219 active generation interconnection or change requests |  |  |  |  |
| As of February 28, 2010 | North | South | West | Total |
| Security Screening Study | 3 | 5 | 14 | 22 |
| SSS Completed | 11 | 8 | 12 | 31 |
| Full Interconnect Study | 23 | 22 | 87 | 132 |
| FIS Completed | 3 | 11 | 2 | 16 |
| Interconnect Agreement Completed | 6 | 7 | 5 | 18 |
| Capacity under Interconnection Agreements | 3,632 | 1,165 | 626 | 5,423 |
| Capacity for Grid, MW | 19,945 | 18,979 | 34,642 | 73,566 |
| Wind Capacity, MW | 4,681 | 8,136 | 32,277 | 45,094 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,554 | 13,575 |
| Gas-CT |  |  | 150 | 450 |
| Total Gas | 1,879 | 8,442 | 3,704 | 14,025 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal | 15 | 3,712 | 1,353 | 5,080 |
| Wind | 7,524 | 31,432 | 6,138 | 45,094 |
| Solar | 629 | 489 |  | 1,118 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 156 | 1,940 |  | 2,096 |
| Grand Total | 10,261 | 46,065 | 17,240 | 73,566 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of February 28, 2010 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change from Last Report |
| 08INR0038 | M Bar Wind | PL | Andrews | West | TBD | Wind | 194 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Apr-10 | Biomass | 45 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | May-10 | Wind | 150 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Jun-10 | Gas-CC | 50 | Date |
| 09INR0079b | Pearsall Expansion | IA | Frio | South | Jun-10 | Gas-CT | 100 |  |
| 10INR0070 | Greenville Engine Plant | PL | Hunt | North | Jul-10 | Gas-CT | 50 | New |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Dec-10 | Coal | 263 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Dec-10 | Wind | 136 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 08INR0012b | Papalote Creek Phase 2 | IA | San Patricio | South | Dec-10 | Wind | 198 |  |
| 06INR0022c | Penascal Wind Farm 2 | IA | Kenedy | South | Dec-10 | Wind | 202 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-11 | Wind | 150 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Dec-11 | Wind | 100 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 | Wind | 200 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 | Wind | 350 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
|  |  |  |  |  |  | Total | 17,240 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 09INR0073 | Scurry | 200 | TBD | Wind |
| 08INR0039 | Hamilton | 90 | TBD | Wind |  | 08INR0022 | Floyd | 100 | TBD | Wind |
| 08INR0023 | Floyd | 100 | TBD | Wind |  | 09INR0051 | Borden | 249 | TBD | Wind |
| 09INR0054 | Stonewall | 149 | TBD | Wind |  | 09INR0061 | Kent | 258 | TBD | Wind |
| 09INR0065 | Webb | 150 | TBD | Wind |  | 10INR0048 | Hardeman | 1,000 | TBD | Wind |
| 10INR0045 | Webb | 734 | Apr-10 | Wind |  | 10INR0046 | Jim Hogg | 264 | Apr-10 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 09INR0018 | Concho | 249 | May-10 | Wind |
| 09INR0035 | Concho | 750 | May-10 | Wind |  | 07INR0032 | Tom Green | 249 | May-10 | Wind |
| 10INR0016 | Childress | 150 | May-10 | Wind |  | 10INR0023 | Haskell | 386 | May-10 | Wind |
| 09INR0069 | Reagan | 36 | May-10 | Wind |  | 09INR0070 | Reagan | 42 | May-10 | Wind |
| 10INR0062a | Pecos | 50 | May-10 | Wind |  | 10INR0079 | Nolan | 60 | May-10 | Wind |
| 10INR0069 | Rusk | 818 | May-10 | Coal |  | 10INR0029 | Hood | 810 | Jun-10 | Gas |
| 09INR0081 | Rusk | 818 | Jun-10 | Coal |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 10INR0013 | Upton | 400 | Jul-10 | Wind |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |
| 10INR0089 | Harris | 40 | Oct-10 | Other |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 09INR0074 | Motley | 70 | Oct-10 | Wind |  | 10INR0041 | Floyd | 135 | Oct-10 | Wind |
| 10INR0081a | Clay | 30 | Oct-10 | Wind |  | 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |
| 10INR0032 | Navarro | 800 | Dec-10 | Gas |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 10INR0082 | Travis | 30 | Dec-10 | Solar |  | 09INR0076 | Jackson | 300 | Dec-10 | Wind |
| 10INR0051 | Brazoria | 200 | Dec-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 07INR0026 | Baylor | 400 | Dec-10 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 08INR0061 | Hardeman | 200 | Dec-10 | Wind |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |  | 10INR0033 | Armstrong | 420 | Dec-10 | Wind |
| 10INR0080 | Presidio | 144 | Dec-10 | Solar |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 11INR0012 | Duval | 400 | Dec-10 | Wind |
| 10INR0060 | Willacy | 401 | Dec-10 | Wind |  | 09INR0041 | Mitchell | 300 | Dec-10 | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 11INR0037 | Smith | 55 | May-11 | Biomass |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 11INR0048 | Harris | 300 | May-11 | Gas |
| 10INR0009 | Castro | 300 | May-11 | Wind |  | 10INR0062b | Pecos | 50 | May-11 | Wind |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0033a | Cameron | 200 | May-11 | Wind |
| 11INR0033b | Cameron | 200 | May-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 11INR0054 | San Patricio | 161 | Jun-11 | Wind |  | 11INR0057 | Cameron | 165 | Jun-11 | Wind |
| 11INR0065 | Nueces | 240 | Jun-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 749 | Aug-11 | Gas |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 11INR0008a | Roberts | 1,000 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |  | 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0013 | Mills | 150 | Dec-11 | Wind |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 12INR0034 | Borden | 342 | Dec-11 | Wind |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 09INR0075 | Kinney | 248 | Dec-11 | Wind |  | 12INR0021 | Edwards | 165 | Jan-12 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 11INR0049 | Wharton | 275 | May-12 | Gas |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 10INR0062c | Pecos | 201 | May-12 | Wind |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 10INR0022 | Harris | 1,380 | Jun-12 | Gas |  | 12INR0002 | Briscoe | 750 | Jul-12 | Wind |
| 08INR0041 | Coke | 200 | Oct-12 | Wind |  | 12INR0026 | Randall | 400 | Oct-12 | Wind |
| 12INR0027 | Gray | 200 | Oct-12 | Wind |  | 12INR0035 | Nueces | 249 | Nov-12 | Wind |
| 08INR0019a | Gray | 250 | Nov-12 | Wind |  | 08INR0019b | Gray | 250 | Nov-12 | Wind |
| 08INR0019c | Gray | 250 | Nov-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 12INR0016 | Nueces | 1,200 | Nov-12 | Other |  | 08INR0054 | Comanche | 401 | Dec-12 | Wind |
| 06INR0022f | Kenedy | 200 | Dec-12 | Wind |  | 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 08INR0056 | Nolan | 149 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 12INR0018 | Gray | 600 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 10INR0024 | Briscoe | 3,000 | Jan-13 | Wind |  | 09INR0058 | Howard | 250 | Mar-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0006 | Gray | 750 | Oct-13 | Wind |  | 06INR0022e | Kenedy | 200 | Dec-13 | Wind |
| 09INR0077 | Reagan | 500 | Dec-13 | Wind |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0005 | Matagorda | 1,200 | Jul-14 | Coal |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 16INR0002 | Brazoria | 1,000 | Jun-17 | Other |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Luminant Energy has submitted the Comanche Peak Area Congestion Mitigation Plan project to loop the future Parker to Everman 345 kV CREZ line into the Comanche Peak 345 kV switch station.  Luminant Energy’s estimated completion date for this project is April 2010 and the estimated cost is $3 M.  This project is in ERCOT Independent Review.

# Luminant Energy submitted a proposal to either accelerate the Waco West to Waco Atco 138 kV line rebuild that is currently scheduled to be completed by the fall of 2010 or to open the line in order to prevent congestion.  This project is in study mode.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints & Capacity Shortages– January, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
|  | Capacity Shortage | $ 1,710,015 |  |  |
| Garfield-Onion & Hicross 138kV | Lytton Springs Autos | $ 1,065,839 | Lytton Springs Autotransformer Addition (10TPIT0058) | Outage: Lytton Springs 345kV circuit breakers & 138kV ckt breakers |
| Basecase |  | $ 922,430 |  | Outage: Center bus |
|  | Voltage - DFW | $ 769,116 |  |  |
| WA Parish - O'Brien 345kV Oasis - PH Robinson 345kV | Garrott - Midtown 138KV | $ 533,835 | Garrott - Midtown - Polk Ckt. 90 (11TPIT0072) | Outage: Garrott – Blogett 138KV |
| Abilene Mulberry Creek - Bitter Creek & Long Creek - Sweetwater Cogen 345kV | Sterling County - Sterling City 69kV | $ 486,262 | CREZ | Outage: Divide Switchyard - Twin Butte 345KV |
| Garfield - Onion & Hicross 138kV Graham - Long Creek - Cook Field Rd 345kV | Abilene South - Potosi Tap 138kV | $ 411,094 | CREZ |  |
|  | RPRS | $ 400,001 |  |  |
|  | Voltage Stability - Valley | $ 373,329 |  |  |
| Dilley Switch – San Miguel Switch 138kV | Derby Sub – Pearsall Switch 69kV | $ 324,919 | Pearsall to Dilley 69 kV (09TPIT0189) | Outage: Sonora - Cauthorn 138KV |

Inter-zonal Congestion

# Other Notable Activities

Five-Year Transmission Plan Update:

The 2009 Five-Year Transmission Plan report is undergoing final edits.  Work on the 2010 Five-Year Transmission Plan has begun.  The analysis is currently focused on identifying reliability concerns in the 2015 summer peak case and finding solutions for identified issues.

TPIT updates have begun.  This marks the end of the one month delay in TPIT to better align with SSWG case building efforts.  TPIT will resume its quarterly updates from this point forward.

Nodal Network Model Management System work has begun in earnest to prepare a Planning case for use in Annual Planning Studies and CRR Auctions in accordance with Nodal Protocols section 3.10.  The key initial goal for this activity is to produce a Planning (Bus/Branch) model consistent with the Network Operations (Breaker) model for use in CRR Monthly Auctions during Market Trials and for CRR Monthly Auctions starting in October 2010.

Voltage Ride Through Study Update:

The vendor has reported their data collection efforts for Phase II has been completed.  ERCOT is reviewing Phase II deliverables to ensure that sufficient data has been collected to model existing wind plants for Phase III of the study and for future VRT reliability tests.  Phase III has started with preparation of a dynamic flat-start base case with (Phase II) wind models using PSSe v.31.

Voltage Stability Study for 2015 Summer on-peak conditions:

In preparation for the annual NERC Long-Term Reliability Assessment reporting, a voltage stability study has begun using the SSWG 2015 year summer on-peak base case to assess the reliability of the network.  The study results will allow an assessment of the 2015 network model to meet voltage stability margin requirements for NERC B and NERC C contingencies.