## Slide 1: Nodal Program Update to Cops 03-09-2010
Jim Galvin

## Slide 2: Program Status
Qualification Market Trials 3.0:
  256 of 276 QSE’s qualified for MMS Transaction Submittal
  99.9% of Generation qualified
  61 of 76 CRRAH qualified
Market Trials 4.0
  On schedule for April 1 for operating day April 2
Market Trials 5.0
  2-week slippage in schedule, ERCOT optimistic on recovering that time, no change from last report

## Slide 3: Program Status
6-month LMP Analysis
  Began March 1
  Program Team encouraging submittals of offers, only 85% of expected offer curves are in place, resulting in high LMP’s
Mock CRR Auction for March
  38 market participants participated submitting approximately 9,700 transactions with 3,100 transactions clearing
  April Mock Auction will take place March 8, Program team encouraging more participation and continued work on qualifying CRRAH

## Slide 4: Program Status
Timeline issues (Yellow and Red flagged):
  Market Trials 5.0 still in 2-week time slippage, but confidence is high on recovering the time
  Integrated Credit Management targeted for May-June timeframe
  Phase 5 reports under Nodal Reports section and DAM/RUC 5/week also flagged as yellow based on Market Trials 5.0 slippage
No additional Risk or Issue items added to the Nodal Program Risks and Issues list

## Slide 5: Market Training
Please review the TAC Nodal Update Presentation and/or the following link for updated available training
  http://nodal.ercot.com/training/courses/index.html
Attendance at Operations Training has been high and identified as encouraging by the Program team
Outreach programs and Wind and Retail Panel discussions in Houston very successful
Credit Management material has been posted to the Training site, will provide good reference for Credit Management process in Nodal

## Slide 6: Market Readiness
View upcoming training opportunities
  Complete list of Training in next 60-days http://nodal.ercot.com/training/courses/index.html
  3 courses on RT/RUC Settlement Training available at Dallas (GPL), Austin (ERCOT) and Houston (Calpine)
  Basic Training, Economics of LMP, CRR, LSE, Generation courses also scheduled
ERCOT has completed 25-outreach visits with more scheduled including Wind Panel and Retail Panel scheduled in Houston February 16,17

## Slide 7: NATF Updates Topics
Start-up Costs for RMR units and inclusion of RMR in DAM and DARUC
Frequency of updating the Network Model
  Investigating with ERCOT appropriate frequency
NSRS, discussion going to WMS on the thought that there will be more NSRS in Nodal
Questions regarding more detail on what should be included in the COP regarding “expected operating conditions
  Questions to the IMM have prompted NATF to look at original stakeholder intentions

## Slide 8: Market Trials Call RT/LFC 3/5
CRR – April Auction open next week.
DAM testing begins in April
LMP test dates for entire market – based on Phase 5 Handbook- will be in May and July mid to late month
Some offer curves are being rejected due to wrong FIP and FOP prices…MPs need to be more diligent with prices
In RTM, they are seeing some intervals at $2250 especially in the morning peak hours. This was worse than last week.
QSE’s need to do better job of monitoring their 3POs for quality and accuracy
Some offer curves are not fully extended between LSL and HSL…therefore ERCOT must fill in

## Slide 9: Market Trials Call CRR 3/5
New Issue: Model Data Issues discovered related to “Planning Go-Live” focused on connectivity nodes and how they are mapped may cause some inaccuracies in ERCOTs model
Planning Model and CRR model are not necessarily in sync
  Information committed to be corrected on or about April 30
62 qualified, amber and red participants identified
Notes: Planning Model and CRR Model inaccuracies

## Slide 10: Market Trials Call CRR 3/5
Upcoming April CRR Auction:
  Monday March 8, Bid window opens, normal timeline
  Wednesday, March 10 NOIEs reiview contract entitlement information
  Thursday, March 11 Bid window for auction closes
  Friday, March 12
    Auction executes
    Balance of year allocations will be set
Notes: Credit lock by 5 pm, entities must have submitted credit limit at that time

## Slide 11: Other Topics
PUCT intends to open a docket on Market Open Safeguards for Nodal
  PUCT would like the Stakeholder process to continue with development and testing of Nodal operations
  Docket will allow for discussions and considerations on appropriate safeguards no details yet at this time
NPRR 206 on Credit Requirements is currently in detail design at ERCOT and being evaluated for delivery for post Go-Live

## Slide 12: Questions?