## Sheet1
PHASE 4
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1
| 2010-04-01 | 2010-04-05 | 2010-04-12 | 2010-04-19 | 2010-04-26 | 2010-05-03
Day Ahead / RUC / SASM
Objective | Connectivity / Execution | AS Co-optimization | Network Constrained Solution / Initial DRUC | DAM + DRUC RT/DA Settlements | DAM + DRUC + HRUC + SASM RT/DA Settlements | Ramping to DAM 5x / week
Network Constraints | None | None | Included | Included | Included | Included
Self AS requested | 100% | 50% | 50% | Actual | Actual | Actual
DAM | 1x / week | 2x / week | 2x / week | 2x / week | 2x / week | 2x / week
Load Bid MW Requested | 80-120% forecasted load | 80-120% forecasted load | 80-120% forecasted load | 80-120% forecasted load | 80-120% forecasted load | 80-120% forecasted load
Virtual Bids / Offers | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 10 transactions totaling 100 MW/QSE/hr | Up to 10 transactions/ QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr
PTP Obligations | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW | None | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load
NOIE CRR Offers | Allocated CRRs only | Allocated CRRs only | None | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only
DRUC | None | None | DRUC w/ Thursday DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM
HRUC | None | None | None | None | HRUC Executed Limited | HRUC Executed Limited
SASM | None | None | None | None | SASM Executed | SASM Executed
Operational Scenarios
Market Timeline | Best Effort | Best Effort | 1000/1330/1430 | 1000/1330/1430 | 1000/1330/1430/TBD/TBD | 1000/1330/1430/TBD/TBD
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday
RTM / LFC
SCED | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7
Price Curve Limitations | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs
LFC Testing | Individual Gen Tests | Individual Gen Tests | Individual Gen Tests | Re-Test per Scheduled Post 2-Hr Approach Doc | Re-Test per Scheduled | 2 hr LFC Prep Conduct 2-Hr LFC Workshop
Telemetry Issues | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime
Operational Scenarios
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday 2 hr LFC Workshop
CRR
Monthly Auction | Post May Auction Notice |  | Post CRR Ownership May Auction Bidding | Post May Auction Results |  | Post June Auction Notice
Balance of Year Auction Annual Auction |  | Post Notice |  | Balance of year Bidding | Balance of year Bidding | Balance of year Auction results posted
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol | Protocol
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday
Outage Scheduling
Data Feed | Pump / MPs permitted actual outages for April effective date and test outages beyond April | Pump / MPs permitted actual outages for April effective date and test outages beyond April | Pump / MPs permitted actual outages for April effective date and test outages beyond April | Pump / MPs permitted actual outages for April effective date and test outages beyond April | Pump / MPs permitted actual outages for April / May effective date and test outages beyond April / May | Pump / MPs permitted actual outages for May effective date and test outages beyond May
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
Settlements
DAM Settlements & Invoices | 2010-04-19: Partial BDs; 2010-04-26: Partial BDs; 2010-05-03: Partial BDs
DAM Re-Settlement & Invoices
RT Initial Settlements | 2010-04-19: Partial BDs; 2010-04-26: Partial BDs; 2010-05-03: Partial BDs
RT Final Settlements (OD + 20)
RT True-up Statements (OD+ 45)
RT Re-Settlement
CRR Auction Invoicing | 2010-04-19: May Monthly Invoices Posted; 2010-05-03: Balance of Year Invoices Posted
CARD Invoice
Balancing Account Invoice
RTM & DAM Late Fee Invoice
Miscellaneous Invoice
Settlements Protocol Timeline | 2010-04-19: Best Effort; 2010-04-26: Best Effort; 2010-05-03: Best Effort