## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
March 25, 2010
Notes: <number>

## Slide 2: PMO Update - Agenda
  2010 Project Spending Update
    As of 3/22/2009
  Nodal Parking Deck
    As of 3/24/2009
  Project Implementations
    February 2010
  2011 Project Prioritization
Notes: <number>

## Slide 3: 2010 Project Spending Update – 3/22/2010
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 1,150,000 | $ 1,150,000 | $ 1,254,380
IO | $ 1,450,000 | $ 1,450,000 | $ 1,544,263
MO | $ 1,500,000 | $ 1,297,649 | $ 1,205,641
RO | $ 1,900,000 | $ 1,892,118 | $ 1,749,693
SO | $ 150,000 | $ 144,068 | $ 148,001
Minor Cap | $ 750,000 | $ 750,000 | $ 750,000
Released but Not Yet Reallocated | $ 0 | $ 5,932 | $ 0
Subtotal | $ 6,900,000 | $ 6,689,767 | $ 6,651,978
Met Center Replacement | $ 31,900,000 | $ 38,000,000 | $ 38,004,419
Data Center Hardware | $ 7,500,000 | $ 7,500,000 | $ 7,453,820
Grand Total | $ 46,300,000 | $ 52,189,767 | $ 52,110,217

## Slide 4: Nodal Parking Deck - Approved by Board of Directors
Source Document | Title | Priority | Current Status
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010
SCR755 | ERCOT.com Website Enhancements | Medium | BoD Approved 2/16/2010

## Slide 5: Nodal Parking Deck – Pending Approval
Source Document | Title | Suggested Priority | Current Status
NPRR146 | ICCP Telemetry Information Submittals | TBD | Tabled at TAC PRS approved 2/19/2009
NPRR207 | Hour Start Unit Deselection and Half Hour Start Unit RUC Clawback | High | Tabled at TAC PRS approved 2/19/2009
NPRR211 | Modify RUC Capacity Short Charge to Use Final Energy Trades | TBD | Pending at WMS
SCR756 | Enhancements to the MarkeTrack Application | TBD | Tabled at RMS
The following items were removed from the Parking Deck in the past month:
NPRR156 – Language revisions and other clarifications eliminated system changes
NPRR169 – Recent developments in system design allowed for an acceptable delivery approach
SCR757 – Withdrawn by submitter

## Slide 6: PMO Update - YTD 2010 Project Implementations
January 2010
  None
February 2010
  CO PR-80047_02 DAM Control Center
  IO PR-90009_01 Infrastructure Monitoring Enhancement (Remedy Phase 3)
March 2010 (projected)
  RO PR-90024-01 POLR Rule and Expedited Switch
      POLR Rule portion
  SO PR-50029-01 Improvements to VSA/DSA Phase II
  SO PR-90002-01 Large Wind Power Production Ramp Forecasting
  CO PR-60029-01 Enterprise Records Management Framework
April 2010 (projected)
  RO PR-90011-01 AMS Meter Flag
  RO PR-50088-01 Data Research and Reporting
  MO PR-90006-01 Information Lifecycle Management Phase I
Notes: <number>

## Slide 7: PMO Update - YTD 2010 Project Implementations
May 2010 (projected)
  None
June 2010 (projected)
  IO PR-90010-01 Monitoring & Reporting Tools
July -December 2010 (projected)
  IO PR-80001-01 Met Center Disposition
  DC PR-10015-01 Telcom Equipment
  DC PR-10016-01 Network Gear
Notes: <number>

## Slide 8: 2011 Project Prioritization Schedule
<number>
April 2009
  CARTs develop draft 2011 project lists
    Request and incorporate input from the market
    5 year project forecast referenced and updated
May 2009
  Initial review at market subcommittee meetings
    MO - COPS (May 11)
    RO - RMS (May 12)
    SO - ROS, WMS (May 13 / May 19)
June 2009
  Approval/endorsement by market subcommittees
    MO - COPS (June 8)
    RO - RMS (June 9)
    SO - ROS, WMS (June 10 / June 16)
    CO, IO, MO, RO, SO – PRS (June 17)
July 2009
  Approval/endorsement by TAC (July 1)
  Available for F&A and Board review (July 20)
Notes: <number>

## Slide 9: 2011 Project Prioritization – Additional Considerations
<number>
Nodal Systems
  MO, SO
    Stabilization will be the focus for much of 2011
    Code freeze will likely extend into Q2 2011
    First major release planned for 2012
    2011 funding will be estimated for:
      Stabilization
      Planning for 2012 major release
Other CARTs
  CO, IO, RO
    Environment freeze will be lifted when reasonable
    2011 funding to be requested in the usual manner:
      Build list of proposed projects
      Complete Project Charters, CBAs, and Time & Cost Estimates
      Estimate cutline based on resource and environment limitations