SSWG REPORT TO ROS

April 2010

- SSWG has met twice since the March ROS meeting, conference calls on March 17 and March 31.

- SSWG is currently attempting to correct data needed to output an accurate system topology through the topology processor (TP) by April 30, 2010 in time for CRR Market Trials.

  - As of Feb 26, TP bus numbers needing corrections: 1063

  - As of Apr 5, TP bus numbers needing corrections: 540

- SSWG members will have to submit NOMCRs to place Connectivity Nodes (CNs) into the correct Connectivity Node Groups (CNGs), the vast majority of the work required to meet the April 30 date. ERCOT will host a training class for SSWG members on Tuesday, April 6, 9:30-11:30, to review how to correct PSSE IDs, CNs, and CNGs.

- Second set of spreadsheet changes are due to ERCOT on April 9.

- ERCOT/SSWG/Siemens are currently working on changes to the topology processor.  Topology processor update expected in May.

- SSWG has submitted a NPRR to address the current Nodal Protocol language requiring Annual Planning Models to use dynamic ratings.

- Calendar with all SSWG activities included (Nodal Planning Model related):

  - April 9		2nd pass of CNG and ID changes due to ESP

  - April 9		TPIT Pass 2 idvs due to ESP

  - April 14	SSWG conference call

  - April 16	Raw files, NOIE, and self-serve dispatch due to ESP

  - April 16	Final TPIT cases posted on the web

  - April 22	SSWG meeting - Taylor

  - April 23	ERCOT sends Pass 1 cases to SSWG

  - April 28	SSWG conference call

  - April 30	Pass 1 changes due to ESP

  - April 30	Complete CNG and CN updates for CRR market trials

  - May 7		ERCOT sends Pass 2 cases to SSWG (gen dispatch included)

  - May 12	SSWG conference call

  - May 14	Pass 2 changes due to ESP

  - May 21	ERCOT sends Pass 3 cases to SSWG

  - May 26	SSWG meeting - Taylor

  - May 28	Pass 3 changes due to ESP

  - June 15 –17	SSWG meeting to finalize cases

Wes Woitt

2010 SSWG Chair