|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for March 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 220 active generation interconnection requests totaling over 73,000 MW. This includes almost 45,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total of $798.0 Million - Transmission Projects approved in 2010 total $0 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.6 Billion - Transmission Projects energized in 2009 total about $762 million - Transmission Projects energized in 2010 total about $41.3 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	4

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Other Notable Activities	16

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Penascal Wind (06INR0022) in Kenedy County for 201 MW

## The total installed wind capacity is now  9,117 MW, of which 7,958 MW (87%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements  - none

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 220 active generation interconnection or change requests |  |  |  |  |
| As of March 31, 2010 | North | South | West | Total |
| Security Screening Study | 3 | 7 | 13 | 23 |
| SSS Completed | 10 | 8 | 14 | 32 |
| Full Interconnect Study | 22 | 22 | 85 | 129 |
| FIS Completed | 5 | 12 | 2 | 19 |
| Interconnect Agreement Completed | 6 | 6 | 5 | 17 |
| Capacity under Interconnection Agreements | 3,632 | 863 | 626 | 5,121 |
| Capacity for Grid, MW | 20,145 | 19,022 | 34,139 | 73,306 |
| Wind Capacity, MW | 4,881 | 8,219 | 31,734 | 44,834 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,554 | 13,575 |
| Gas-CT |  |  | 50 | 350 |
| Total Gas | 1,879 | 8,442 | 3,604 | 13,925 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal | 15 | 3,712 | 1,353 | 5,080 |
| Wind | 6,915 | 31,983 | 5,936 | 44,834 |
| Solar | 489 | 489 |  | 978 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 389 | 1,947 |  | 2,336 |
| Grand Total | 9,745 | 46,623 | 16,938 | 73,306 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of March 31, 2010 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change from Last Report |
| 08INR0038 | M Bar Wind | PL | Andrews | West | TBD | Wind | 194 |  |
| 10INR0070 | Greenville Engine Plant | PL | Hunt | North | Jul-10 | Gas-CT | 50 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Jul-10 | Gas-CC | 50 | Date |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | Sep-10 | Wind | 150 | Date |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Dec-10 | Biomass | 45 | Date |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 08INR0012b | Papalote Creek Phase 2 | IA | San Patricio | South | Dec-10 | Wind | 198 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 | Coal | 263 | Date |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-11 | Wind | 150 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 | Wind | 200 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 | Wind | 350 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 | Wind | 120 | Date |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-14 | Wind | 100 | Date |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Jun-14 | Wind | 136 | Date |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
|  |  |  |  |  |  | TOTAL | 16,938 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 09INR0073 | Scurry | 200 | TBD | Wind |
| 09INR0065 | Webb | 150 | TBD | Wind |  | 09INR0061 | Kent | 258 | TBD | Wind |
| 09INR0054 | Stonewall | 148.5 | TBD | Wind |  | 09INR0051 | Borden | 249 | TBD | Wind |
| 08INR0039 | Hamilton | 90 | TBD | Wind |  | 08INR0022 | Floyd | 100 | TBD | Wind |
| 08INR0023 | Floyd | 100 | TBD | Wind |  | 10INR0048 | Hardeman | 1000 | TBD | Wind |
| 10INR0046 | Jim Hogg | 264 | TBD | Wind |  | 10INR0045 | Webb | 734 | TBD | Wind |
| 10INR0079 | Nolan | 60 | May-10 | Wind |  | 10INR0062a | Pecos | 49.5 | May-10 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 09INR0070 | Reagan | 42 | May-10 | Wind |
| 09INR0069 | Reagan | 36 | May-10 | Wind |  | 10INR0023 | Haskell | 386 | May-10 | Wind |
| 10INR0016 | Childress | 150 | May-10 | Wind |  | 09INR0035 | Concho | 750 | May-10 | Wind |
| 09INR0018 | Concho | 249 | May-10 | Wind |  | 10INR0069 | Rusk | 818 | May-10 | Coal |
| 09INR0081 | Rusk | 818 | Jun-10 | Coal |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 10INR0029 | Hood | 810 | Jun-10 | Gas |  | 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0013 | Upton | 400 | Jul-10 | Wind |  | 10INR0089 | Harris | 40 | Oct-10 | Other |
| 10INR0081a | Clay | 30.4 | Oct-10 | Wind |  | 09INR0074 | Motley | 70 | Oct-10 | Wind |
| 10INR0041 | Floyd | 135 | Oct-10 | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |  | 10INR0032 | Navarro | 800 | Dec-10 | Gas |
| 10INR0082 | Travis | 30 | Dec-10 | Solar |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 10INR0060 | Willacy | 400.5 | Dec-10 | Wind |
| 10INR0056 | Borden | 249 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 09INR0076 | Jackson | 300 | Dec-10 | Wind |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 10INR0033 | Armstrong | 420 | Dec-10 | Wind |  | 11INR0012 | Duval | 400 | Dec-10 | Wind |
| 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 08INR0061 | Hardeman | 200 | Dec-10 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 07INR0035 | Tom Green | 270 | Dec-10 | Wind |  | 07INR0015 | Foard | 180 | Dec-10 | Wind |
| 07INR0013 | Coke | 200 | Dec-10 | Wind |  | 09INR0041 | Mitchell | 300 | Dec-10 | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 11INR0071 | Harris | 20 | Apr-11 | Gas |
| 11INR0037 | Smith | 55 | May-11 | Biomass |  | 11INR0048 | Harris | 300 | May-11 | Gas |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0062 | Nueces | 149 | May-11 | Wind |
| 10INR0062b | Pecos | 49.5 | May-11 | Wind |  | 10INR0009 | Castro | 300 | May-11 | Wind |
| 11INR0033a | Cameron | 200 | May-11 | Wind |  | 11INR0033b | Cameron | 200 | May-11 | Wind |
| 09INR0050 | Fannin | 1200 | Jun-11 | Gas |  | 11INR0065 | Nueces | 240 | Jun-11 | Wind |
| 11INR0057 | Cameron | 165 | Jun-11 | Wind |  | 11INR0054 | San Patricio | 161 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0006 | Lamar | 579 | Jul-11 | Gas |  | 11INR0040 | freestone | 749 | Aug-11 | Gas |
| 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 11INR0008a | Roberts | 1000 | Sep-11 | Wind |  | 10INR0081b | Clay | 19.2 | Oct-11 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 12INR0034 | Borden | 342 | Dec-11 | Wind |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0013 | Mills | 150 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 09INR0075 | Kinney | 248 | Dec-11 | Wind |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 12INR0021 | Edwards | 165 | Jan-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 11INR0049 | Wharton | 275 | May-12 | Gas |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 09INR0031 | Ector | 275 | May-12 | Gas |
| 10INR0062c | Pecos | 201 | May-12 | Wind |  | 12INR0006 | Limestone | 875 | Jun-12 | Coal |
| 10INR0022 | Harris | 1380 | Jun-12 | Gas |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0002 | Briscoe | 750 | Jul-12 | Wind |  | 12INR0027 | Gray | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0016 | Nueces | 1200 | Nov-12 | Other |  | 12INR0035 | Nueces | 249 | Nov-12 | Wind |
| 08INR0044 | Concho | 200 | Nov-12 | Wind |  | 08INR0019c | Gray | 250 | Nov-12 | Wind |
| 08INR0019a | Gray | 250 | Nov-12 | Wind |  | 08INR0019b | Gray | 250 | Nov-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 12INR0018 | Gray | 600 | Dec-12 | Wind |
| 12INR0005 | Floyd | 1100 | Dec-12 | Wind |  | 08INR0056 | Nolan | 149 | Dec-12 | Wind |
| 08INR0054 | Comanche | 401 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 10INR0024 | Briscoe | 3000 | Jan-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0006 | Gray | 750 | Oct-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 09INR0077 | Reagan | 500 | Dec-13 | Wind |  | 06INR0022e | Kenedy | 200 | Dec-13 | Wind |
| 13INR0010 | Parmer | 1200 | Dec-13 | Wind |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0005 | Matagorda | 1200 | Jul-14 | Coal |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 16INR0002 | Brazoria | 1000 | Jun-17 | Other |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Luminant Energy has submitted the Comanche Peak Area Congestion Mitigation Plan project to loop the future Parker to Everman 345 kV CREZ line into the Comanche Peak 345 kV switch station.  Luminant Energy’s estimated completion date for this project is April 2010 and the estimated cost is $3 M.  The review of this project is complete and an ERCOT recommendation letter is being prepared.

# Luminant Energy submitted a proposal to either accelerate the Waco West to Waco Atco 138 kV line rebuild that is currently scheduled to be completed by the fall of 2010 or to open the line in order to prevent congestion.  This project has exited the RPG review process with the understanding that Oncor will proceed with construction as rapidly as possible.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints & Capacity Shortages– March, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton & Lewisville Switch 345kV | West Denton - Teasley 138kV | $ 1,440,860 | West Dention re-route (07TPIT0132) | Outage on Jacksboro Switching to Willow Creek 345KV |
| Twin Butte - San Angelo Red Creek 345kV | Twin Butte 345/138kV Autotransformer | $ 1,112,663 |  | Outage on Twin Butte - San Angelo Red Creek 345kV |
|  | Voltage - DFW | $ 933,260 |  |  |
| Planned Outage | Horse Hollow 345kV | $ 896,245 |  |  |
| Sandow Switch - Austrop 345kV | Taylor West - Taylor 138kV | $ 876,865 | Salado Sw-Cedar Valley Sw (09TPIT0051) | Outage on Salado - Bell County Switching Station 138 KV |
| Roanoke Switch T1 345/138kV Autotransformer Morgan Creek Bittercreek - Sweetwater Cogen 345kV | West Denton - Airport TMPP 138kV | $ 319,036 | West Dention re-route (07TPIT0132) | Outage on Jacksboro Switching to Willow Creek 345KV |
| Sandow Switch - Austrop 345kV | Hutto - Taylor West 138kV | $ 291,677 | Salado Sw-Cedar Valley Sw (09TPIT0051) | Outage on Salado - Bell County Switching Station 138 KV |
| Abilene Mulberry Creek - Bitter Creek & Long Creek - Sweetwater Cogen 345kV | Anson - Radium 69kV | $ 241,094 |  | Outage on Divide Switchyard - Twin Butte 345kV |
| Pawnee - Lon Hill 345kV | Sinton - Skidmore 69kV | $ 153,207 |  |  |
|  | Voltage Stability - Valley | $ 113,793 |  |  |

Inter-zonal Congestion

# Other Notable Activities

Work on the 2010 Five-Year Transmission Plan is underway.  The analysis is currently focused on identifying reliability projects needed for 2015.

TPIT worksheet updates for April have been completed and posted on March 31, 2010 at  http://planning.ercot.com/reports/tpit/.  This marks the end of the one month delay in TPIT to better align with SSWG case building efforts.  TPIT will resume its quarterly updates from this point forward.  TPIT updates to the base cases are underway and should be completed by April 16, 2010.

Nodal Network Model Management System Topology Processor work continues with bi-weekly meetings/calls with SSWG and weekly ERCOT topology processor output.  The most recent topology processor output was the first utilizing the NMMS 8.1 database which allows three winding transformers and facility ratings to be included.  ERCOT created and submitted over 60 NOMCRs for SSWG members in response to SSWG changes submitted on an ERCOT created spreadsheet.  NOMCR training for planning data is being planned for SSWG members so that they can enter more complicated NOMCRs.

Voltage Ride Through Study Update:

The Phase II effort to develop models for each wind plant is essentially complete.  These models have been successfully integrated into the VRT base cases for flat start and dynamic simulation.  ERCOT is reviewing the Phase II deliverables and documentation to ensure that the modeling efforts developed by the vendor can be used by ERCOT into the future.  Phase III is underway with completion of dynamic flat start base cases and preliminary contingency simulations with (Phase II) wind models using PSSe v.31.  The vendor has recommended the use of dynamic motor load models for Phase III simulations.  ERCOT has attempted to apply models received from the CREZ reactive study to the VRT study cases, but will likely require additional support from the transmission owners.

Voltage Stability Study for 2015 Summer on-peak conditions:

In preparation for the annual NERC Long-Term Reliability Assessment reporting, a steady-state voltage stability study was performed using the SSWG 2015 year summer on-peak base case to assess the reliability of the network.  The study result shows sufficient voltage stability margin for NERC category B and NERC category C contingencies.