## Slide 1: ROS Update regarding TSP Nodal Engagement
http://nodal.ercot.com <number>
ERCOT
April 12, 2010

## Slide 2: Agenda
Introduction of new TSP Bi-Weekly Call (next call April 21)
Validation and maintenance of the Network Operations Model
Planning Model activities
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 3: Introduction and Objectives
Past few months have revealed a gap in expectations and communications between TSPs and ERCOT nodal program
  ROS/NDSWG/SSWG/NATF/NodalTrialCalls/TAC/Board
This TSP dedicated call is being started on bi-weekly basis to better communicate and track significant activities/issues/risks specifically related to nodal program activities
Attempting to aggregate key nodal information together for TSPs
Initial calls may yield lessons-learned for what forums should focus on which issues, and this call does not replace other forums, but allow a central sharing of information
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 4: Market Trials 2010 Roadmap
http://nodal.ercot.com <number>

## Slide 5: Nodal Model Effort Activity
ERCOT TAC Meeting - ROS Report
03/04/2010 Ken Donohoo
<number>
Operations
Model
(NMMS)
CRR
Model
Topology
Processor
(Software)
Long Term
Planning
Model
NDSWG
Support
Significant
Effort
Good Shape
Improving
SSWG
Support
Significant
Complex
Work
To
Complete
SSWG
Support
Additional
Capability
Needed To Meet
Planning
Needs
Development
Delayed
Under Development
Outputs
12/15/2009
02/24/2010
Updates
Continuing
Full
Functionality
Needed

## Slide 6: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 7: Nodal Model Effort Activity
ERCOT TAC Meeting - ROS Report
03/04/2010 Ken Donohoo
<number>
Operations
Model
(NMMS)
CRR
Model
Topology
Processor
(Software)
Long Term
Planning
Model
NDSWG
Support
SSWG
Support
SSWG
Support
SSWG
& ERCOT
Development

## Slide 8: Update on SEM post Go-Live Activities for Network Operations Model
Feb 2010
April 2010
March 2010
ERCOT applying high volumes of TSP NOMCRs (supporting TSP validation)
ERCOT completing RE/ RARFs in model
ERCOT releasing GenMap/EPS Meter packages to RE’s
ERCOT testing bi-weekly model loads to nodal EMS/MMS
ERCOT anticipates TSP validation being ~90% complete
RARF should be ~90% complete (Load Resources by 3/15 Model Load)
ERCOT staffed to support high volumes of NOMCRs
ERCOT anticipates transitioning to maintenance mode for TSP and RARF changes
ERCOT releasing RE confirmations of model (RARF as reflected in model since RE’s cannot access)
ERCOT formally loading bi-weekly model loads to nodal EMS/MMS on schedule
Mar1-TSP metric MP14C becomes Amber for TSPs that have not confirmed validation processing complete
Apr1- TSP metric becomes Red for TSPs that have not confirmed validation processing complete
Market Trials- Nodal Real-Time Market, State Estimator, CRR Auctions
Market Trials- Day-Ahead Market
Closed-Loop LFC Tests
NDWSG/ROS updates related to Network Operations Model Validation
SEM Go-Live 8/31/09 and assessing status of Post SEM Go-Live
High-Level view of Validation Progression and related metric
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 9: Status of Network Operations Model Validation
Current status of completion (measured by MP-14C TSP Model Validation) is:
  17 of 22 TSPs have submitted confirmation that validation is complete
  Represents 99% of the modeled system equipment
Conclusion
  Nearing completion of process
  Conducting TSP workshops for Model Validation re-fresher/tutorials
  Last one planned- Friday April 9, 1:30-3pm
    http://www.ercot.com/calendar/2010/04/20100409-MTTSP
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 10: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 11: Nodal Model Effort Activity
ERCOT TAC Meeting - ROS Report
03/04/2010 Ken Donohoo
<number>
Operations
Model
(NMMS)
CRR
Model
Topology
Processor
(Software)
Long Term
Planning
Model
NDSWG
Support
SSWG
Support
SSWG
Support
SSWG
& ERCOT
Development

## Slide 12: Status of Model for CRR Auction
http://nodal.ercot.com <number>
SSWG began analyzing output from Network Operations Model via the Topology Processor in December 2009 to validate data
Recognition at SSWG of gaps in data needed to support Topology Processor logic
SSWG/ERCOT quantifying effort needed to close gaps in Network Operations Model for proper provisioning of the model via Topology Processor to the CRR Monthly Auctions
  Change data (TSP submit data updates)
  Change software (ERCOT changes Topology Processor)
NMMS Network
Operations
Model
CRR
Model
NMMS
Topology Processor
Software Creates and
Exports Model
Process Flow for creating CRR Model
Notes: <number>
<number>

## Slide 13: Status of Model for CRR Auction
http://nodal.ercot.com <number>
Market Trial High-Level Key Dates:
  June CRR Auction (conduct in May)
    March 17 TSP/SSWG Phase 1 work- assignment of Connectivity Node Groups and PSSE Generator IDs
  July CRR Auction (conduct in June)
    April 30 TSP/SSWG data changes received improve CRR Model for Connectivity Node to Connectivity Node Group assignment
  August CRR Auction (conducted in July)
    May 21 TSP/SSWG remaining data changes for CRR Model
    May 28 ERCOT Topology Processor enhancements delivered
    Note this is the last trial auction prior to 168-hour test
Notes: <number>
<number>

## Slide 14: SSWG Schedule
  April 9 2nd pass of CNG and ID changes due to ESP
  April 9 TPIT Pass 2 idvs due to ESP
  April 14 SSWG conference call
  April 16 Raw files, NOIE, and self-serve dispatch due to ESP
  April 16 Final TPIT cases posted on the web
  April 22 SSWG meeting - Taylor
  April 23 ERCOT sends Pass 1 cases to SSWG
  April 28 SSWG conference call
  April 30 Pass 1 changes due to ESP
  April 30 Complete CNG and CN updates for CRR market trials
  May 7 ERCOT sends Pass 2 cases to SSWG (gen dispatch included)
  May 12 SSWG conference call
  May 14 Pass 2 changes due to ESP
  May 21 ERCOT sends Pass 3 cases to SSWG
  May 26 SSWG meeting - Taylor
  May 28 Pass 3 changes due to ESP
  June 15 –17 SSWG meeting to finalize 11DSA cases

## Slide 15: SSWG Planning Model Activities
CRR Related Issues-
Correcting Connectivity Node Groups
  Feb 26 TP output: 1063 CNGs needing correction
  Apr 5 TP output: 540 CNGs needing correction
  Of the 540 CNGs, approx 150 are generator related, meaning TSPs will have to work with ERCOT to change
Get Connectivity Nodes into the correct CNGs (i.e. Fix Topology)
Topology Processor changes
Identifying important modeling issues

## Slide 16: SSWG Modeling Issues
Model On Demand related issues:
Transformer modeling: 2 winding vs 3 winding
No ratings on zero impedance line segments
Ownership
Loads and cap banks being collapsed to the correct CNGs
Cap banks connected to distribution voltage
FACTS devices

## Slide 17: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 18: Nodal Model Effort Activity
ERCOT TAC Meeting - ROS Report
03/04/2010 Ken Donohoo
<number>
Operations
Model
(NMMS)
CRR
Model
Topology
Processor
(Software)
Long Term
Planning
Model
NDSWG
Support
SSWG
Support
SSWG
Support
SSWG
& ERCOT
Development

## Slide 19: Planning Go-Live Summary
http://nodal.ercot.com <number>
Justification of Planning Model Go-Live in 2010
  ERCOT understanding that Nodal Planning Model functionality is needed to comply with Nodal Protocols effective Dec 1, 2010
  ERCOT understanding that annual planning models will be created using new toolset (ie MOD) based on the Network Operations Model after Dec 1, 2010
    Impacts Data sets published in 2011 (for 2012/2015)
    Impacts Annual CRR Auction conducted in 2011 (for 2012/2013)
Potential ERCOT flexibility in 2010 implementation dates
  ERCOT will work with TSPs (SSWG) and QSE/CRR (NATF) to consider refinement of Planning Model Go-Live sequence to extend from August 2010 go-live to being no later than Dec 1, 2010
  ERCOT needs to work with TSPs on details of timing
Notes: <number>
<number>

## Slide 20: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 21: TSP Outage Scheduler
http://nodal.ercot.com <number>
Qualification activities in-flight
Weekly Market Call every Friday 9-10am
  http://www.ercot.com/committees/nodal/mt/index
Handbook for Outage Scheduler Activities
  http://nodal.ercot.com/readiness/markettrials/os/index.html
OS Qualification Status
  17/25 TSPs
  96% complete Equipment Share
Notes: <number>
<number>

## Slide 22: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 23: TSPs being contacted to resolve telemetry issues
http://nodal.ercot.com <number>
Telemetry Compliance with Nodal Protocols 3.10.7.5
Providing Updates to NDSWG
ERCOT sending out missing point data
TSPs have been working with ERCOT to comment on missing points (approx 1,500)
Feedback on status of points for missing/provided telemetry
Bucketed into assignments and resolving with different ERCTOT teams
Primary effort is engaging ownership and modeling issues
Goal is to get to a maintenance mode with TSP telemetry by May 1

## Slide 24: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 25: Working Towards Go-Live
http://nodal.ercot.com <number>
Update on Frequency Model Load
  Network Operations Model currently being consumed every 2 weeks by Nodal EMS/MMS and other downstream systems
  Closely aligned with Zonal Model load
  ERCOT working with stakeholder on potentially increasing nodal model load frequency to weekly frequency
NPRRs/OGRRs in discussion
  NOGRR034- Telemetry Performance (ROS/NDSWG and NATF feedback)
  NPRR146- ICCP Telemetry/NetworkModel (ROS/NDSWG)
  NPRR219- Alignment NPRR for Outages (special PRS meeting?)
Notes: <number>
<number>

## Slide 26: Working Towards Go-Live
http://nodal.ercot.com <number>
ERCOT recognition that some Nodal Protocols come into effect to align with 12/1/2010 which are weeks or months before go-live on 12/1/2010
  TSP Model Changes due by Sept 1, for Dec 1 (per protocols 3.10.1)
  Outages in parallel/dual-entry to support CRR Auction Model and Go-Live
  CRR Auction process Oct-Nov 2010
  Potential Board action on Nodal Protocols in July for market notice on August 1 for effective date on Sept1
Notes: <number>
<number>

## Slide 27: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 28: Active Market Participant Metrics (April 8, 2010)
http://nodal.ercot.com <number>
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
MP3 Market Submissions Connectivity Qualification | Green | QSERs | Generation Ratio Share | 99.0% | 1.0% | 0.0% | 0.0% | Successful submission of RT and DAM transactions | 81/84 QSERS Qualified (includes QSEs with Load Resources).
 | Amber | QSEs | Even weighting | 94.3% | 2.1% | 1.0% | 2.6% |  | 181/192 QSEs qualified. Below 95% threshold for overall GREEN.
MP6 Telemetry Compliance with Nodal Protocols 3.10.7.5 | Green | QSERs | Generation Ratio Share | 99.9% | 0.1% | 0.0% | 0.0% | Expected State Estimator telemetry submitted. | 78/79 QSERs completed. 3501/3502 SE points provided (99.6%).
 | Green | QSERs | Generation Ratio Share | 99.9% | 0.0% | 0.1% | 0.0% | Expected SCED telemetry submitted. | 78/79 QSERs completed. 7621/7629 SCED points provided (99.1%).
 | Green/White only | TSPs | Ownership Ratio Share | 0.3% | 0.0% | 0.0% | 99.7% | Expected TSP telemetry per ICCP Handbook submitted. No schedule for AMBER/RED scores | 1/17 TSPs completed, all other TSPs are in review by ERCOT. ~94% TSP CB and LD points provided.
MP11 Resource Registration | Green | REs | Registered MW Capacity Ratio Share | 97.7% | 1.82% | .5% | 0.0% | Decision Making Authority form submitted, and GENMAP validated | 153/157 Resources completed.

## Slide 29: Active Market Participant Metrics (April 8, 2010)
http://nodal.ercot.com <number>
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
MP14-C TSP Model Validation | Green | TSPs | Ownership Ratio Share | 99.4% | .6% | 0.0% | 0.0% | Network Model data validated by TSP | 17/28 TSPs have submitted model validation e-mails to ERCOT.
MP15-A Real-time Market Participation | Green | QSERs | Generation Ratio Share | 99.0% | 1.0% | 0.0% | 0.0% | Weekly average of daily SCED submissions | 75/79 QSERs above 95% weekly average for SCED submissions.
MP15-B CRR Connectivity Qualification | Red | CRRAHs | Even weighting | 91.4% | 0.0% | 8.6% | 0.0 | Successful submission CRR transactions | 64/70 CRRAHs qualified. Greater than 5% overall RED.
MP16 DAM Participation | Green/White Only | QSERs | Generation Ratio Share | 89% | 0.0% | 0.0% | 11.0% | Participation in 50% of the Day-Ahead Market runs | 57/79 QSERs with adequate participation.
 | Green/White Only | QSEs | Even Weighting | 51.6% | 0.0% | 0.0% | 48.4% |  | 93 out of 192 QSEs with adequate participation.
MP20 Outage Scheduler Connectivity Qualification | Green | QSERs | Generation Ratio Share | 98.1% | 0.0% | 0.0% | 1.9% | Successful submission of OS transactions. AMBER/RED scores light up 4/13/2010 after OS window closes | 74/78 QSERS qualified.
 | Green | TSPs | Ownership Ratio Share | 99.8% | 0% | 0% | .02% |  | 18/25 TSPs qualified.

## Slide 30: Active Market Participant Metrics (April 8, 2010)
http://nodal.ercot.com <number>
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
CRR3 Operation of CRR Auctions and Allocations | Green/White only | CRRAHs | Even weighting | 68.1% | 0% | 0% | 31.9% | Participation in at least one of the last two auctions or allocations. AMBER/RED scores light up 5/5/2010 after May bid window closes | 49/70 CRRAHs with adequate participation in March or April Auctions or Allocations.

## Slide 31: Active ERCOT Metrics (April 8, 2010)
http://nodal.ercot.com <number>
Next update – 4/7/2010
Metric Name | Current Score | Applies to | Percentage (if applicable) | Primary Criteria | Notes
E1 ERCOT Staff Completes Training | Green | ERCOT | 100% | Training plans must be adhered to for highly impacted departments | 15 out of 15 highly impacted departments are up to date with their training plans.
E9 Develop Nodal Procedures | Green | ERCOT | 100% | Procedures developed 1 month prior an to the appropriate Market Trials Phase and/or procedures exercised in the current Market Trials phase. | All MT4 and MT5 are now developed and the MT3 procedures were exercised during MT3 as scheduled. MT4 procedures on target to be exercised by the end of MT4.
MO4 Verify SCED Execution Quality | Green | ERCOT | N/A | All of the successful SCED executions passed the post-execution price validations for the given reporting period. | For the 3/23 – 4/5 period, there were 4,048 * SCED intervals with no price validation error flags.
MO5 Generate 6 Months of LMPs | Green | ERCOT | 95.9% | Greater than 95% of the SCED executions produced and posted LMPs for the given reporting period. | For the 3/23 – 4/5 period, 3,887 out of 4,052 SCED runs with LMP posted correctly.