## Slide 1: Nodal Program Update to Cops 04-13-2010
Jim Galvin

## Slide 2: Program Status
Qualification of Market Participants- 95% of MPs qualified:
  81 of 84 QSEs with resources qualified
  181 of 192 QSEs without resources qualified
Full Functionality testing to begin in May will result in push to get remaining QSEs qualified
Market Trials:
  2-CRR Auctions now completed
  Three DAM markets simulated with two additional this week
  Strong participation in DAM trials (over 150 QSEs)

## Slide 3: Program Status
6-month LMP Analysis Continues
  Began March 1
  Only a few instances when $2250 price CAP has been reached
  Submitted information and increase in expected offers are improving LMP results
Mock CRR Auction for April
  Completed and invoiced
  Participation again very encouraging

## Slide 4: Program Status
Timeline issues:
  Phase 5 testing previously flagged as a two-week lag has been mitigated and is back on schedule with no impact to Market Go-Live
  No new issues added to Market Issues list

## Slide 5: Market Trials- DAM
DAM Market Trials began April 1, three DAM run for April 1,6,8
  DAM runs were controlled with Self Arrangement of AS at 100% for April 1, going to 50% for other days
  AS co-optimization for April 6,8
  Load bid request was for 80-120% of Load
  Virtual bids/offers and PTP Obligations limited to 5 transactions totaling 50 MW
Over 150 QSEs participated in the DAM trials
  25 QSEs submitted AS offers (April 7 data)

## Slide 6: Market Trials- DAM
Ancillary Service Insufficiency:
  ERCOT received insufficient bids for Non-spin and RRS and therefore reduced the AS requirement for those services
  Prices:
    Reg Up- $50 - $58.18
    Reg Down- $4.02 - $7.44
    Responsive- $55 - $63.18
    NS- $50 - $54.32
DAM Energy
  Market prices cleared between $21 - $35
  Submittal of Energy only, TPO, PTP Obligations were robust

## Slide 7: Market Trials- DAM Week 3
Upcoming DAM Market Trials 4/13 and 4/15-
  Network constrained condition and initial DRUC
  AS obligations 50% self arranged, 80-120% Load bid conditions to remain
  Increase in virtual transactions to 10
  No allocated CRRs or PTP Obligations
  COP updates after the DAM/DRUC (4/15)
  DRUC (4/15)

## Slide 8: Market Trials DAM- Week 4 and 5
Constrained conditions will remain, as will requested 80-120% of Load
Ancillary Service self arrangement no requirement
DRUC after each DAM
HRUC and SASM
DAM Settlement
For more information on FAQs and System issues please consult the following presentation:
  http://www.ercot.com/calendar/2010/04/20100409-MT Day Ahead Market presentation

## Slide 9: Market Trials DAM- Settlement
DAM settlement statement and invoice will be generated for DAM operating day April 21, 2010 (April 20 DAM run)
Statement and invoice provided in accordance with the ERCOT protocol requirement, expected to be published on Friday, April 23 2010
COMS extracts expected within the ERCOT protocol 48-hour timeline (expected Monday, April 26 2010
ERCOT will provide RTM Statements for this operating day on May 3, 2010
Please consult Market Trials COMS Testing Handbook
  http://nodal.ercot.com/readiness/markettrials/coms/index.html

## Slide 10: Market Trials- RTM
Real Time Market and LFC Handbook available
  http://nodal.ercot.com/readiness/markettrials/rtm/index.html
April 16 primary LFC testing completes, re-testing to take place between April 19-30
ERCOT will host a workshop on upcoming LFC 2-hour test, May 3, 2010

## Slide 11: Market Training
Please review the TAC Nodal Update Presentation and/or the following link for updated available training
  http://nodal.ercot.com/training/courses/index.html

## Slide 12: Questions?