## May
Note that May will be focused on resolving issues from Phase 4 and ramping up to DAM 5x / week 2 hr LFC tests to be executed
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4
| 2010-04-01 | 2010-04-05 | 2010-04-12 | 2010-04-19 | 2010-04-26 | 2010-05-03 | 2010-05-10 | 2010-05-17 | 2010-05-24
Day Ahead / RUC / SASM
Objective | Connectivity / Execution | AS Co-optimization | Network Constrained Solution / Initial DRUC | DAM + DRUC RT/DA Settlements | DAM + DRUC + HRUC + SASM RT/DA Settlements | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Ramping to DAM 5x / week
Network Constraints | None | None | Included | Included | Included | Included | Included | Included | Included
Self AS requested | 100% | 50% | 50% | Actual | Actual | Actual | Actual | Actual | Actual
DAM | 1x / week | 2x / week | 2x / week | 2x / week | 2x / week | 2x / week | 3x / week | 3x / week | 5x / week
Load Bid MW Requested | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | Restrained based on OLA only
Virtual Bids / Offers | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 10 transactions totaling 100 MW/QSE/hr | Up to 10 transactions/ QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Restrained based on OLA only
PTP Obligations | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW | None | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Restrained based on OLA only
NOIE CRR Offers | Allocated CRRs only | Allocated CRRs only | None | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Any
DRUC | None | None | DRUC w/ Thursday DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM
HRUC | None | None | None | None | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited
WRUC | None | None | None | None | None | None | None | None | Executed on Mon and Wed
SASM | None | None | None | None | SASM Executed | SASM Executed | SASM Executed | Executed as needed | Executed as needed
COP Updates | None | None | After DAM and DRUC | After DAM and DRUC | After DAM, DRUC and HRUC | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM
Operational Scenarios
Market Timeline | Best Effort | Best Effort | 1000/1330/1430 | 1000/1330/1430 | 1000/1330/1430/TBD/TBD | 1000/1330/1430/TBD/TBD | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
RTM / LFC
SCED | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7
Price Curve Limitations | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs Deconstructed Zonal During 2 hr Test | 80-120% of costs
LFC Testing | Individual Gen Tests | Individual Gen Tests | Individual Gen Tests | Re-Test per Scheduled Post 2-Hr Approach Doc | Re-Test per Scheduled | 2 hr LFC Prep Conduct 2-Hr LFC Workshop | 2 hr LFC Prep | 2 hr LFC Test Post 8-Hr Approach Doc | Analyze 2 hr LFC findings
Telemetry Issues | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime
Operational Scenarios
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol | Protocol | Protocol | Protocol
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday 2 hr LFC Workshop | Monday / Friday | Monday / Friday | Monday / Friday
CRR
Monthly Auction | Post May Auction Notice |  | Post CRR Ownership May Auction Bidding | Post May Auction Results |  | Post June Auction Notice | Bidding | Auction results posted
Balance of Year Auction Annual Auction | 2010-04-05: Post Notice; 2010-04-26: Balance of year Bidding; 2010-05-03: Balance of year Auction results posted
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol | Protocol | Protocol | Protocol | Protocol
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
Outage Scheduling
Data Feed | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April / May effective date and test outages beyond April / May | Zonal to Nodal import process / MPs permitted actual outages for May effective date and test outages beyond May | Zonal to Nodal import process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal import process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal import process / MPs permitted actual outages for April effective date and test outages beyond May
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
Settlements
DAM Settlements & Invoices |  |  |  | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs
DAM Re-Settlement & Invoices
RT Initial Settlements |  |  |  | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs
RT Final Settlements (OD + 20) | 2010-05-24: Final Settlements Executed
RT True-up Statements (OD+ 45)
RT Re-Settlement
CRR Auction Invoicing | 2010-04-19: May Monthly Invoices Posted; 2010-05-03: Balance of Year Invoices Posted; 2010-05-17: June Monthly Invoices Posted
CARD Invoice
Balancing Account Invoice
RTM & DAM Late Fee Invoice
Miscellaneous Invoice
Settlements Protocol Timeline |  |  |  | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort

## June
[6 empty] | Note that May will be focused on resolving issues from Phase 4 and ramping up to DAM 5x / week 2 hr LFC tests to be executed |  |  |  | Note that June will be focused on Operational Scenarios 2x / week and during LFC Closed Loop test 8hr LFC test will be executed
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
| 2010-04-01 | 2010-04-05 | 2010-04-12 | 2010-04-19 | 2010-04-26 | 2010-05-03 | 2010-05-10 | 2010-05-17 | 2010-05-24 | 2010-05-31 | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28
Day Ahead / RUC / SASM
Objective | Connectivity / Execution | AS Co-optimization | Network Constrained Solution / Initial DRUC | DAM + DRUC RT/DA Settlements | DAM + DRUC + HRUC + SASM RT/DA Settlements | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week
Network Constraints | None | None | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included
Self AS requested | 100% | 50% | 50% | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
DAM | 1x / week | 2x / week | 2x / week | 2x / week | 2x / week | 2x / week | 3x / week | 3x / week | 5x / week | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios
Load Bid MW Requested | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only
Virtual Bids / Offers | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 10 transactions totaling 100 MW/QSE/hr | Up to 10 transactions/ QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only
PTP Obligations | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW | None | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only
NOIE CRR Offers | Allocated CRRs only | Allocated CRRs only | None | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Any | Any | Any | Any | Any | Any
DRUC | None | None | DRUC w/ Thursday DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM
HRUC | None | None | None | None | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited
WRUC | None | None | None | None | None | None | None | None | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed
SASM | None | None | None | None | SASM Executed | SASM Executed | SASM Executed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | Executed as needed
COP Updates | None | None | After DAM and DRUC | After DAM and DRUC | After DAM, DRUC and HRUC | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM
Operational Scenarios | 2010-05-31: TBD (Potentially market defined) RUC fails; commit/decommit through VDI; 2010-06-07: DAM fails More than 1 SASM for same operating hour; 2010-06-14: Extend DAM / Insufficient AS RUC for AS; Cancellation of previous RUC commitment; 2010-06-21: Manual DRUC Commitment / Forced RUC of QSEs that have never received; 2010-06-28: Exercise all SASM types DAM Solution delay (past DRUC deadline)
Market Timeline | Best Effort | Best Effort | 1000/1330/1430 | 1000/1330/1430 | 1000/1330/1430/TBD/TBD | 1000/1330/1430/TBD/TBD | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
RTM / LFC
SCED | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7
Price Curve Limitations | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs Deconstructed Zonal During 2 hr Test | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs Deconstructed Zonal During 8 hr Test | 80-120% of costs | 80-120% of costs
LFC Testing | Individual Gen Tests | Individual Gen Tests | Individual Gen Tests | Re-Test per Scheduled Post 2-Hr Approach Doc | Re-Test per Scheduled | 2 hr LFC Prep Conduct 2-Hr LFC Workshop | 2 hr LFC Prep | 2 hr LFC Test Post 8-Hr Approach Doc | Analyze 2 hr LFC findings | Analyze 2 hr Test findings Report 2 hr Test findings Conduct 8-Hr LFC Workshop | 8 hr LFC Prep | 8 hr LFC Test Post 48-Hr Approach Doc | Analyze 8 hr LFC findings | Analyze 8 hr LFC findings Report 8 hr LFC findings Conduct 48-Hr LFC Workshop
Telemetry Issues | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime
Operational Scenarios | 2010-05-31: TBD (Potentially market defined); 2010-06-07: TBD (Potentially market defined); 2010-06-14: On-demand RUC Emergency Base Point flags RRS/NSRS deployment (Gen, CLR)
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday 2 hr LFC Workshop | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday 8 hr LFC Workshop | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday 48 hr LFC workshop
CRR
Monthly Auction | Post May Auction Notice |  | Post CRR Ownership May Auction Bidding | Post May Auction Results |  | Post June Auction Notice | Bidding | Auction results posted |  | Post July Auction Notice | July Auction Bidding | July Auction results posted |  | Post August Auction Notice
Balance of Year Auction Annual Auction | 2010-04-05: Post Notice; 2010-04-26: Balance of year Bidding; 2010-05-03: Balance of year Auction results posted
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
Outage Scheduling
Data Feed | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April / May effective date and test outages beyond April / May | Zonal to Nodal Import Process / MPs permitted actual outages for May effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal import process / MPs permitted actual outages for April effective date and test outages beyond May / June | Zonal to Nodal import process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal import process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal import process / MPs permitted actual outages for April effective date and test outages beyond May | Dual Entry for 48 hr OD/LFC test. MPs will update and maintain outages to match what is in Zonal for the week 11 48Hr OD/LFC test. Note: outages in Nodal will not be updated during weeks 9 and 10
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
Settlements
DAM Settlements & Invoices |  |  |  | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | BDs based on market inputs and actual scenarios
DAM Re-Settlement & Invoices | 2010-06-21: DAM Re-Settlement Executed
RT Initial Settlements |  |  |  | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | BDs based on market inputs and actual scenarios
RT Final Settlements (OD + 20) | 2010-05-24: Final Settlements Executed; 2010-05-31: Final Settlements Executed; 2010-06-07: Final Settlements Executed; 2010-06-14: Final Settlements Executed; 2010-06-21: Final Settlements Executed; 2010-06-28: Final Settlements Executed
RT True-up Statements (OD+ 45) | 2010-06-21: True-Up Settlements Executed; 2010-06-28: True-Up Settlements Executed
RT Re-Settlement
CRR Auction Invoicing | 2010-04-19: May Monthly Invoices Posted; 2010-05-03: Balance of Year Invoices Posted; 2010-05-17: June Monthly Invoices Posted; 2010-06-14: July Monthly Invoices Posted
CARD Invoice | 2010-06-14: May CARD Initial; 2010-06-21: May CARD Final
Balancing Account Invoice | 2010-06-14: May Balancing Account
RTM & DAM Late Fee Invoice | 2010-06-07: RTM and DAM Late Fee Invoice
Miscellaneous Invoice | 2010-06-28: Miscellaneous Invoice Issued
Settlements Protocol Timeline |  |  |  | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Protocol

## July
[6 empty] | Note that May will be focused on resolving issues from Phase 4 and ramping up to DAM 5x / week 2 hr LFC tests to be executed |  |  |  | Note that June will be focused on Operational Scenarios 2x / week and during LFC Closed Loop test 8hr LFC test will be executed |  |  |  |  | Note that July will be focused on exercising normal processes and procedures. 48 hr LFC test will be executed
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
| 2010-04-01 | 2010-04-05 | 2010-04-12 | 2010-04-19 | 2010-04-26 | 2010-05-03 | 2010-05-10 | 2010-05-17 | 2010-05-24 | 2010-05-31 | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26
Day Ahead / RUC / SASM
Objective | Connectivity / Execution | AS Co-optimization | Network Constrained Solution / Initial DRUC | DAM + DRUC RT/DA Settlements | DAM + DRUC + HRUC + SASM RT/DA Settlements | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Ramping to DAM 5x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week | Executing Operational Scenarios 2x / week | Exercising normal DAM / Processes and Procedures | Exercising normal DAM / Processes and Procedures + 7X24 support for adjustment period | Exercising normal DAM / Processes and Procedures | Exercising normal DAM / Processes and Procedures + 7X24 support for adjustment period
Network Constraints | None | None | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included | Included
Self AS requested | 100% | 50% | 50% | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
DAM | 1x / week | 2x / week | 2x / week | 2x / week | 2x / week | 2x / week | 3x / week | 3x / week | 5x / week | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios | 3x / week normal 2x / week Op Scenarios | 5x / week | 7x / week | 5x / week | 7x / week
Load Bid MW Requested | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | 80% Tue/120% Thurs forecasted load | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only
Virtual Bids / Offers | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 5 transactions totaling 50 MW/QSE/hr | Up to 10 transactions totaling 100 MW/QSE/hr | Up to 10 transactions/ QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Up to 10 transactions/QSE/hr | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only
PTP Obligations | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW | None | Up to 5 bids totaling 50 MW | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Up to 5 bids totaling 50 MW unless the bid represents QSE's load | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only | Restrained based on OLA only
NOIE CRR Offers | Allocated CRRs only | Allocated CRRs only | None | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Allocated CRRs only | Any | Any | Any | Any | Any | Any | Any | Any | Any | Any
DRUC | None | None | DRUC w/ Thursday DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM | DRUC w/ each DAM
HRUC | None | None | None | None | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC Executed Limited | HRUC 7x24 | HRUC Executed Limited | HRUC 7x24
WRUC | None | None | None | None | None | None | None | None | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed | Executed on Mon and Wed
SASM | None | None | None | None | SASM Executed | SASM Executed | SASM Executed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | Executed as needed | SASM Executed | Executed as needed | SASM Executed
COP Updates | None | None | After DAM and DRUC | After DAM and DRUC | After DAM, DRUC and HRUC | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM | After DAM, DRUC HRUC, SASM
Operational Scenarios | 2010-05-31: TBD (Potentially market defined) RUC fails; commit/decommit through VDI; 2010-06-07: DAM fails More than 1 SASM for same operating hour; 2010-06-14: Extend DAM / Insufficient AS RUC for AS; Cancellation of previous RUC commitment; 2010-06-21: Manual DRUC Commitment / Forced RUC of QSEs that have never received; 2010-06-28: Exercise all SASM types DAM Solution delay (past DRUC deadline)
Market Timeline | Best Effort | Best Effort | 1000/1330/1430 | 1000/1330/1430 | 1000/1330/1430/TBD/TBD | 1000/1330/1430/TBD/TBD | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols - Best Effort | Protocols | Protocols | Protocols | Protocols
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
RTM / LFC
SCED | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7 | Continuos 24x7
Price Curve Limitations | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs Deconstructed Zonal During 2 hr Test | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs Deconstructed Zonal During 8 hr Test | 80-120% of costs | 80-120% of costs | 80-120% of costs | 80-120% of costs Deconstructed Zonal During 48 hr Test | 80-120% of costs | 80-120% of costs
LFC Testing | Individual Gen Tests | Individual Gen Tests | Individual Gen Tests | Re-Test per Scheduled Post 2-Hr Approach Doc | Re-Test per Scheduled | 2 hr LFC Prep Conduct 2-Hr LFC Workshop | 2 hr LFC Prep | 2 hr LFC Test Post 8-Hr Approach Doc | Analyze 2 hr LFC findings | Analyze 2 hr Test findings Report 2 hr Test findings Conduct 8-Hr LFC Workshop | 8 hr LFC Prep | 8 hr LFC Test Post 48-Hr Approach Doc | Analyze 8 hr LFC findings | Analyze 8 hr LFC findings Report 8 hr LFC findings Conduct 48-Hr LFC Workshop | Prep for 48 hr tests Practice Operational Scenarios | 48 hr LFC Test | Analyze 48 hr test findings | Analyze 48 hr test findings Report 48 hr Test findings
Telemetry Issues | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime | Monitored in Realtime
Operational Scenarios | 2010-05-31: TBD (Potentially market defined); 2010-06-07: TBD (Potentially market defined); 2010-06-14: On-demand RUC Emergency Base Point flags RRS/NSRS deployment (Gen, CLR); 2010-07-12: SCED Failure Voltage Support RRS/NSRS deploy (Gen/CLR/LR) Declare EEA
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday 2 hr LFC Workshop | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday 8 hr LFC Workshop | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday 48 hr LFC workshop | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
CRR
Monthly Auction | Post May Auction Notice |  | Post CRR Ownership May Auction Bidding | Post May Auction Results |  | Post June Auction Notice | Bidding | Auction results posted |  | Post July Auction Notice | July Auction Bidding | July Auction results posted |  | Post August Auction Notice | August Auction Bidding | August Auction results posted
Balance of Year Auction Annual Auction | 2010-04-05: Post Notice; 2010-04-26: Balance of year Bidding; 2010-05-03: Balance of year Auction results posted
Market Timeline | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol / Best Effort | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol | Protocol
Credit | Manual | Manual | Manual | Manual | Manual | Manual | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated | Itegrated
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday Phase 5 Kick Off | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
Outage Scheduling
Data Feed | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond April | Zonal to Nodal Import Process / MPs permitted actual outages for April / May effective date and test outages beyond April / May | Zonal to Nodal Import Process / MPs permitted actual outages for May effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Dual Entry for 8hr LFC. Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May / June | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Zonal to Nodal Import Process / MPs permitted actual outages for April effective date and test outages beyond May | Dual Entry for 48 hr OD/LFC test. MPs will update and maintain outages to match what is in Zonal for the week 11 48Hr OD/LFC test. Note: outages in Nodal will not be updated during weeks 9 and 10 | Dual Entry for 48 hr OD/LFC test. MPs will update and maintain outages to match what is in Zonal for the week 11 48Hr OD/LFC test. Note: outages in Nodal will not be updated during weeks 9 and 10 | Dual Entry for 48 hr OD/LFC test. MPs will update and maintain outages to match what is in Zonal for the week 11 48Hr OD/LFC test. | MPs permitted actual outage updates | MPs permitted actual outage updates
Market Calls | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday | Monday / Friday
Settlements
DAM Settlements & Invoices |  |  |  | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios
DAM Re-Settlement & Invoices | 2010-06-21: DAM Re-Settlement Executed; 2010-07-26: DAM Re-Settlement Executed
RT Initial Settlements |  |  |  | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | Partial BDs Specified BDs during scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios | BDs based on market inputs and actual scenarios
RT Final Settlements (OD + 20) | 2010-05-24: Final Settlements Executed; 2010-05-31: Final Settlements Executed; 2010-06-07: Final Settlements Executed; 2010-06-14: Final Settlements Executed; 2010-06-21: Final Settlements Executed; 2010-06-28: Final Settlements Executed; 2010-07-05: Final Settlements Executed; 2010-07-12: Final Settlements Executed; 2010-07-19: Final Settlements Executed; 2010-07-26: Final Settlements Executed
RT True-up Statements (OD+ 45) | 2010-06-21: True-Up Settlements Executed; 2010-06-28: True-Up Settlements Executed; 2010-07-05: True-Up Settlements Executed; 2010-07-12: True-Up Settlements Executed; 2010-07-19: True-Up Settlements Executed; 2010-07-26: True-Up Settlements Executed
RT Re-Settlement | 2010-07-05: Re-Settlement Executed; 2010-07-26: Re-Settlement Executed
CRR Auction Invoicing | 2010-04-19: May Monthly Invoices Posted; 2010-05-03: Balance of Year Invoices Posted; 2010-05-17: June Monthly Invoices Posted; 2010-06-14: July Monthly Invoices Posted; 2010-07-12: August Monthly Invoices Posted
CARD Invoice | 2010-06-14: May CARD Initial; 2010-06-21: May CARD Final; 2010-07-12: June CARD Initial; 2010-07-19: June CARD Final
Balancing Account Invoice | 2010-06-14: May Balancing Account; 2010-07-12: June Balancing Account
RTM & DAM Late Fee Invoice | 2010-06-07: RTM and DAM Late Fee Invoice; 2010-07-12: RTM and DAM Late Fee Invoice
Miscellaneous Invoice | 2010-06-28: Miscellaneous Invoice Issued
Settlements Protocol Timeline |  |  |  | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Best Effort | Protocol | Protocol | Protocol | Protocol | Protocol