## Slide 1
Steady-State Working Group Report
ROS
May 13, 2010

## Slide 2: SSWG Activities
SSWG has met four times since the April ROS meeting
  April 14 Conference Call
  April 22 Meeting
  April 28 Conference Call
  May 12 Conference Call
TPIT update posted April 16
Currently creating 2011 Data Set A cases
Future meetings
  May 26
  June 15-17

## Slide 3: SSWG Nodal Planning Model Activities
CRR Related Issues- (as of May 3)
Correcting Connectivity Node Groups
  Feb 26 TP output: 1063 CNGs needing correction
  May 3 TP output: 325 CNGs needing correction
1063
892
863
757
721
540
522
440
325
325
0

## Slide 4: SSWG Nodal Planning Model Activities
Topology Processor changes (Radial line reduction, Multi-section line creation)
  Delivery scheduled for May 28
  SSWG has submitted a System Change Request related to the Topology Processor changes
  Will require additional changes to planning data in IMM (PSSE ckt IDs, PSSE bus numbers) after May 28
SSWG will ask ROS for SCR approval in June
SSWG requests direction from ROS for future System Change Request related to creation of Planning cases in Nodal environment (Examples, see SSWG Modeling Issues slide)
  Does ROS need to approve each SCR?
SSWG seeks approval of NPRR224
Planning Model Change Request (PMCR) & Model On Demand (MOD) training in July

## Slide 5: SSWG Nodal Planning Model Issues
Annual Planning Model related issues:
Transformer modeling: 2 winding vs 3 winding
No ratings on zero impedance line segments
Ownership
Loads and cap banks being collapsed to the correct CNGs
Cap banks connected to distribution voltage
FACTS devices

## Slide 6: SSWG Additional Items
Wind Generator Dispatch – Future cases
  SSWG agreed to begin using AWS Truewind data in cases with all CREZ lines modeled
  ERCOT currently drafting procedures
June TPIT update
  Due to Nodal work and training, SSWG plans to only update 345 kV changes to 10DSB cases
September TPIT update
  Due to Nodal work, SSWG plans to only update 2011 Winter and 11DSA cases
Notes: <number>

## Slide 7: SSWG Schedule
  May 21 TSP/SSWG remaining data changes for CRR Model
  May 25 TP output with all changes through 5/21
  May 26 SSWG meeting – Taylor
  May 28 ERCOT Topology Processor enhancements delivered
  May 28 Pass 3 changes due to ESP
  June 1 TPIT spreadsheet updates due to ERCOT
  June 4 ERCOT Sends Pass 4 cases to SSWG
  June – August Make remaining changes to IMM prior to Planning Go-Live
  June 11 Pass 4 changes due to ESP (updated gen dispatch for the meeting on the 15th)
  June 15-17 SSWG meeting to finalize cases
  June – July TPIT update work
  July TSPs Complete changes based on TP enhancements
  July MOD/PMCR training
  Aug Compare TP output to SSWG 2010 summer peak case
  Sept 1 TPIT spreadsheet updates due to ERCOT
  Sept 21-23 SSWG meeting to finalize DSB cases
  Sept – Oct TPIT update work
  Nov Create 2012 summer peak case using TP and MOD
  Dec – Feb 2011 Review, update, and modify TP/MOD process for case creation
  Dec 1 TPIT spreadsheet updates due to ERCOT
  Dec 1 Nodal Go-Live
  Dec – Jan 2011 TPIT update work
  Mar – April 2011 Assuming Nov test meets SSWG approval, begin work to create 12DSA using Nodal method
Nodal work
Base Case development
TPIT Updates