|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for April 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 217 active generation interconnection requests totaling over 72,000 MW. This includes over 44,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total of $678.5 Million - Transmission Projects approved in 2010 total $2.9 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.6 Billion - Transmission Projects energized in 2010 total about $41.3 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	4

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Other Notable Activities	16

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations   -  None

## The total installed wind capacity remains  9,117 MW, of which 7,958 MW (87%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements

## Las Brisas Energy Center (12INR0016) in Nueces County for 1,300 MW (Petroleum Coke – Steam)

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 217 active generation interconnection or change requests |  |  |  |  |
| As of April 30, 2010 | North | South | West | Total |
| Security Screening Study | 3 | 7 | 7 | 17 |
| SSS Completed | 11 | 6 | 19 | 36 |
| Full Interconnect Study | 21 | 20 | 83 | 124 |
| FIS Completed | 5 | 13 | 2 | 19 |
| Interconnect Agreement Completed | 6 | 6 | 5 | 17 |
| Capacity under Interconnection Agreements | 3,632 | 2163 | 626 | 6,421 |
| Capacity for Grid, MW | 20,545 | 18,913 | 33,241 | 72,699 |
| Wind Capacity, MW | 5,191 | 8,069 | 30,886 | 44,146 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,554 | 13,715 |
| Gas-CT |  |  | 50 | 597 |
| Total Gas | 2,169 | 8,539 | 3,604 | 14,312 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 3,727 | 1,353 | 5,080 |
| Wind | 6,994 | 31,216 | 5,936 | 44,146 |
| Solar | 419 | 549 |  | 968 |
| Biomass | 58 | 50 | 145 | 253 |
| Other |  | 740 | 1,300 | 2,040 |
| Grand Total | 9,640 | 44,821 | 18,238 | 72,699 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of April 30, 2010 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change from Last Report |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Jul-10 | Gas-CC | 50 |  |
| 10INR0070 | Greenville Engine Plant | PL | Hunt | North | Jul-10 | Gas-CT | 50 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | Sep-10 | Wind | 150 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 | Wind | 400 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Dec-10 | Biomass | 45 |  |
| 08INR0012b | Papalote Creek Phase 2 | IA | San Patricio | South | Dec-10 | Wind | 198 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 | Coal | 263 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-11 | Wind | 150 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 | Wind | 194 | Date |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 | Wind | 200 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 | Coal | 925 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 | Wind | 350 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-12 | Wind | 150 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 | Wind | 500 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 | Wind | 120 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 | Wind | 202 | Date |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-12 | Wind | 120 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Jun-14 | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-14 | Wind | 100 |  |
| 12INR0016 | Las Brisas Energy Center | IA | Nueces | South | Sep-14 | Other | 1,300 | New |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
|  |  |  |  |  |  | TOTAL | 18,238 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 09INR0054 | Stonewall | 149 | TBD | Wind |
| 09INR0061 | Kent | 258 | TBD | Wind |  | 10INR0048 | Hardeman | 1,000 | TBD | Wind |
| 10INR0045 | Webb | 734 | TBD | Wind |  | 10INR0046 | Jim Hogg | 264 | TBD | Wind |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 09INR0069 | Reagan | 36 | TBD | Wind |
| 09INR0070 | Reagan | 42 | TBD | Wind |  | 10INR0054 | Palo Pinto | 36 | TBD | Wind |
| 10INR0079 | Nolan | 60 | TBD | Wind |  | 10INR0069 | Rusk | 13 | TBD | Coal |
| 10INR0029 | Hood | 810 | Jun-10 | Gas |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 09INR0081 | Rusk | 18 | Jun-10 | Coal |  | 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |
| 10INR0013 | Upton | 400 | Jul-10 | Wind |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 10INR0041 | Floyd | 135 | Oct-10 | Wind |  | 09INR0074 | Motley | 70 | Oct-10 | Wind |
| 10INR0081a | Clay | 30 | Oct-10 | Wind |  | 10INR0089 | Harris | 40 | Oct-10 | Other |
| 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 10INR0008 | Pecos | 500 | Dec-10 | Wind |  | 08INR0061 | Hardeman | 200 | Dec-10 | Wind |
| 08INR0062 | Archer | 249 | Dec-10 | Wind |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 11INR0012 | Duval | 400 | Dec-10 | Wind |  | 10INR0032 | Navarro | 775 | Dec-10 | Gas |
| 10INR0033 | Armstrong | 399 | Dec-10 | Wind |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 09INR0076 | Jackson | 300 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 10INR0056 | Borden | 249 | Dec-10 | Wind |  | 10INR0060 | Willacy | 401 | Dec-10 | Wind |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 10INR0082 | Travis | 30 | Dec-10 | Solar |  | 11INR0050 | Crosby | 149 | Mar-11 | Wind |
| 11INR0081 | Live Oak | 72 | Mar-11 | Wind |  | 11INR0071 | Harris | 7 | Apr-11 | Gas |
| 11INR0075 | Fort Bend | 15 | Apr-11 | Coal |  | 11INR0086 | Travis | 60 | Apr-11 | Solar |
| 10INR0009 | Castro | 300 | May-11 | Wind |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 11INR0048 | Harris | 300 | May-11 | Gas |  | 11INR0061 | Presidio | 90 | May-11 | Solar |
| 11INR0060 | Tom Green | 90 | May-11 | Solar |  | 11INR0058 | Pecos | 135 | May-11 | Solar |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 11INR0087 | Wise | 90 | May-11 | Gas |
| 11INR0033b | Cameron | 200 | May-11 | Wind |  | 11INR0033a | Cameron | 200 | May-11 | Wind |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 10INR0023 | Haskell | 386 | Jun-11 | Wind |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 11INR0054 | San Patricio | 161 | Jun-11 | Wind |  | 11INR0057 | Cameron | 165 | Jun-11 | Wind |
| 11INR0065 | Nueces | 240 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 640 | Aug-11 | Gas |  | 11INR0008a | Roberts | 1,000 | Sep-11 | Wind |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |  | 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |
| 10INR0062a | Pecos | 80 | Oct-11 | Wind |  | 10INR0081b | Clay | 19 | Oct-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 11INR0013 | Mills | 150 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 12INR0034 | Borden | 342 | Dec-11 | Wind |
| 09INR0048 | Jack | 150 | Dec-11 | Wind |  | 09INR0075 | Kinney | 248 | Dec-11 | Wind |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 11INR0049 | Wharton | 275 | May-12 | Gas |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 10INR0022 | Harris | 1,380 | Jun-12 | Gas |
| 12INR0002 | Briscoe | 750 | Jul-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 12INR0027 | Gray | 200 | Oct-12 | Wind |
| 08INR0019b | Gray | 250 | Nov-12 | Wind |  | 08INR0019c | Gray | 250 | Nov-12 | Wind |
| 08INR0019a | Gray | 250 | Nov-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 12INR0035 | Nueces | 249 | Nov-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 08INR0054 | Comanche | 401 | Dec-12 | Wind |  | 08INR0056 | Nolan | 149 | Dec-12 | Wind |
| 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |  | 12INR0018 | Gray | 600 | Dec-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |  | 09INR0058 | Howard | 250 | Mar-13 | Wind |
| 10INR0062b | Pecos | 220 | May-13 | Wind |  | 09INR0041 | Mitchell | 300 | Jun-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0006 | Gray | 750 | Oct-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 06INR0022e | Kenedy | 200 | Dec-13 | Wind |  | 08INR0022 | Floyd | 100 | Dec-13 | Wind |
| 08INR0023 | Floyd | 100 | Dec-13 | Wind |  | 09INR0077 | Reagan | 500 | Dec-13 | Wind |
| 09INR0073 | Scurry | 200 | Dec-13 | Wind |  | 13INR0010 | Parmer | 1,200 | Dec-13 | Wind |
| 14INR0002 | Goliad | 756 | Feb-14 | Coal |  | 14INR0003 | Nolan | 850 | Jun-14 | Coal |
| 14INR0005 | Matagorda | 1,200 | Jul-14 | Coal |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 16INR0002 | Brazoria | 700 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project has been withdrawn due to changes in the study assumptions.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Austin Energy has submitted a project to construct a new 345 kV bus with a 345/ 138 kV autotransformer at the Dunlap station.  The project also involves rerouting several nearby transmission lines.  The estimated cost of the project is $16.7 M.  This project is currently in the comment phase.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints & Capacity Shortages– April, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
|  | DFW Reactive | $ 2,888,611 | Renner SVCs [10TPIT0056; 11TPIT0095] |  |
| Graham SES - Long Creek Switching Station & Cookfield Road Switching Station 345kV | Comanche Switch - Comanche Tap 138kV | $ 1,669,891 |  | Outage on Comanche Peak SES 345KV CB and Comanche Switch DSC 345 KV |
| Graham SES - Long Creek Switching Station & Cookfield Road Switching Station 345kV | Cisco - Putnam 69kV | $ 851,650 | Cisco, convert station to 138kV [11TPIT0056] |  |
| Roanoke Switch - West Denton & Lewisville Switch 345kV | West Denton - Pockrus 138kV | $ 732,181 | West Denton re-route (07TPIT0132) | Outage on West Denton-Jim Christal and North Denton-JMCRSTL 138 kV |
| Roanoke Switch - West Denton & Lewisville Switch 345kV | West Denton - Teasley 138kV | $ 707,340 | West Denton re-route (07TPIT0132) | Outage on West Denton-Jim Christal and North Denton-JMCRSTL 138 kV |
| Abilene Mulberry Creek - Bitter Creek & Long Creek Switching Station - Sweetwater Generating Plant 345kV | Merkel - Trent 69kV | $ 660,768 |  | Outage on Potter to McElmurray Tap 138kV |
| Pawnee - Lon Hill 345kV | Sinton - Skidmore 69kV | $ 544,324 | Lon Hill to Sinton 69 kVLine Modifications [11TPIT0103] |  |
| Graham SES - Parker Switch 345kV | Barton Switch - Oran TU 138kV | $ 312,159 |  |  |
| Odessa EHV - Morgan Creek - Quail Switch 345kV | Big Spring Switch - Big Spring West 138kV | $ 256,296 |  | Outage on Cal Energy 345 KV breaker and Midland East 345 KV switch |
| Paris Switch - Valley & Paris Switch - Valley South 345kV | Paris Switch 345/138kV Autotransformer | $ 193,051 |  | Outage on Monticello SES 345kV bus and Monticello SES - Paris SW 345 KV |

Inter-zonal Congestion

# Other Notable Activities

Work on the 2010 Five-Year Transmission Plan is underway.  The initial set of projects needed to reliably serve load in 2015 has been identified and is out for comment.  The analysis is currently focused on finding reliability projects for the years 2011-2014.

The final 2009 Five-Year Transmission Plan report has been posted to the ERCOT Planning and Operations Information website.

Nodal Network Model Management System Topology Processor work continues with bi-weekly meetings/calls with SSWG and weekly ERCOT topology processor output.  The most recent topology processor output was the first utilizing the NMMS 8.2 upgrade to the NMMS database which eliminates one day of processing before creating a Topology Processor output.  This will allow ERCOT to create the weekly toplogy processor output and give the ERCOT TSPs an additional day to submit NOMCR that will be reflected in that output.

The Phase III of the Voltage Ride Through Study continues.  Contingency simulations for the study base scenarios (high wind/high load and high wind/low load) are complete.  Analysis is underway for additional scenarios with no West Texas conventional generation online and the inclusion of dynamic motor load models.  The vendor has reached out to both equipment manufacturers and simulation software providers to investigate certain unusual wind turbine model responses observed during Phase III dynamic simulations.