## Slide 1: TSP Nodal Engagement Market Participant Call
http://nodal.ercot.com <number>
ERCOT
May 5, 2010

## Slide 2: Antitrust Admonition
http://nodal.ercot.com <number>
ANTITRUST ADMONITION
ERCOT strictly prohibits Market Participants and their employees who are participating in ERCOT activities from using their participation in ERCOT activities as a forum for engaging in practices or communications that violate the antitrust laws. The ERCOT Board has approved guidelines for members of ERCOT Committees, Subcommittees and Working Groups to be reviewed and followed by each Market Participant attending ERCOT meetings. If you have not received a copy of these Guidelines, copies are available at the Client Relations desk. Please remember your ongoing obligation to comply with all applicable laws, including the antitrust laws.
DISCLAIMER
All presentations and materials submitted by Market Participants or any other Entity to ERCOT staff for this meeting are received and posted with the acknowledgement that the information will be considered public in accordance with the ERCOT Websites Content Management Operating Procedure.

## Slide 3: Agenda
Reminder of Objective
Update for Network Operations Model
Planning Model activities
TSP Outage Scheduler activities
Transitioning to Nodal go-live
Metrics update (includes telemetry)
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 4: Objectives
This TSP dedicated call is on a bi-weekly basis to better communicate and track significant activities/issues/risks specifically related to nodal program activities
Attempting to aggregate key nodal information together for TSPs
  This call does not replace other forums
    ROS/NDSWG/SSWG/NATF/PRS/NodalTrialCalls/TAC/Board
Reminder of Nodal Calendar Meetings/Training:
  http://nodal.ercot.com/readiness/index.html
  Special note-
    Web-Based Training module of the Outage Scheduler User Interface available in next few weeks.
    Note that in June (at Austin, Houston and Dallas) will be one day sessions to present the outage scheduler tool, reinforce the web-based training and answer any questions.
    Sessions will be available to TSPs and QSEs although most of the discussion may be applicable to TSPs. We intend to follow up these sessions with some web-cast conference calls in late June or early July to address issues specific to the larger community of QSEs with Resources.
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 5: Market Trials 2010 Roadmap
http://nodal.ercot.com <number>

## Slide 6: Agenda
Introduction
Update for Network Operations Model
Planning Model activities
TSP Outage Scheduler activities
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 7: Nodal Model Effort Activity
ERCOT TAC Meeting - ROS Report
03/04/2010 Ken Donohoo
<number>
Operations
Model
(NMMS)
CRR
Model
Topology
Processor
(Software)
Long Term
Planning
Model
NDSWG
Support
SSWG
Support
SSWG
Support
SSWG
& ERCOT
Development

## Slide 8: Update for Network Operations Model
Network Operations Model Validation:
  24 of 28 TSPs have submitted confirmation that validation complete
  Represents 99.9% of the modeled system equipment
  Materials still available from last TSP validation workshop
    http://www.ercot.com/calendar/2010/04/20100409-MTTSP
NMMS System Update
Currently experiencing 3 issues in production:
1- Performance issues with Oracle – currently identifies as ERCOT owned
2- Issues with NMMS data templates and data consistency – Siemens owned
3- Issues with PTC and NOMCR’s – Siemens owned
Issue 1 Database issue being addresses. The behavior currently exhibited on production is not reproducible in other environments.
Issue 2 Being addressed by Siemens, first tests have identified the problem and Siemens should have a fix ready for production today.
Issue 3 Being addressed by Siemens, difficult to reproduce.
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 9: Agenda
Introduction
Update for Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 10: Nodal Model Effort Activity
ERCOT TAC Meeting - ROS Report
03/04/2010 Ken Donohoo
<number>
Operations
Model
(NMMS)
CRR
Model
Topology
Processor
(Software)
Long Term
Planning
Model
NDSWG
Support
SSWG
Support
SSWG
Support
SSWG
& ERCOT
Development

## Slide 11: Status of Model for CRR Auction
http://nodal.ercot.com <number>
SSWG began analyzing output from Network Operations Model via the Topology Processor in December 2009 to validate data
Recognition at SSWG of gaps in data needed to support Topology Processor logic
SSWG/ERCOT quantifying effort needed to close gaps in Network Operations Model for proper provisioning of the model via Topology Processor to the CRR Monthly Auctions
  Change data (TSP submit data updates)
  Change software (ERCOT changes Topology Processor)
NMMS Network
Operations
Model
CRR
Model
NMMS
Topology Processor
Software Creates and
Exports Model
Process Flow for creating CRR Model
Notes: <number>
<number>

## Slide 12: Status of Model for CRR Auction
http://nodal.ercot.com <number>
Market Trial High-Level Key Dates:
  June CRR Auction (conduct in May)
    March 17 TSP/SSWG Phase 1 work- assignment of Connectivity Node Groups and PSSE Generator IDs
  July CRR Auction (conduct in June)
    April 30 TSP/SSWG data changes received improve CRR Model for Connectivity Node to Connectivity Node Group assignment
  August CRR Auction (conducted in July)
    May 21 TSP/SSWG remaining data changes for CRR Model
    May 28 ERCOT Topology Processor enhancements delivered
    Note this is the last trial auction prior to 168-hour test
Notes: <number>
<number>

## Slide 13: SSWG Nodal Schedule
  April 30 Submit CNG and CN updates for first CRR market trials
  May 4 TP output with all changes through 4/30
  May 12 SSWG conference call
  May 21 TSP/SSWG remaining data changes for CRR Model
  May 25 TP output with all changes through 5/21
  May 26 SSWG meeting – Taylor
  May 28 ERCOT Topology Processor enhancements delivered
  June – August Make remaining changes to IMM prior to Planning Go-Live
  July TSPs Complete changes based on TP enhancements
  July MOD/PMCR training
  Aug Compare TP output to SSWG 2010 summer peak case
  Nov Create 2012 summer peak case using TP and MOD
  Dec – Feb 2011 Review, update, and modify TP/MOD process for case creation
  Dec 1 Nodal Go-Live
  Mar – April 2011 Assuming Nov test meets SSWG approval, begin work to create 12DSA using Nodal method

## Slide 14: SSWG Planning Model Activities
CRR Related Issues- (as of May 3)
Correcting Connectivity Node Groups
  Feb 26 TP output: 1063 CNGs needing correction
  Apr 5 TP output: 540 CNGs needing correction
  May 3 TP output: 325 CNGs needing correction
Get Connectivity Nodes into the correct CNGs (i.e. Fix Topology)
Topology Processor changes
  SSWG has submitted a System Change Request related the Topology Processor changes
Identifying important modeling issues

## Slide 15: SSWG Modeling Issues
Annual Planning Model related issues:
Transformer modeling: 2 winding vs 3 winding
No ratings on zero impedance line segments (double check)
Ownership
Loads and cap banks being collapsed to the correct CNGs
Cap banks connected to distribution voltage
FACTS devices

## Slide 16: Agenda
Introduction
Update for Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
TSP Telemetry Update
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 17: Nodal Model Effort Activity
ERCOT TAC Meeting - ROS Report
03/04/2010 Ken Donohoo
<number>
Operations
Model
(NMMS)
CRR
Model
Topology
Processor
(Software)
Long Term
Planning
Model
NDSWG
Support
SSWG
Support
SSWG
Support
SSWG
& ERCOT
Development

## Slide 18: Planning Go-Live Summary
http://nodal.ercot.com <number>
Justification of Planning Model Go-Live in 2010
  ERCOT understanding that Nodal Planning Model functionality is needed to comply with Nodal Protocols effective Dec 1, 2010
  ERCOT understanding that annual planning models will be created using new toolset (ie MOD) based on the Network Operations Model after Dec 1, 2010
    Impacts Data sets published in 2011 (for 2012/2015)
    Impacts Annual CRR Auction conducted in 2011 (for 2012/2013)
Potential ERCOT flexibility in 2010 implementation dates
  ERCOT will work with TSPs (SSWG) and QSE/CRR (NATF) to consider refinement of Planning Model Go-Live sequence to extend from August 2010 go-live to being no later than Dec 1, 2010
  ERCOT needs to work with TSPs on details of timing
Notes: <number>
<number>

## Slide 19: Agenda
Introduction
Update for Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 20: TSP Outage Scheduler
http://nodal.ercot.com <number>
Qualification activities in-flight
Weekly Market Call every Friday 9-10am
  http://www.ercot.com/committees/nodal/mt/index
Handbook for Outage Scheduler Activities
  http://nodal.ercot.com/readiness/markettrials/os/index.html
OS Qualification Status
  23/25 TSPs
  99.8% complete Equipment Share
Notes: <number>
<number>

## Slide 21: Agenda
Introduction
Validation and maintenance of the Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 22: Working Towards Go-Live
http://nodal.ercot.com <number>
Update on Frequency Model Load
  Network Operations Model currently being consumed every 2 weeks by Nodal EMS/MMS and other downstream systems
  Closely aligned with Zonal Model load
  ERCOT working on potentially increasing nodal model load frequency to weekly frequency
NPRRs/OGRRs in discussion
  NOGRR034- Telemetry Performance (June ROS)
  NPRR146- ICCP Telemetry/NetworkModel (May ROS)
  NPRR219- Alignment NPRR for Outages (PRS)
  NPRR224- Remove Dynamic Ratings for Annual Planning Model (PRS)
Notes: <number>
<number>

## Slide 23: Working Towards Go-Live
http://nodal.ercot.com <number>
ERCOT recognition that some Nodal Protocols come into effect to align with 12/1/2010 which are weeks or months before go-live on 12/1/2010
  TSP Model Changes due by Sept 1, for Dec 1 (per protocols 3.10.1)
  Outages in parallel/dual-entry to support CRR Auction Model and Go-Live
  CRR Auction process Oct-Nov 2010
  Potential Board action on Nodal Protocols in July for market notice on August 1 for effective date on Sept1
May 25 Nodal Workshop to discuss go-live sequence
  http://www.ercot.com/calendar/2010/05/20100525-MT
Notes: <number>
<number>

## Slide 24: Agenda
Introduction
Update for Network Operations Model
Planning Model activities
  Supporting Monthly CRR Auction
  Model On-Demand
TSP Outage Scheduler activities
Transitioning to Nodal go-live
Metrics update
http://nodal.ercot.com <number>
Notes: <number>
<number>

## Slide 25: Network Modeling Metrics
http://nodal.ercot.com <number>
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
Market Participant Metrics |  |  |  |  |  |  |  |  | 
MP14-C TSP Model Validation | Green | TSPs | Ownership Ratio Share | 99.9% | .1% | 0.0% | 0.0% | Network Model data validated by TSP | 24/28 TSPs have submitted model validation e-mail to ERCOT.
MP6 Telemetry Compliance with Nodal Protocols 3.10.7.5 | Green | QSERs | Generation Ratio Share | 100% | 0.0% | 0.0% | 0.0% | Expected State Estimator telemetry submitted. | 78/78 complete. 3502 total SE points provided
 | Green | QSERs | Generation Ratio Share | 100% | 0.0% | 0.0% | 0.0% | Expected SCED telemetry submitted. | 78/78 complete. 7629 SCED points provided
 | Green | TSPs | Ownership Ratio Share | 99.3% | 0.0% | 0.0% | .7% | Expected TSP telemetry per ICCP Handbook submitted | 16/17 TSPs above 95% threshold for GREEN. 357 points outstanding
MP18 Mapping of Resources and Loads in Private Use Networks | 6/2/2010 | QSERs | Generation Ratio Share | N/A | N/A | N/A | N/A | # of QSE(n) PUN Points Provided / # of QSE(n) PUN Points Expected | 306 points across 7 QSEs with Resources. 15 points still assigned to TDSP.
MP23 Telemetry Quality (MP to ICCP server) | 7/14/2010 | TSPs | Ownership Ratio Share | N/A | N/A | N/A | N/A | # of TSP(n) Suspect/Bad points provided / # of TSP(n) points total | 1356 Suspect/Bad points (97.9% good quality).
 | 7/14/2010 | QSERs | Generation Ratio Share | N/A | N/A | N/A | N/A | # of QSER(n) Suspect/Bad points provides / # of QSER(n) points total | 871 Suspect/Bad points (94.9% good quality)
Network Model Metrics
Notes:
MP6 does not include 405 QSE CB and DSC points from TSP outreach. ERCOT is determining whether these rollback into the QSER MP6 measurement

## Slide 26: Network Model Metrics
http://nodal.ercot.com <number>
Network Modeling Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
ERCOT Metrics |  |  |  |  |  |  |  |  | 
EMO9(A) State Estimator Standards Performance | 5/19/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | State Estimator converges 97% during monthly test period | March 91.4% convergence
EMO9(B) RTCA Modeling Differences | 5/19/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | 95% of values matched between Zonal and Nodal Network Models Impedances Dynamically and Non-dynamically Rated Lines Load Tap Settings | Measurement excludes pseudo switches and multi-section lines
EMO9(C) RTCA CSC Comparison | 7/14/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | CSC Pre-contingency SE Flows within 5% (Hourly snapshot) | Measurement establishes baseline flows on Commercial lines to indicate the significance of Psuedo modeling and multi-section lines on the SE flows.
EMO9(D) Validate Zonal and Nodal Security Analysis Results | 9/8/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | 90% of active constraints in Zonal RTCA are also detected in Nodal RTCA | To be determined
Notes:
1. SE performance requirements in EMO12 moved to EMO9(A)

## Slide 27: MP6 Telemetry Compliance with Nodal Protocols 3.10.7.5
http://nodal.ercot.com <number>
 | TSP Telemetry Status |  |  |  | Disconnects |  |  |  | 
TSP - These statistics are consistent with the DSV11 4/14/10 nodal database load. Status indicators are provided here for Circuit Breaker points, Load Points, and Disconnects. Circuit Breaker points, Load points, and Disconnects will be measured in the MP-6 metric. | # nodal CB and LD points missing | # nodal CB and LD points provided | # nodal CB and LD points requested | % nodal CB and LD points provided | # disconnects missing | # disconnects provided | # disconnects requested | % disconnects provided | Overall
AUSTIN ENERGY | 0 | 748 | 748 | 100.0% | 1 | 870 | 871 | 99.9% | 99.9%
AEP TEXAS CENTRAL COMPANY | 6 | 2814 | 2820 | 99.8% | 17 | 5516 | 5533 | 99.7% | 99.7%
BRAZOS ELECTRIC POWER CO OP INC | 22 | 1170 | 1192 | 98.2% | 60 | 1735 | 1795 | 96.7% | 97.3%
BRYAN TEXAS UTILITIES | 15 | 135 | 150 | 90.0% | 24 | 277 | 301 | 92.0% | 91.4%
CENTERPOINT ENERGY HOUSTON ELECTRIC LLC | 1 | 2818 | 2819 | 100.0% | 1 | 2389 | 2390 | 100.0% | 100.0%
CPS ENERGY | 1 | 874 | 875 | 99.9% | 2 | 1277 | 1279 | 99.8% | 99.9%
CITY OF COLLEGE STATION | 0 | 35 | 35 | 100.0% | 0 | 51 | 51 | 100.0% | 100.0%
DENTON MUNICIPAL ELECTRIC | 2 | 84 | 86 | 97.7% | 10 | 117 | 127 | 92.1% | 94.4%
GEUS | 0 | 30 | 30 | 100.0% | 0 | 26 | 26 | 100.0% | 100.0%
CITY OF GARLAND | 0 | 319 | 319 | 100.0% | 5 | 603 | 608 | 99.2% | 99.5%
LCRA TRANSMISSION SERVICES CORPORATION | 9 | 1831 | 1840 | 99.5% | 24 | 3585 | 3609 | 99.3% | 99.4%
ONCOR ELECTRIC DELIVERY COMPANY | 32 | 5460 | 5492 | 99.4% | 96 | 8491 | 8587 | 98.9% | 99.1%
BROWNSVILLE PUBLIC UTILITY BOARD | 6 | 93 | 99 | 93.9% | 20 | 132 | 152 | 86.8% | 89.6%
RAYBURN COUNTRY CO OP DBA RAYBURN ELECTRIC | 53 | 136 | 189 | 72.0% | 142 | 79 | 221 | 35.7% | 52.4%
SOUTH TEXAS ELECTRIC CO OP INC | 4 | 626 | 630 | 99.4% | 2 | 1075 | 1077 | 99.8% | 99.6%
TEXAS-NEW MEXICO POWER CO | 0 | 591 | 591 | 100.0% | 42 | 1027 | 1069 | 96.1% | 97.5%
 | 151 | 17764 | 17915 | 99.2% | 446 | 27250 | 27696 | 98.4% | 98.7%
#s based on DSV11 (last CB, LD, and Disconnect breakdown)
Across the board improvement with DSV12 and DSV13
Next dashboard to be published 5/11
Scorecard updated (w/AMBER/RED scores 5/19)
MP6 RAG Rules
Red – < 80% of expected points sent by TSP
Amber – >= 80% and < 100% of expected points sent by TSP
Green – 100% of expected points sent by MP