Active Readiness Metric Inventory

V17.1

June 1, 2010

Table of Contents

Revision History	5

Introduction	13

Market Participant Metrics	14

MP3 – Market Submissions Connectivity Qualification	14

MP6 – Telemetry Compliance with the Nodal Protocols 3.10.7.5	14

MP11 – MP Resource Registration	15

MP14 – A – MP EDS-2, Release 3 Trials Participation	17

MP14–C – TSP Model Validation	17

MP15–A – Real-Time Market Participation	18

MP15(B) – CRR Connectivity Qualification	18

MP16 – Day-Ahead Market Participation	19

MP17 – MP Qualification Activities	20

MP18 – Mapping of Resources and Loads in Private Area Networks is Complete	21

MP20 – Outage Scheduler Connectivity Qualification	22

MP21 – Wind Generation Resources ICCP Telemetry	23

MP22 – New Entrant Readiness	24

MP23 – Telemetry Quality (MP to ICCP Server)	25

Commercial Operations Metrics	27

CO1 - Settle Market for 7 Days and provide appropriate extracts	27

CO2 - Verify Dispute Process	27

CO3 - Verify DAM Settlement Statements	28

CO4 - Zonal/Nodal Coordinated Settlement Operations	28

CO5 - Verify RTM Settlement Statements	29

CO6 - Verify RTM Settlement Invoices	29

CO7 - Verify DAM Invoices	30

CO8 - Verify CRR Auction Invoices	30

CO9 - Verify Financial Transfer and Processing	31

CO10 - Verify Credit Calculations	31

Congestion Revenue Rights Metrics	32

CRR2 - Develop TCR to CRR Transition Plan	32

CRR3 – Operation of CRR Auctions and Allocations	32

CRR4 - Implement TCR to CRR Transition Plan	33

ERCOT Internal Metrics	34

E1 - ERCOT Staff Completes Training	34

E2 - Verify ERCOT Performance Monitoring Test Plan	34

E3 - Validate Telemetry/SE ISM/ Data Accuracy	34

E4 - Transition Pricing Mechanisms	35

E5 - Nodal SAS 70 Readiness	36

E6 - Develop Nodal Operating Guides	37

E7 - Validate ISM Access & Accuracy of Postings Required by the IMM	37

E8 - ERCOT Staffed for Texas Nodal Operations	38

E9 - Develop TN Procedures	38

E10 - Validate ISM, CRD, and Lodestar Source Reporting Access & Accuracy for internal ERCOT use	39

E12 - MIS Compliance Test	40

E14 - Verify QSE Performance Monitoring Test Plan	41

E15 - Verify TSP Performance Monitoring Test Plan	41

Energy Management Operations Metrics	42

EMO1 - Network Security Analysis & Transmission Constraint Management	42

EMO2 - Verify Voltage Support Functionality	42

EMO3 - Verify Outage Evaluation System Functionality	43

EMO6 - QSE Individual LFC Testing	44

EMO7 - Verify Load Forecast Accuracy	44

EMO8 - Conduct EECP Test	46

EMO9(A) – State Estimator Standards Performance Metric	46

EMO9(B) – Real-Time Contingency Analysis Modeling Differences	46

EMO9(C) - Validate Zonal and Nodal Security Analysis Results	47

EMO10 – Monitor Telemetry Quality – Anomalous / Auto-Disabled Telemetered Points	48

EMO12 - Network Operations Model 	52

EMO13 – Operating Personnel and Facilities Readiness	52

Network Model Management Metrics	53

N1 - ERCOT Telemetry Alarm Processing	53

N2 –Telemetry/ICCP System Failover	53

N3 - Validate SE Performance and Accuracy	54

Market Operations Metrics	55

MO3 - Verify Supplemental Ancillary Services Market (SASM)	55

MO4 - Verify SCED Execution Quality	55

MO5 - Generate Real-time LMPs for 6 months	57

MO7 – ERCOT Operating Personnel and Facilities Readiness	57

MO8 - Verify DAM Execution Quality	58

MO9 - Generate Day-Ahead LMPs and Settlement Point Prices	60

M10 – DRUC Execution	61

Contingency Metrics	62

C1 - Contingency Plan for Weekly, Daily and Hourly RUC Failure	62

C2 - Contingency Plan Procuedures for DAM Failure	62

C3 - Contingency Plan procedures for ICCP Data Failure	62

C4 - Contingency Plan procedures for SCED Failure	63

C5 - Contingency Plan procedures for Key Settlement and Financial Transfer Processes	63

C6 - Develop Plan procedures for SE Failure	63

C7 - Contingency Plan procedures for a Backup Facility	64

C8 - Contingency Plan procedures for Portal/API Failure	64

C9 - Contingency Plan procedures for Site Unavailability	64

C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS	65

IMM Metrics	66

IMM1 - Market Monitor Systems Capability	66

Overall Readiness Metrics	67

R0 – Market Participants Operations Readiness	67

R1 - Nodal Readiness Declaration	67

R2 – Develop Texas Nodal Market Launch Plan	67

R3 - 168-Hour System Stability Test and Trial Real Time Settlement	68

# Revision History

| Date | Author | Version Number | Description of Revision |
| --- | --- | --- | --- |
| 8/27/2007 | Chris Wilkinson | 0.91 | Initial Version The intent of this document is to inventory all Texas NODAL Market Readiness Metrics that the NODAL PMO is actively measuring. These metrics have been reviewed and approved by TPTF and TAC. This version picks up where 17a_Metric_Inventory_metric_descriptions_V24.doc left off, which was the last consolidated view of metrics presented to TPTF. Going forward, al TPTF future metrics will be housed in the Future Metric Inventory document. This document is different than 17a_Metric_Inventory_metric_descriptions_V24.doc in that it covers the following active metrics only: - MP1 - MP2 - MP3 - MP5 - MP11 - MP14 - E1 - E6 - E8 - E9 - N1 |
| 8/29/2007 | Chris Wilkinson | 1.0 | Incremented document to V1.0 to reflect TPTF approval of - MP1 - MP2 - MP3 - MP5 - MP11 - MP14 - E1 - E6 - E8 - E9 - N1 |
| 8/31/2007 | Chris Wilkinson | 1.1 | Updated for iteration 3. Moved the following metrics from the Future Inventory to the Active Metric Inventory V1.1. These will be reviewed by TPTF on 9/10/07. - MO5 - N2 - E5 - E3 - EMO9 - N3 - MP6 - MP12 - MO4 |
| 9/5/2007 | Chris Wilkinson | 1.2 | Updated Iteration 3 metrics with feedback from ERT and EDS teams MP6 – Server failover and com link failover measured beginning in October 2007. Remaining three criteria will be measured in January 2008. E3 – Removed MIS Access from Title. Noted RAG Rules – Amber end of October, Red end of November. E5 – Moved back to Future Metric Inventory EMO9 – Removed “Associated Shift Factors” from second metric and noted that the metric will be measured monthly. Zonal does not include shift factors in the constraints. N2 – Corrected spelling on “minutes” in criteria N3 – Added clarification to three metrics that the sample elements were predetermined. Also cleaned up sentence structure to clarify monthly periodicity. MO5 – Noted 50 percent targets between September 2007 and April 2008 to allow for EDS system down-time. |
| 9/18/07 | Chris Wilkinson | 1.3 | Noted that MP12 and E3 were approved by TPTF on 9/11/07 by accepting redlines on those two metrics. Updated MP6 to reflect criteria from most current Texas NODAL Market Telemetry Standard. Edited EMO9 to limit scope to Security Analysis Results Edited N3 to reflect language from Texas NODAL Market State Estimator Standard. Did not change criteria. Added E0 ERCOT Engagement to track ERCOT survey results. Changed criteria of MO5 to reflect 100 percent LMP posting after April 2008. Updated file name to reflect ERCOT.com naming conventions |
| 10/01/07 | Chris Wilkinson | 1.4 | Accepted red-line changes based on TPTF approvals on 9/26/07 for: - MP6 - E3 - EMO9 - N2 - N3 - MO5 - E0 MO4 remains redlined for future consideration. This metric was pended to allow for general conversation around “reasonable LMP” in October. |
| 11/9/07 | Chris Wilkinson | 1.5 | Updates to MO4 to reflect 11/5/07 discussion of LMP reasonability Updated MP11 to Reflect November RARF deadlines. |
| 11/12/07 | Chris Wilkinson | 2.0 | Updated document to include the following metrics. These metrics were approved in November 9, 2009 TPTF session: - E5 - E12 - EMO1 - EMO2 - EMO5 - EMO6 - EMO7 - EMO10 - EMO11 - CRR2 - CRR3 - CRR4 - CRR5 - MO4 |
| 11/28/07 | Chris Wilkinson | 2.1 | TAC approved these metrics on November 28, 2007: - EMO1 - EMO2 - EMO5 - EMO6 - EMO7 - EMO10 - EMO11 - CRR2 - CRR3 - CRR4 - CRR5 - MO4 The following metrics are awaiting TAC approval: - E5 - E12 - MP8 - MP9 - MP10 - MP13 - MP15 - MP17 |
| 12/05/07 | Chris Wilkinson | 2.2 | Added MP11 for TAC approval. MP11 was approved by TPTF on 12/3/07. |
| 12/20/07 | Chris Wilkinson | 2.3 | Added metrics approved by TPTF to Active inventory for TAC approval: MP19 - Load Serving Entities Engagement and Readiness MP16 - MP EDS-4 Trials Participation MP18 - Mapping of Resources and Loads in Private Area Networks is Complete CO1 - Settle Market for 7 Days and Provide Appropriate Extracts CO2 - Verify Dispute Process of 168 Hour Test CO3 - Verify DAM Settlement Statements CO4 - Zonal/Nodal Coordinated Settlement Operations CO5 - Verify RTM Settlement Statements CO6 - Verify RTM Settlement Invoices CO7 - Verify DAM Invoices CO8 - Verify CRR Auction Invoices CO9 - Verify Financial Transfer and Processing CO10 - Verify Credit Calculations EMO12 - Network Operations Model and SE Performance EMO13 - ERCOT Operating Personnel and Facilities Readiness MO7 - ERCOT Operating Personnel and Facilities Readiness |
| 1/7/08 | Chris Wilkinson | 3.0 | Accepted redlines for following metrics based on 1/3/08 TAC approval E5, Nodal SAS 70 Preparedness E12, MIS Compliance Test MP8, QSE Ability to Submit Transactions Via MIS MP9, QSE Ability to Submit Web Service Transactions MP10, Mapping of Resources to Resource Nodes and Resources to EPS Meters is Complete MP11, MP Registration Activities MP13, MP Completes EDS-4 Related Training MP15, MP EDS-3 Participation MP17, MP Qualification Activities MP16 - MP EDS-4 Trials Participation MP18 - Mapping of Resources and Loads in Private Area Networks is Complete MP19 - Load Serving Entitles Engagement and Readiness CO1 - Settle Market for 7 Days and provide appropriate extracts CO2 - Verify Dispute Process of 168 Hour Test CO3 - Verify DAM Settlement Statements CO4 - Zonal/Nodal Coordinated Settlement Operations CO5 - Verify RTM Settlement Statements CO6 - Verify RTM Settlement Invoices CO7 - Verify DAM Invoices CO8 - Verify CRR Auction Invoices CO9 - Verify Financial Transfer and Processing CO10 - Verify Credit Calculations EMO12 - Network Operations Model and SE Performance EMO13 - ERCOT Operating Personnel and Facilities Readiness MO7 - ERCOT Operating Personnel and Facilities Readiness |
| 1/11/08 | Chris Wilkinson | 3.1 | Added Red-lined versions of the following metrics. These were endorsed by TPTF on 1/8/08. ERCOT Internal Metrics E2 - Verify ERCOT Performance Monitoring Test Plan E4 - Transition Pricing Mechanisms E7 - Validate EDW Access and Accuracy of Postings Required by the IMM and PUCT Rules E10 - Validate EDW Commercial Systems Access Accuracy E11 - Validate EDW Compliance Data Access E14 - Verify QSE Performance Monitoring Test Plan E15 - Verify TSP Performance Monitoring Test Plan Energy Management Operations Metrics EMO3 - Verify Outage Evaluation System Functionality EMO8 - Conduct EECP Test Market Operations Metrics MO3 - Verify Supplemental Ancillary Services Market (SASM) Contingency Metrics C1 - Contingency Plan Procedures for Weekly, Daily and Hourly RUC Failure C2 - Contingency Plan Procedures for DAM Failure C3 - Contingency Plan Procedures for ICCP Data Failure C4 - Contingency Plan Procedures for SCED Failure C5 - Contingency Plan Procedures for Key Settlement and Financial Transfer Processes C6 - Develop Plan for SE Failure C7 - Contingency Plan Procedures for a Backup Facility C8 - Contingency Plan Procedures for Portal/API Failure C9 - Contingency Plan Procedures for Site Unavailability C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS IMM Metrics IMM1 - Market Monitor Systems Capability Overall Readiness Metrics R0 - Market Participants Operations Readiness R1 - Nodal Readiness Declaration R2 - Develop Texas Nodal Market Launch Plan |
| 1/31/08 | Chris Wilkinson | 3.2 | Added Red-lined versions of the following metrics. These were endorsed by TPTF on 1/22/08. N4 - Network Modeling Single Entry R3 - 168-Hour System Stability Test and Trial Real Time Settlement Added Red-lined versions of MP14 - MP EDS-2 Trials Participation. This metric was modified by TPTF on 1/22/08. |
| 2/12/08 | Chris Wilkinson | 4.0 | Accepted redlines for following metrics based on 2/7/08 TAC approval: Markey Participant Metrics MP14 - MP EDS-2 Trials Participation Network Model Management Metrics N4 - Network Modeling Single Entry ERCOT Internal Metrics E2 - Verify ERCOT Performance Monitoring Test Plan E4 - Transition Pricing Mechanisms E7 - Validate EDW Access and Accuracy of Postings Required by the IMM and PUCT Rules E10 - Validate EDW Commercial Systems Access Accuracy E11 - Validate EDW Compliance Data Access E14 - Verify QSE Performance Monitoring Test Plan E15 - Verify TSP Performance Monitoring Test Plan Energy Management Operations Metrics EMO3 - Verify Outage Evaluation System Functionality EMO8 - Conduct EECP Test Market Operations Metrics MO3 - Verify Supplemental Ancillary Services Market (SASM) Contingency Metrics C1 - Contingency Plan Procedures for Weekly, Daily and Hourly RUC Failure C2 - Contingency Plan Procedures for DAM Failure C3 - Contingency Plan Procedures for ICCP Data Failure C4 - Contingency Plan Procedures for SCED Failure C5 - Contingency Plan Procedures for Key Settlement and Financial Transfer Processes C6 - Develop Plan for SE Failure C7 - Contingency Plan Procedures for a Backup Facility C8 - Contingency Plan Procedures for Portal/API Failure C9 - Contingency Plan Procedures for Site Unavailability C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS IMM Metrics IMM1 - Market Monitor Systems Capability Overall Readiness Metrics R0 - Market Participants Operations Readiness R1 - Nodal Readiness Declaration R2 - Develop Texas Nodal Market Launch Plan R3 - 168-Hour System Stability Test and Trial Real Time Settlement |
| 2/28/08 | Chris Wilkinson | 4.1 | Updated MP10 and CO2 with changes endorsed by TPTF on 2/21/08. These changes will remain in red-line until approved by TAC. |
| 3/26/08 | Chris Wilkinson | 5.0 | Redlines of MP10 and CO2 approved by TAC on march 6, 2008. |
| 3/27/2008 | Chris Wilkinson | 5.1 | Updated E5 and CO1 with changes endorsed by TPTF in February. These changes will remain in red-line until approved by TAC. |
| 4/4/2008 | Chris Wilkinson | 6.0 | Accepted changes to E5 and CO1 as approved by TAC. Removed references to EMO10 and EMO11. These metrics were approved by TAC as EMO12 and EMO13 and were in this document twice. |
| 4/30/2008 | Chris Wilkinson | 6.1 | Updated metric inventory with the results of metric change control activity at TPTF on April 21, 2008: - Added new metric MP20 MP Ability to Submit Outage – Connectivity Test - Redlined EMO5 Verify ACE Performance - Redlined E8 ERCOT Staffed for Texas NODAL Operations These changes will remain in red-line until approved by TAC. |
| 7/7/2008 | SallyRose Anderson | 7.0 | Accepted changes to E8, EMO5, and MP20 as approved by TAC on May 8th, 2008. Noted that the schedule change will impact the Metric Map and the EDS Timeline Cross Reference. |
| 7/7/2008 | SallyRose Anderson | 7.1 | Updated metric inventory with the results of the July 22nd, 2008 TPTF meeting and subsequent vote: - Added new metric MP21 – Wind Generating Resources ICCP telemetry This addition will remain in red-line until approved by TAC. |
| 8/25/2008 | SallyRose Anderson | 7.2 | Added TPTF approved redlined versions of the following MP metrics: - MP1 - MP6 - MP10 - MP11 - MP12 - MP13 - MP14-A - MP14-B - MP14-C - MP15-A - MP15-B - MP17 - MP19 - MP20 - MP22 Removed the following metrics and placed them in the pmo_completed_metric_inventory for TAC vote and approval: - MP2 - MP3 - MP5 - MP8 - MP9 MP21 remains the same redline as seen in the prior version of this document (v7.1). These modifications will remain in redline until approved by TAC. |
| 9/4/2008 | SallyRose Anderson | 8.0 | Accepted changes to the following metrics, as approved by TAC. These metrics now appear in the Active Metric Inventory in blackline. - MP1 - MP6 - MP10 - MP11 - MP12 - MP13 - MP14-A - MP14-B - MP14-C - MP15-A - MP15-B - MP17 - MP19 - MP20 - MP22 Accepted removal of the following metrics, as approved by TAC. These metrics now appear in the Completed Metric Inventory in blackline. - MP2 - MP3 - MP5 - MP8 - MP9 Rejected insertion of MP21 as TAC did not approve the insertion of this metric. This metric will return to the Working Metric Inventory for TPTF consideration. Above actions were approved by TAC on Thursday, the 4th of September 2008. |
| 9/22/2008 | SallyRose Anderson | 8.1 | Inserted TPTF approved redlined version of MP21, Wind Generation Resources ICCP Telemetry, for TAC review. TPTF approved this version of MP21, along with the newly proposed reporting structure, on September 22, 2008. |
| 10/2/2008 | SallyRose Anderson | 9.0 | Accepted MP21, as approved by TAC on October 2, 2008. MP21 now appears in blackline. |
| 12/03/2009 | Brandon McElfresh | 10.0 | Removed the old EDS Timeline cross reference and the metric map. Updated metric map will be used moving forward. Accepted the removal of MP1, MP10, MP19, and E1. Reactivated MP3 from the completed inventory Updated criteria and made name changes to MP3, MP6, MP8, MP11, MP15B, MP15A, MP20, E1, and E9. Changes reviewed at 12/8/2009 NATF meeting. |
| 1/5/2010 | Brandon McElfresh | 11 | Placed MP14-C and N4 on the completed inventory. Edited MP6, MP11, MO4, and MO5 with design changes. Changes reviewed at 1/5/2010 NATF meeting. |
| 1/12/2010 | Brandon McElfresh | 11.1 | Grayed out all of the metrics that are currently in design at ERCOT and not yet reviewed at NATF. |
| 1/13/2010 | Brandon McElfresh | 11.2 | Corrected MP11 language to be only applicable to Resource Entities. |
| 2/3/2010 | Brandon McElfresh | 12.2 | Edited MP6, MP15-A, MP20 with design changes. Changes reviewed at 2/2/2010 NATF meeting. |
| 2/16/2010 | Brandon McElfresh | 13.2 | Final language for MP14-C. Edits reviewed at 2/15/2010 NDSWG meeting. |
| 3/2/2010 | Brandon McElfresh | 14.2 | Final language for CRR3, CRR5, MP16, MO4, and MO5. Placed MP12 and MP13 on the removed inventory. Both changes reviewed by NATF on 3/2/2010. |
| 4/6/2010 | Brandon McElfresh | 15.2 | Updated language for MP16, CRR3, N2, EMO6, and CO8. Changes reviewed at the 4/6/2010 NATF meeting. |
| 4/14/2010 | Brandon McElfresh | 15.3 | Updated typos in MP16 Metric. Rag Rules for individual MPs was incorrect |
| 5/3/2010 | Brandon McElfresh | 16.1 | Added MO8, MO9, MO10 (placeholder), EMO9(A-C), EMO10, MO8-10, and MP23 (placeholder), E10 (placeholder). Removed EMO5 because of TPTF approval on 4/21/2008 meeting. Changes reviewed at 5/4 NATF meeting. |
| 6/1/2010 | Brandon McElfresh | 17.1 | Added MP21, MP22, CO10. Changes will be removed at 6/1/2010 NATF meeting. |

# Introduction

The Readiness Metric Inventory is a detailed report of all readiness metrics. The following table outlines the information provided per metric. The intent of this document is to inventory all Texas NODAL Market Readiness Metrics that the NODAL PMO is actively measuring. These metrics have been reviewed by TPTF and TAC and will be governed by a change control process going forward once approved.

Metric Number – Metric Name

| Reported By: Indicates if the metric is discoverable by ERCOT, Market Participants, WEMM or any combination thereof. |  |  | EDS: Indicates the related Early Delivery System, if applicable. |
| --- | --- | --- | --- |
| Target Completion: Indicates the time period that the metric result will be published. |  |  |  |
| Category: Indicates how the data will roll up functionally in the Readiness Dashboard tool. |  |  |  |
| Metric Description: Provides a description of the metric. |  |  |  |
| Background: Indicates the intent of the metric. |  |  |  |
| Criteria: Outlines the criteria used to determine if the metric has been successfully completed. Provides a concrete measurement standard to evaluate the metric against |  |  |  |
| Reporting Data Sources: Indicates the source of the data to be used when evaluating the measurement standard and or the individual or team responsible for reporting status. |  |  |  |
| References | TP: Cross reference to the Transition Plan | TNP: Cross reference to the Texas Nodal Protocols |  |

# Market Participant Metrics

### MP3 – Market Submissions Connectivity Qualification

| Reported By: QSEs with Resources, QSEs without Resources, ERCOT |  |  | Phase: 2.1 |
| --- | --- | --- | --- |
| Target Completion: January 29, 2010 |  |  |  |
| Category: Connectivity |  |  |  |
| Metric Description: QSEs with Resources shall demonstrate their ability to successfully submit Real-Time Market transactions and all QSEs shall demonstrate their ability to successfully submit Day-Ahead Market transactions to the MIS and/or an External Web Service in the Market Trials environment and successfully pass validation with the MMS system. |  |  |  |
| MP Criteria: Criteria will be met when the market participant can demonstrate the ability to submit the following applicable transactions: Real-Time Market Transactions: - Current Operating Plan - Energy Offer Curve - Output Schedules - Incremental/Decremental Offer Curves Day-Ahead Market Transactions - Three Part Offers - Ancillary Service Offers - Energy-only Offers and Bids - Trades (Energy, Ancillary Services, Capacity) - Self-Arranged Ancillary Services - CRR Offers - PTP Obligation Bids - Self Schedules - DC Tie Schedules - Resource Parameters RAG Rules Red – Submissions not complete, participation not adequate Amber – Incomplete Submissions, but actively working with ERCOT Green – Submissions complete RAG Rules – Market Segment Red – over 5% of market share not meeting criteria Amber – any alternative scenario Green – over 95% of market share meeting criteria ERCOT Criteria: ERCOT scores in connectivity will mirror the Market Participant MP3 scores. The Lowest common denominator between QSERs and QSEs will be adopted as the ERCOT score. |  |  |  |
| Reporting Data Sources: Dashboard reported by Market Trials team (MMS database query) |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP6 – Telemetry Compliance with the Nodal Protocols 3.10.7.5

| Reported By: QSER, TSP |  |  | Phase: 2.1, 3, 4, 5 |
| --- | --- | --- | --- |
| Target Completion: May 31, 2010 |  |  |  |
| Metric Description: ERCOT will verify with TSPs and QSEs with Resources that all required Nodal ICCP telemetry is provided and readable by ERCOT Nodal systems and that Market Participant telemetry systems are compliant with Nodal Protocols section 3.10.7.5. |  |  |  |
| Category: Real-Time Market (RTM) |  |  |  |
| Criteria: Criteria will be met when QSEs with Resources and TSPs demonstrate that all Nodal telemetry expected for State Estimator and SCED solutions is being sent to ERCOT. The Nodal Scorecard will be updated after each EMS Database Load. See http://www.ercot.com/gridinfo/transmission/opsys-change-schedule for the EMS Database Load schedule. QSERs – State Estimator (SE) scores will be released in December 2009 and Security Constrained Economic Dispatch (SCED) scores will be released in January 2010. TSPs – All ICCP as required per the ICCP Communication Handbook required. Scores will be released in May 2010. A single scoring system will be applied to both the SE and SCED indicators, as follows: - Score Calculation: % = [1 - (a / (a + b))]*100 Where: a = qty of nodal points missing for SE or SCED b = qty of nodal points provided for SE or SCED Example: Qty of Nodal points missing for SE 5 Qty of Nodal points provided for SE 25 SE score = [1 - (5 / (5+25)]*100 = 83% SE Score Evaluation Amber \ For Market Participants Red – < 80% of expected telemetry points sent by MP Amber – >= 80% and < 98% of expected telemetry points sent by MP Green – >= 98%% of expected telemetry points sent by MP For Market Segment Red – over 5% of market share not meeting criteria Amber – any alternative scenario Green – over 95% of market share meeting criteria |  |  |  |
| Reporting Data Sources: State Estimator Reports |  |  |  |
| References | TP: 5.4.1 (2)(k), 5.4.1 (2)(a) | TNP: 3.10.7.5 |  |

### MP11 – MP Resource Registration

| Reported By: RE |  |  |  |
| --- | --- | --- | --- |
| Target Completion: April 1, 2010 |  |  |  |
| Category: Registration and Qualification |  |  |  |
| Metric Description: This metric shall measure whether Resource Entities have completed the resource registration activities required for the Nodal program. |  |  |  |
| Criteria: MP Readiness will be achieved when the MP has completed the required resource registration activities including: - Transmission Asset Registration 11/16/2009 – 12/1/2009 - RARF True-up: Resource Entities complete schedule RARF submittals with updated business rule validations 2/2/2010 – 4/1/2010 - Resource Entities complete refresh of declaration of Resource Decision Making Authority for each network modeled Generation Resource 12/7/2009 – 1/8/2010, all corrections in by 1/29/2010 - Resource Entities sign-off on verification of Resource Node and Meter Mapping 1/18/2009 – 4/1/2010. Each RE has 10 business days to complete verification. RAG Rules – MPs Red – No submittals have been received according to schedule and/or not responding to escalation calls after the target completion date. Amber – Demonstrating progress in making corrections after target completion date. Score will change to RED after 30-days past target completion date if no corrections are received. Green – All forms received and accepted RAG Rules – Market Segment - Red – over 5% of registered megawatt capacity not meeting criteria Amber – any alternative scenario Green – over 95% of registered megawatt capacity meeting criteria |  |  |  |
| - Reporting Data Sources: Wholesale Client Services |  |  |  |
| - References | - TP: N/A | - TNP: 16.2 thru 16.8 & 3.7.1 & 3.10 |  |

### MP14 – A – MP EDS-2, Release 3 Trials Participation

| Reported By: QSER, TSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: October 31, 2008 |  |  |  |
| Category: Trials Participation |  |  |  |
| Metric Description: This metric evaluates the level of TSP and QSE market participant participation in the EDS 2, Release 3 Trials. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants have the ability to access Telemetry and State Estimator performance reports. |  |  |  |
| Criteria: The Readiness Team will review documentation that an adequate number of MPs within QSER and TSP market segments have reviewed performance reports pertaining to the TAC approved Telemetry and State Estimator Criteria, on MIS and confirmed ability to access those reports. # of TSP and QSE MPs Participating in Trial >=95% of TSP and QSE MPs intending to participate in Nodal Market # of TSP and QSER MPs Participating in Trial accessing Telemetry SE Performance Report >= 75% RAG Rules - MPs Red - Not participating in trials Amber – not applicable Green – Meeting criteria RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: Self-Reported |  |  |  |
| References | TP: 5.4.1 | TNP: 3.10.8, 3.3.2.1, 3.10.7 |  |

### MP14–C – TSP Model Validation

| Reported By: TSP |  |  |  |
| --- | --- | --- | --- |
| Target Completion: April 1, 2010 |  |  |  |
| Category: Network Model |  |  |  |
| Metric Description: - Per the approved SEM Go-Live Procedure, after SEM Go-Live on August 31, 2009, ERCOT shall ensure that TSPs have sufficient time “to synchronize the Nodal Network Operations Model with the TSP’s native model databases, before transitioning to relevant sub-sections of the Nodal Protocol § 3. The duration of the transition period, as defined in the Texas Nodal Market Program schedule, will be mutually agreed upon by ERCOT and TSPs.” The date reflected in the program schedule was 6-months, from Aug 31, 2009 through Feb 28, 2010. - Per Protocols Section 3.10.4(7) of Protocols, “A TSP, with ERCOT’s assistance, shall validate its portion of the Network Operations Model”. |  |  |  |
| - Criteria: Validation of the data used for the Network Operations Model will be based on the TSP’s best practices and should align with the following protocol sections: - Nodal Protocol § 3.10.7.1 (1) - Nodal Protocol § 3.10.7.1.1 - Nodal Protocol § 3.10.7.1.2 - Nodal Protocol § 3.10.7.1.3 - Nodal Protocol § 3.10.7.1.4 - Nodal Protocol § 3.10.7.1.5 - Nodal Protocol § 3.10.7.2 (4) - Nodal Protocol § 3.10.7.2 (7) - Nodal Protocol § 3.10.4 (7) - Upon completion of the validation process, each TSP Accountable Executive shall notify ERCOT via email that their validation efforts are complete. RAG Rules - MPs Red – Not compliant by April 1, 2010 Amber – Not compliant by March 1, 2010 Green – Compliant by March 1, 2010 RAG Rules – Market Segment (weighted by equipment ownership share) Red – Less than or equal to 80% Amber – Between 80-95% Green – 95+% meeting criteria |  |  |  |
| Reporting Data Sources: Self-Reported |  |  |  |
| References | TP: 5.4.1 | TNP: see above |  |

### MP15–A – Real-Time Market Participation

| Reported By: QSER |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test |  |  |  |
| Metric Description: This metric evaluates the level of QSE market participant participation in Real-Time SCED submissions. |  |  |  |
| Criteria: Ensure active participation in SCED through monitoring of Energy Offer Curves and Output Schedule submissions. Weekly average of daily submissions of Offer Curves and Output Schedule >= 95% For Market Participants Meeting criteria = Green Within 10% of meeting criteria = Amber Not meeting criteria = Red For Market Segment Red – over 5% of market share not meeting criteria Amber – any alternative scenario Green – over 95% of market share meeting criteria |  |  |  |
| Reporting Data Sources: Market Trials Real-Time Market Lead |  |  |  |
| References | TP: 5.4.8 | TNP: 6.4.4, 6.5.7.1.12, 6.5.7.1.13 |  |

### MP15(B) – CRR Connectivity Qualification

| Reported By: CRR Account Holder, ERCOT |  |  |  |
| --- | --- | --- | --- |
| Target Completion: January 29, 2010 |  |  |  |
| Metric Description: This metric evaluates CRRAH connectivity qualification to participate in the CRR monthly and annual auctions. |  |  |  |
| Criteria: Criteria will be met when the market participant can demonstrate the ability to submit/complete the following applicable transactions during CRR connectivity qualification. - Logged-in and accessed the CRR application - Downloaded one of the pre-auction market information - Uploaded a bid/offer portfolio (in either XML or CSV) - Edited a bid/offer within a portfolio (confirms web browser supports java applets) - Created a sell/buy bilateral trade posting - Accepted a sell bilateral trade posting RAG Rules Red – Submissions not complete, participation not adequate Amber – Incomplete Submissions, but actively working with ERCOT Green – Submissions complete RAG Rules – Market Segment Red – over 5% of market average not meeting criteria Amber – any alternative scenario Green – over 95% of market average meeting criteria ERCOT Criteria: ERCOT scores in connectivity will mirror the Market Participant MP15(B) scores. |  |  |  |
| Reporting Data Sources: Dashboard posted on Readiness Center by CRR Market Trials team |  |  |  |
| References | TP: 5.4.8 | TNP: 6.4.4, 6.5.7.1.12, 6.5.7.1.13 |  |

### MP16 – Day-Ahead Market Participation

| Reported By: QSERs, QSEs, & ERCOT |  |  | Phase: 4, 5 |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test |  |  |  |
| Metric Description: This metric evaluates the level of market participant participation in executing the Day—Ahead Market leading up to the 168 Hour Test. |  |  |  |
| Criteria: Each QSE participates in at least 50% of the scheduled DAM executions by successfully submitting the relevant transactions as tracked on the DAM Participation Dashboard. Participation, for the purposes of this metric, is defined as the submission of DAM specific transactions (bids, offers, or AS self-arrangements). This does not include submission of COPs or Energy Offer Curves, which are measured in MP15-A Real-Time Market Participation. RAG Rules Red – Participation in < 25% of DAM Executions Amber – Participation in >= 25% and < 50% of DAM Executions Green – Participation in >= 50% of DAM Executions in Green - QSEs with Load participating in Phase 4 to 168 Hour Test - Day-Ahead Market testing represent >= 80% of the load intending to participate in Nodal Market RAG Rules – Market Segment (Load) Red - < 50% of load participating Amber - >= 50% and < 80% of load participating Green - QSEs with Resources participating in Phase 4 to 168 Hour Test – Day-Ahead Market testing represent >= 80% of the generation intending to participate in Nodal Market RAG Rules – Market Segment (Generation) Red - < 50% of generation participating Amber - >= 50% and < 80% of generation participating Green - QSEs without Resources and/or Load participating in Phase 4 to 168 Hour Test – Day-Ahead Market testing represent >= 80% of the QSEs w/o Resources intending to participate in Nodal Market RAG Rules – Market Segment (Even weighting) Red - < 50% of QSEs w/o Resources participating Amber - >= 50% and < 80% of QSEs w/o Resources participating PLEASE NOTE: All DAM participation scores will be based on a rolling two week average beginning on the 5/5/2010 Nodal Scorecard update. At a minimum, there will be four DAM runs and a maximum of 10 DAM runs in this rolling average throughout the rest of Market Trials. |  |  |  |
| Reporting Data Sources: Day-Ahead Market Trials PM |  |  |  |
| References | TP: 5.4.1 | TNP: 3.9, 3.16-18, 9.2.7-8 |  |

### MP17 – MP Qualification Activities

| Reported By: QSER, QSE, CRRAHs |  |  |  |
| --- | --- | --- | --- |
| Target Completion: Go-Live |  |  |  |
| Metric Description: This metric will measure the completion of specified qualification requirements to support 168-Hour Test Activities and participate in the NODAL market. This metric is not intended to be used for final qualification of Market Participants to participate in Nodal. Final determination for Nodal Go-Live will be measured in the Readiness Metrics R0 “Market Participant Nodal Readiness Declaration” and R1 “ERCOT Nodal Readiness Declaration.” |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that market participants are qualified to engage in the market. Market Participants must meet the following metrics to be qualified (GREEN) for MP17. If any of the metrics that apply to the specific Market Participants are AMBER or RED, MP17 will be scored using the lowest common score. This metric will be reported on a bi-weekly basis starting on July X, 2010. Prior to the 168 hour test QSEs with Resources (QSERs) - MP3 Market Submissions Connectivity Qualification * - MP6 Telemetry Compliance with Nodal Protocols 3.10.7.5 - MP15-A Real-Time Market Daily Participation * - MP16 DAM Participation - MP18 Mapping of Resources and Loads in Private Use Networks - MP23 Telemetry Quality (MP to ICCP Server) - N2 Telemetry/ICCP System Failover - EMO3 Individual LFC Tests QSEs without Resources (QSEs) - MP3 Market Submissions Connectivity Qualification * - MP16 DAM Participation CRR Account Holders (CRRAHs) - MP15-B CRR Connectivity Qualification * - CRR3 Operation of CRR Auctions and Allocations * Market Participants must meet these metrics to meet entry criteria for the 168 hour test. For all other metrics that cause an MP17 score of AMBER or RED, ERCOT will make a determination as to whether the Market Participant is qualified for the 168-hour test and the cutover/go-live sequence. After the 168 hour test Market Participants who have an AMBER or RED score for MP17 will continue to be reported as such until the issues causing the metric to be AMBER or RED are resolved. The metric “R3 - 168-Hour System Stability Test and Trial Real Time Settlement,” which is intended to measure whether ERCOT and MPs have met the exit criteria for the 168 hour test, will be added to MP17 after the 168 hour test is complete. Please note that the exit criteria for the 168 hour test is still in design and will be discussed at the June, July, and August NATF meetings. For auditing purposes, ERCOT will use the results of MP17 in an overall Nodal Qualification checklist for each Market Participant. This qualification checklist will be used by ERCOT, the ERCOT Board of Directors, the Technical Advisory Committee, and the Public Utility Commission of Texas when they fulfill the criteria of R0 “Market Participant Nodal Readiness Declaration” and R1 “ERCOT Nodal Readiness Declaration” metrics. MP RAG Rules Green = MP17 Metric met Amber = Working with ERCOT to resolve issues Red = Not responsive Market Segment Rules (QSERs) Green = >= 95% Generation meeting criteria Amber = < 95% and >= 90% Generation meeting criteria Red = < 90% Generation meeting criteria Market Segment Rules (QSEs, CRRAHs) Green = >= 95% meeting criteria Amber = < 95% and >= 90% meeting criteria Red = < 90% meeting criteria |  |  |  |
| Reporting Data Sources: Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.1, 16.2 |  |

### MP18 – Mapping of Resources and Loads in Private Area Networks

| Reported By: TSPs & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Start Go Live Activities less 120 days |  |  |  |
| Metric Description: ERCOT shall ensure that all Private Use Networks in the TN Market have completed their mapping of any generation and loads necessary for go live operation. |  |  |  |
| Background: It is the intent of this metric to ensure that Private Use Networks are modeled as specified by the Nodal Protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that all Private Use Networks in the TN Market have accurately modeled in the Network Operations Model. Readiness will be achieved when each Private Use Network has either mapped their generation and load or have accepted the existing default configuration. Generation and Load Mapping = 100% RAG Rules – Market Segment Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: Extract from Registration / ERCOT Manager of Wholesale Client Services |  |  |  |
| References | TP: N/A | TNP: 16.2.3.2(2) |  |

### MP20 – Outage Scheduler Connectivity Qualification

| Reported By: QSER, TSP |  |  | Phase: 3 |
| --- | --- | --- | --- |
| Target Completion: Phase 3 completion |  |  |  |
| Metric Description: This metric evaluates the ability of a Market Participant to complete Outage Schedule connectivity qualification. |  |  |  |
| Criteria: During Market Trials Phase 3.0, Market Participants will perform OS connectivity and qualification activities. RAG Rules Red – Submissions not complete, participation not adequate Amber – Incomplete Submissions, but actively working with ERCOT Green – Submissions complete RAG Rules – Market Segment Red – over 5% of market share not meeting criteria Amber – any alternative scenario Green – over 95% of market share meeting criteria |  |  |  |
| Reporting Data Sources: Market Trials team (Outage Scheduler Database Query) |  |  |  |
| References | TP: 5.4.1. 5.4.10 | TNP: 3.1 |  |

### MP21 – Wind Generation Resources ICCP Meteorological Telemetry

| Reported By: REs (WGRs) |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test |  |  |  |
| Category: Network Model |  |  |  |
| Metric Description: The intent of this metric is to ensure that Wind-powered Generation Resources (WGR) are providing to ERCOT through their selected QSE the required meteorological telemetry to meet nodal protocols contained in Sections 3.13 Renewable Production Potential Forecasts and Section 4.2.2 Wind-Powered Generation Resource Production Potential. This meteorological telemetry must be submitted in the NProd environment as described in the Nodal ICCP Communication Handbook. The specific telemetry meteorological information that is required from Wind-powered Generation Resources consists of the following: - Wind Speed (mph); - Wind Direction (degrees); - Temperature (Celsius); and - Barometric Pressure (mbar) |  |  |  |
| Criteria: The Supply Integration and Grid Application team performs a validation of meteorological data every two to three weeks. Each validation reviews the last 14 days of 10-second data for each measured value (temperature, barometric pressure, wind speed, and wind direction). The validation performs the following reasonability tests: - Is the range of the data reasonable? Is the data in the correct units of measure? - Is the data dynamic (or does it stay static for significant periods of time)? - Is the data free of large, sudden drops or spikes in value? - Does the wind speed line up with the power production (excluding curtailment periods)? Wind-powered Generation Resources will be measured on whether they have submitted meteorological data and whether the data passed the reasonability tests described above. RAG Rules (Wind-powered Generation Resources) Red – Submissions not complete, participation not adequate Amber – Incomplete Submissions, but actively working with ERCOT Green – Submissions complete RAG Rules (Wind Generation Resources – Market Segment) Red – over 5% of registered megawatt capacity not meeting criteria Amber – any alternative scenario Green – over 95% of registered megawatt capacity meeting criteria PLEASE NOTE: All MP21 telemetry scores will be updated on the Nodal Readiness Scorecard semi-monthly based on the newest 14 day validation check. |  |  |  |
| Reporting Data Sources: PI database in Market Trials / Market Trials Real-Time team |  |  |  |
| References | TP: N/A | TNP: 3.13 & 4.2.2 |  |

### MP22 – New Entrant Readiness

| Reported By: QSERs, QSEs, CRRAHs |  |  | Phase: N/A |
| --- | --- | --- | --- |
| Target Completion: Go-Live |  |  |  |
| Category: Readiness |  |  |  |
| Metric Description: The New Entrant metric is meant for QSEs and CRRAHs that attempt to qualify for the Nodal Market between the 168 hour test and before Nodal Go-Live. For a period beginning with the start of the Go-Live Sequence through 15 (fifteen) days after the Nodal Go-Live, ERCOT will not distribute Production Certificates to new QSEs or CRRAHs. |  |  |  |
| Criteria: New QSEs and CRRAHs must meet the following requirements in order to be qualify as a New Entrant into the Nodal Market: Registration must begin by these dates to be qualified for Nodal Go-Live - August 13th, 2010 - QSEs with Resources with a new WAN connection * - CRRAHs (to be qualified for the 10/13 PCRR nomination and for the 11/11 December 2010 CRR Auction) * ~ - October 1st, 2010 - QSE with Resources using a Nodal qualified service provider * - QSEs without Resources * - Sub-QSEs using a Nodal qualified parent QSE * Qualification will follow the Nodal production qualification process and all testing will be done in the MOTE environment * QSE Application or CRRAH Application must be submitted, which includes Credit Application ~ Doesn’t include NOIE Allocation Eligibility Form, which must be submitted by 6/30 for CRRAHs eligible for PCRRs ##### For New Entrant Market Participants Meeting Criteria = Green Failing to Meet Criteria registration start deadline = Amber Failing to Meet registration start deadline by 15 Calendar Days or more = Red |  |  |  |
| Reporting Data Sources: Production PMs |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP23 – Telemetry Quality (MP to ICCP Server)

| Reported By: TSPs, QSERs |  |  |  |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test |  |  |  |
| Category: Registration and Qualification |  |  |  |
| Metric Description: Placeholder |  |  |  |
| Criteria: Criteria will be met when QSEs with Resources and TSPs demonstrate that all Nodal telemetry submitted to ERCOT ICCP server consistently meet expected quality requirements. The Nodal Scorecard will be updated after each EMS Database Load. See http://www.ercot.com/gridinfo/transmission/opsys-change-schedule for the EMS Database Load schedule. QSERs – To be determined TSPs – To be determined A single scoring system will be applied to both QSERs and TSPs, as follows: - Score Calculation: % = [1 - (a / (b)]*100 Where: a = qty of suspect/bad nodal points b = qty of total nodal points For Market Participants Red – < 90% of expected telemetry points sent by MP Amber – >= 90% and < 98% of expected telemetry points sent by MP Green – 98% of expected telemetry points sent by MP For Market Segment Red – over 5% of market share not meeting criteria Amber – any alternative scenario Green – over 95% of market share meeting criteria |  |  |  |
| Reporting Data Sources: Placeholder |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### Commercial Operations Metrics

### CO1 - Settle Market for 7 Days and provide appropriate extracts

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: ERCOT will issue to eligible market participants test DAM settlement statements, test RTM settlement statements, test DAM settlement invoice(s), and test RTM settlement invoice(s) and provide appropriate extracts for consecutive 7 Operating Days consistent. |  |  |  |
| Background: The intent of this metric is to prove ERCOT's ability to settle the DAM and the RTM for 7 consecutive days and determine acceptance by QSEs and CRR Account Holders. |  |  |  |
| Criteria: The Readiness Team will confirm settlement statements and invoices and confirm appropriate extracts were posted and available for download for each eligible market participant for the seven day period. Readiness will be met when QSEs accept the posting of the seven settlement statements and the weekly invoice The Readiness Team will poll the QSEs to obtain their acceptance. Posted Statements: QSE Statements for DAM (7 Initial and one resettlement) for each eligible MP = 8 QSE Statements for RTM (7 Initial and one resettlement) for each eligible MP = 8 QSE Invoices for DAM for each eligible MP = 7 QSE Invoices for RTM for each eligible MP = 1 CRR Invoices for DAM for each eligible MP = 7 CRR Invoices for RTM for each eligible MP = 1 AND Number of QSEs who accept the Test Settlement and Invoice statements > 99% |  |  |  |
| Reporting Data Sources: MIS Posted Settlement Statements and Invoices / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.6 (4), 6.1(g) | TNP: |  |

### CO2 - Verify Dispute Process

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: ERCOT shall provide settlement dispute resolution service for all MPs submitting a dispute. The dispute resolution metric is dependent upon Market Participants ability to receive statements, invoices and data extracts and submit disputes via the MIS. |  |  |  |
| Background: The intent of this metric is to ensure that dispute management process is functioning, allowing for Market Participants to log and ERCOT to facilitate the resolution of disputes. ERCOT will select several Market Participants to verify dispute creation process. |  |  |  |
| Criteria: The Readiness Team will review documentation that settlements disputes have been addressed in accordance with ERCOT's dispute resolution process. The Readiness Team will evaluate that the settlement dispute process can process a dispute through to resolution. These disputes are tests of the dispute process and are not considered in ERCOT’s ZONAL dispute system. # of unprocessed Disputes that were logged during EDS4.9 = 0 Invoice and settlement disputes logged ≥ 1 per QSE and CRR Account Holder Completed Simulated Dispute within Dispute Tracking System >=10 |  |  |  |
| Reporting Data Sources: Publicly Posted Dispute Process / 168 Hour Test Dispute Tracking Log/Tool / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.9 (2) | TNP: |  |

### CO3 - Verify DAM Settlement Statements

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Major Milestone plus 30 days |  |  |  |
| Metric Description: ERCOT will test DAM settlement statements by independent calculation and verify appropriate statement posting to the MIS. |  |  |  |
| Background: The intent of this metric to verify the accuracy and appropriate posting of Day Ahead Settlement Statements. Day Ahead settlements use Day Ahead Settlement Point Prices (DASPP) that are calculated for Resource Nodes, Load Zones, and Hubs. |  |  |  |
| Criteria: The Readiness Team will confirm that the DAM settlement calculations were validated and statements posted for each eligible participant. The validation will be accomplished by comparing Day Ahead Settlement Statements generated by the system to calculations independently generated using common input data. A statement sampling representing all applicable charge types shall be used. Readiness will be met when the dollar difference between the system generated Day Ahead Settlement Statement and the independently generated calculations equals zero for the sample set. Readiness will be met when all Day Ahead Settlemement Statements are posted in the appropriate area of the MIS. For the sample set: System Generated DA Statement Dollars - Independently Generated DA Calculation Dollars =$0 System Generated DA Statements not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated DA Statements/ DA Settlement Determinants / Independently Generated DA Calculations / ERCOT EDS 4 PM |  |  |  |
| - References | - TP: 5.4.7 (3) | - TNP: |  |

### CO4 - Zonal/Nodal Coordinated Settlement Operations

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS 4 168 Hour Test Major Milestone |  |  |  |
| Metric Description: ERCOT shall run both Zonal and Nodal settlement processes in a coordinated manner. (Note: Only the Zonal statements will be binding until Nodal Go Live; then Nodal Statements will be binding; For any given Operating Day, only one of the two settlement process will be binding) |  |  |  |
| Background: The intent of this metric is to ensure ERCOT's ability to process settlements for both Zonal and Nodal markets for the period where Zonal and Nodal market settlement will overlap. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that Zonal and nodal coordinated settlements have been implemented prior to Texas Nodal Market Go Live. Readiness will be met when statements have been produced for both Nodal and Zonal at the threshold defined below. During a planned 24 hour period: Zonal Settlements Run >=3 and Nodal Settlements Run >= 3 Zonal/Nodal Settlements Process(es) documented to support >= 6 Settlement Runs |  |  |  |
| Reporting Data Sources: Settlement Statement Completion Statistics from Job Scheduler for Zonal and Nodal Settlements Runs / ERCOT EDS 4 PM |  |  |  |
| References | TP: 6.1 (j) | TNP: |  |

### CO5 - Verify RTM Settlement Statements

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 8 complete plus 14 days |  |  |  |
| Metric Description: ERCOT will test RTM Settlement Statements by independent calculation and verification of the appropriate posting to the MIS. |  |  |  |
| Background: The intent of this metric is to verify the accuracy and appropriate posting of RTM Settlement Statements. |  |  |  |
| Criteria: The Readiness Team will confirm that the RTM settlement calculations were validated and statements posted for each eligible participant. The validation will be accomplished by comparing Real Time Settlement Statements generated by the system to calculations independently generated using common input data. A statement sampling representing all applicable charge types and at least 25 percent of QSEs planning to participate in the NODAL market shall be used. Readiness will be met when the dollar difference between the system generated Real Time Settlement Statement and the independently generated calculations equals zero for the sample set. Readiness will be met when all Real Time Settlemement Statements are posted in the appropriate area of the MIS. For the sample set: System Generated RT Statement Dollars- Independently Generated RT Calculation Dollars =$0 System Generated RT Statements not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated RT Statements/ RT Settlement Determinants/ Independently Generated RT Calculations / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.7 (3) | TNP: |  |

### CO6 - Verify RTM Settlement Invoices

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 8 complete plus 14 days |  |  |  |
| Metric Description: ERCOT will test RTM Settlement Invoices by independent calculation and verification of the appropriate posting to the MIS. |  |  |  |
| Background: The intent of this metric is to verify the accuracy and appropriate posting of Real Time Market Settlement Invoices. |  |  |  |
| Criteria: The Readiness Team will review documentation and data that verifies that the RTM Settlement invoices were issued according to ERCOT processes and that calculations summing distinct statements are correct. An invoice sampling of all applicable charge types and 100 percent of QSEs planning to participate in the NODAL market shall be used. (Sample set from CO5 may be used). Readiness will be met when the dollar difference between the system generated Real Time Settlement Invoice and the one independently generated calculations equals zero for the sample set. Readiness will be met when all RTM Settlement Invoices are posted in the appropriate area of the MIS. For the sample set: System Generated RT Invoice Dollars - Independently Generated RT Calculation Dollars = $0 System Generated RT Invoices not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated RTM Invoices/ System Generated RTM Statements/ Independently Generated RT Calculations / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: |  |

### CO7 - Verify DAM Invoices

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Major Milestone plus 30 days |  |  |  |
| Metric Description: ERCOT will test DAM settlement section of the invoices by independent calculation and verification of the appropriate posting to the MIS. |  |  |  |
| Background: The intent of this metric is to verify the accuracy and appropriate posting of DAM Settlement Invoices. |  |  |  |
| Criteria: The Readiness Team will review documentation and data that verifies that the DAM Settlement invoices were issued according to ERCOT processes and that calculations summing distinct statements are correct. An invoice sampling of all applicable charge types and 100 percent of QSEs planning to participate in the NODAL market shall be used. (Sample set from CO3 may be used). Readiness will be met when the dollar difference between the system generated Day Ahead Settlement Invoice and the one independently generated equals zero for the sample set. Readiness will be met when verified DAM Invoices are posted in the appropriate area of the MIS. For each invoice in the sample: System Generated DAM Invoice Dollars - Independently Generated DAM Invoice Dollars = $0 System Generated DAM Invoices not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated DAM Invoices/ System Generated DA Statements / Independently Generated DAM Calculations / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: |  |

### CO8 - Verify CRR Auction Invoices

| Reported By: ERCOT |  |  | - Phase: 4,5 |
| --- | --- | --- | --- |
| Target Completion: Phase 5 completion |  |  |  |
| Metric Description: ERCOT will test CRR Auction invoices by independent calculation and verify appropriate posting to the MIS. |  |  |  |
| Criteria: The Readiness Team will verify that the CRR Auction Invoices were generated for the eligible CRR Account Holders accordingly to ERCOT processes. The Readiness Team will review documentation that ERCOT has verified the CRR Auction Invoices are consistent with the CRR Auction results. An invoice sampling of at least 25 percent of QSEs planning to participate in the NODAL market shall be used. CRR Auction Invoices will be posted for each eligible CRR Account Holder. Readiness will be met when the dollar difference between the CRR Auction Results and the CRR Auction Invoice equals zero. Readiness will be met when all CRR Auction Invoices are posted in the appropriate area of the MIS. CRR Auction Result for MPn - CRR Auction Invoice for MPn = $0 - These may not be one to one System Generated CRR Auction Invoices not posted = 0 |  |  |  |
| Reporting Data Sources: CRR Auction Results / CRR Auction Invoices / CRR Market Trials team |  |  |  |
| References | TP: N/A | TNP: |  |

### CO9 - Verify Financial Transfer and Processing

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Major Milestone |  |  |  |
| Metric Description: ERCOT will perform a "Penny Test" with newly registered market participants. |  |  |  |
| Background: The intent of this metric is to verify that the financial transfer process is functioning between ERCOT and newly registered Market Participants. |  |  |  |
| Criteria: The Readiness Team will review the results of the "Penny Test" to confirm that ERCOT can transfer funds to Registered Market Participants and that Market Participants can transfer funds to ERCOT. Readiness will be met when $0.01 has been successfully transferred from ERCOT to each newly registered Market Participant. Readiness will be met when $0.01 has been successfully transferred from newly registered Market Participant to each ERCOT. Number of unsuccessful transfers to registered MPs = 0 Number of unsuccessful transfers to ERCOT = 0 |  |  |  |
| Reporting Data Sources: Results of the Penny Test / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### CO10 - Verify Credit Calculations

| Reported By: ERCOT |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: 168-Hour Test |  |  |  |
| Metric Description: ERCOT will calculate and monitor the available credit limit of market participants. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the Credit Management and Monitoring system has been tested successfully prior to Texas Nodal Market Launch. The Readiness Team will review documentation that verifies ERCOT and Market Participants have tested the Credit Monitoring & Management (CMM) and ensured it is able to; calculate credit score, record and track collaterals, track late payments, and send available credit limits to the CRR, MMS and MIS systems during Market Trials testing. Readiness will be met when ERCOT has verified available credit limit test results with market participants and performed a detailed validation using a statistical sample of Market Participants’ credit limits. <= 25% of Market Participants’ available credit limits were reported by Market Participants and confirmed by ERCOT to be inconsistent with Nodal Protocols ERCOT performs and validates credit calculations for a statistical sample of Market Participants |  |  |  |
| Reporting Data Sources: CMM Database / MIS / Market Trials Credit Project Manager |  |  |  |
| References | TP: 6.1 (l) | TNP: 16.11 & 4.4.10 |  |

# Congestion Revenue Rights Metrics

### CRR2 - Develop TCR to CRR Transition Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 270 days |  |  |  |
| Metric Description: ERCOT will provide detailed TCR to CRR plan describing each step of the transition. |  |  |  |
| Background: The intent of this metric is to verify the existence and publication of the TCR to CRR transition Plan. |  |  |  |
| Criteria: The Readiness Team will review, from a public source, the TCR to CRR transition plan including rebate, timing and other CRR details of interest. Readiness will be achieved when the Readiness Team will be provided with documentation that verifies that the TCR to CRR transition plan has been created, updated, and updates approved by TAC. TCR to CRR Transition Plan exists, updated according to schedule, and approved by the TAC |  |  |  |
| Reporting Data Sources: TCR to CRR Transition Plan / ERCOT CRR PM |  |  |  |
| References | TP: N/A | TNP: |  |

### CRR3 – Operation of CRR Auctions and Allocations

| Reported By: ERCOT, CRRAHs |  |  | - Phase: 4, 5 |
| --- | --- | --- | --- |
| Target Completion: Market Trials Phase 5 Completion |  |  |  |
| Metric Description: ERCOT shall execute test monthly allocations and auctions of Congestion Revenue Rights for CRR Account Holders prior to Nodal market launch during Market Trials. |  |  |  |
| ERCOT Criteria: The Readiness Team will review documentation that verifies that Congestion Revenue Rights auctions produce a solution, allocate revenue rights to potential CRR account holders and produce accurate results for statistical sampling of bids as determined by the CRR team. Readiness will be met when the CRR auctions solve within acceptable timelines and when CRRs results are distributed to applicable account holders . CRR Auction Results distributed to participants according to schedule defined in CRR Handbook = 100% (This will be done by tracking whether ERCOT meets the “publication of results” date in the CRR Handbook for each auction/allocation). ERCOT RAG Rules – Schedule Green – Meeting or better than schedule based on CRR Handbook schedule Amber – <= 5 business days off schedule Red – > 5 business days off schedule Allocated Revenue Rights in statistical sample = 100% accurate (This will be done by a built-in report that compares Source/Sink prices to CRR clearing prices) ERCOT RAG Rules – Accuracy Green – 100% accuracy Amber – 97% <= accuracy < 100% OR Red – Criteria Not Met (less than 97%) CRRAH Criteria: Registered CRRAHs participate in at least 50% of the available auctions in Market Trials. CRRAHs will only be measured on the previous two auctions to encourage participation in at least every other auction. Participation, for the purposes of this metric, is defined as the submission of CRR bids, the submission of CRR offers, submission of credit, and/or participating in a CRR allocation. Please note that this metric became effective after the March 2nd, 2010 NATF meeting. The metric will light up with GREEN/WHITE only on March 24th, 2010. AMBER and RED scores will be released on May 5, 2010 providing enough time to notify market participants of their scores after the May bid window closes on April 15th, 2010. CRRAH RAG Rules – Participation Green – >= 50% participation in CRR Auctions throughout Market Trials Amber - < 50% participation Red – No participation CRRAH RAG Rules – Market Segment Red - < 50% of CRRAHs participating Amber - >= 50% and < 80% of CRRAHs participating Green - >= 80% of CRRAHs participating |  |  |  |
| Reporting Data Sources: Extract from CRR Database / CRR Market Trials Team |  |  |  |
| References | TP: 5.4.5 (1) | TNP: |  |

### CRR4 - Implement TCR to CRR Transition Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 120 days |  |  |  |
| Metric Description: ERCOT shall Implement the approved TCR to CRR Transition Plan to assign rights for the Nodal Market Go-Live. |  |  |  |
| Background: The intent of this metric is to ensure that there is an acceptable TCR to CRR Transition Plan. |  |  |  |
| Criteria: The Readiness Team will be notified of the implementation of the approved TCR to CRR Transition Plan. Readiness will be achieved when the Readiness Team is provided with documentation that verifies that the TCR to CRR transition plan previously described in Metric CRR2, "Develop TCR to CRR TransitionPlan" has been implemented. TCR to CRR Transition Plan Business Procedures have been implemented |  |  |  |
| Reporting Data Sources: Notification of the TCR to CRR Transition Plan Implementation / ERCOT CRR PM |  |  |  |
| References | TP: 6.1 (i) | TNP: |  |

# ERCOT Internal Metrics

### E1 - ERCOT Staff Completes Training

| Reported By: ERCOT |  |  | Phase: 2.1, 3, 4, 5 |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT Staff Completes required training modules by area of expertise and job responsibilities. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT staff has the ability to facilitate the Nodal Market. |  |  |  |
| Criteria: Criteria will be met when the Readiness Team will review documentation verifies that ERCOT Staff have completed the required training. Each department will have an overall training score: - The overall ERCOT Internal Training Metric is obtained by summing the points from all of the departments, and applying the criteria posted below.Green (0 pt): No uncompleted training due within 30 days - Amber (1 pt): Uncompleted training due within 30 days - Red (3 pt): Uncompleted training is past due RAG Rules Red – > 6 points, totaled over all impacted departments Amber – 4-6 points, totaled over all impacted departments Green – 0-3 points, totaled over all impacted departments |  |  |  |
| Reporting Data Sources: Learning Management System / ERCOT Readiness PM - ERCOT will plan which training modules individuals are required to take and will track progress against the plan. - ERCOT will publish accomplishments against the plan. |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E2 - Verify ERCOT Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a detailed test plan to ensure adherence to the ERCOT Performance Monitoring Requirements |  |  |  |
| Background: It is the intent of this metric to ensure that the systems, access and capabilities are in place to monitor ERCOT performance in the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT is ready to begin the monitoring activities as specified in Section 8.2: Performance Monitoring and Compliance. Readiness will be achieved when the ERCOT Performance Monitoring plan is approved by TPTF and posted. ERCOT Performance Monitoring Test Plan Exists |  |  |  |
| Reporting Data Sources: Notification of Capability to Monitor ERCOT Compliance / ERCOT Readiness PM |  |  |  |
| References | TP: 5.4.12 | TNP: 8.2 |  |

### E3 - Validate Telemetry/SE ISM/ Data Accuracy

| Reported By: MP & ERCOT |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall provide access to accurate operational data via the EDW for both ERCOT Operations and Market Participant. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that operations data access is available via the data warehouse. Readiness will be achieved when source system data is accurately represented and the necessary reports are available in the ISM reports and is accessible by ERCOT Operations and Market Participants. Operations confirms ability to access ISM reports and Telemetry / SE data accuracy; and Market Participants confirm ability to access ISM/MIS reports and Telemetry / SE data accuracy. RAG Rules Red – Not meeting criteria by the 168 Hour Test Amber – Not meeting criteria by the 168 Hour Test Green – meeting criteria |  |  |  |
| Reporting Data Sources: Notification from Operations Attesting ISM Access / Market Trials Reports Lead |  |  |  |
| - References | - TP: N/A | - TNP: 17.3.2 |  |

### E4 - Transition Pricing Mechanisms

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 90 days |  |  |  |
| Metric Description: ERCOT and the Market Participants shall develop mechanisms to be implemented for a limited period after Nodal Go-Live. |  |  |  |
| Background: This metric will ensure that a plan for limiting pricing of energy and ancillary services is in place during the early stages of nodal market start-up has been created. |  |  |  |
| Criteria: Readiness will be achieved when the ERCOT Board of Directors approves a NPRR establishing the mechanisms. NPRR is Approved |  |  |  |
| Reporting Data Sources: NPRR / ERCOT Readiness PM |  |  |  |
| References | TP: 6.1 (m) | TNP: N/A |  |

### E5 - Nodal SAS 70 Readiness

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 45 days |  |  |  |
| Metric Description: ERCOT shall prepare for the transition from current to nodal SAS 70 requirements by identifying those control objectives which must be developed, changed or modified So that NODAL operations are able to make a final SAS70 Readiness Declaration stating that ERCOT is prepared for a SAS70 audit of the NODAL systems.are prepared to meet |  |  |  |
| Background: It is the intent of this metric to ensure that SAS 70 Audits can be accomplished in the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that the current to nodal transition SAS 70 control objectives have been updated for nodal operations. The ERCOT Readiness PM will faciltate an impact assessment to determine which control objectives are impacted by Nodal. Each individual department is responsible for updating the control objectives in their respective areas. The ERCOT Readiness PM will monitor progress to this end. The ERCOT Internal Audit department will provide pre-audit consulting services, reviewing the updated control objectives and providing recommendations related to ERCOT’s ability to meet these objectives. Upon review of Internal Audit’s recommendations, the Readiness PM will declare ERCOT’s final readiness status at Go-Live less 45 days. Control Objectives Updated = 100% of Control Objectives identified as requiring a Nodal update ERCOT meets SAS 70 Requirements - This metric will be measured regularly with updates published in conjunction with planned milestones. - Tentative milestones will include: - Control Objectives Impact Assessment (Q1 2008) - Control Objectives Updated (By Business Area) (Q2 2008) - Pre-Audit Assessment (By Business Area) (Q2 / Q3 2008) - Final SAS70 Readiness Declaration (Q4 2008) RAG Rules Red – Failure to meet plan Amber – Behind Training Schedule Green – Meeting Plan |  |  |  |
| Reporting Data Sources: Control Objectives Log revision history / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E6 - Develop Nodal Operating Guides

| Reported By: ERCOT |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Less 360 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall develop Nodal Operating Guides to direct Market Participants on the daily operation of the Texas Nodal Market and Grid. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has provided the Market Participants with the information required to operate the Texas Nodal Market and Grid. |  |  |  |
| Criteria: The Readiness Team will receive documentation that the creation and posting of approved Nodal Operating Guides has occurred. Readiness will be met when the Operating Guides have been posted to the MIS and approved by ROS and TAC. - Traceability of Operating Guidelines to Protocols (50 percent) - Progress against plan (50 percent) - August 22nd – OWG Review of additional comments - September 12th – Impact Analyses due - September 13th – ROS Meeting to consider NOGRR001-017 and IAs - October 5th – TAC Meeting to consider NOGRR001-017 and IAs RAG Rules Red – Failure to Meet Plan and Provide Full Traceability by February, 2008 Amber – Meeting Either Schedule or Traceability, but Not Other Green – On Schedule and Traceability Targets |  |  |  |
| Reporting Data Sources: Operating Guides / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E7 - Validate ISM Access & Accuracy of Postings Required by the IMM

| Reported By: IMM & ERCOT |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test |  |  |  |
| Metric Description: ERCOT shall provide access to accurate data to the ISM and postings to the MIS. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that data access is available to the IMM via the ISM and the MIS. Readiness will be met when source system data is accurately represented in the ISM and is accessible by the IMM and when data to be posted is accessible by Market Participants. IMM confirms ability to access ISM Market Particpants are able to view required postings on the MIS |  |  |  |
| Reporting Data Sources: Notification from IMM Attesting ISM Access / Market Trials Reports Lead |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E8 - ERCOT Staffed for Texas Nodal Operations

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - Full Nodal Functionality 24*7 Operations Major Milestone less 60 days |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT will ensure the appropriate staffing levels required to execute the nodal market. In addition, the roles and responsibilities have been appropriately defined for nodal personnel. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT is appropriately staffed to support Nodal Operations as approved by the PUCT. |  |  |  |
| Criteria: Each impacted Director or VP is responsible for conducting a sizing and alignment analyses for their area as a part of the overall ERT project. Each department will develop their respective supporting documentation and readiness assessment. The Readiness Team will view the analysis results for each department and verify completion of the sizing and alignment analysis and the development of the corresponding staffing plan. Readiness will be achieved upon the completion of Sizing and Alignment Analysis for each Department and Departmental Staffing Plans and the execution of those plans. ERCOT will publish accomplishments against the plan. This metric will be measure continuously with updates published in conjunction with planned EDS milestones. - Sizing and Alignment Analysis completed for each impacted department - Creation of Org. Charts (Q22007) - Division and Department Head approval of deliverables - Allocation of appropriate funding to staff the organization (Q12008) - Staffing to plan (Q42008) For the Staffing to Plan criteria the following standards will apply: RED; AMBER; GREEN. May 1, 2008; <85%; 85-90%; >90%. June 1, 2008; <90%; 90-95%; >95%. July 1, 2008; <95%; 95-98%; >98%. AND Staffing levels are maintained through Go-Live. Any open Critical position (those that would impact Nodal Go-Live) indicates ‘AMBER’. Any Critical position vacant for more than 30 days indicates ‘RED’ status. |
| Reporting Data Sources: Sizing and Alignment Analysis for each Department / Departmental Staffing Plans / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E9 - Develop TN Procedures

| Reported By: ERCOT |  |  | Phase:: 2.1,3,4,5 |
| --- | --- | --- | --- |
| Target Completion: Go-Live |  |  |  |
| Category: ERCOT Internal |  |  |  |
| Metric Description: ERCOT shall develop it’s internal processes and procedures supporting the Texas Nodal Market. |  |  |  |
| Criteria: Criteria will be met when the when the processes and procedures supporting the Nodal Market have been completed. Phase 1 (Prior to 9/1/2010) Red - More than one procedure is not developed 1 month prior to the Market Trial phase where it is scheduled to be exercised or more than 3 procedures scheduled to be exercised in the current or prior Market Trials phase are not exercised. Amber - One procedure is not developed 1 month prior to the Market Trial phase where it is scheduled to be exercised or 3 or fewer procedures scheduled to be exercised in the current or prior Market Trials phase are not exercised.Green - ERCOT procedures are developed 1 month prior to the Market Trials phase where they are scheduled to be exercised and ERCOT procedures are exercised in the current or prior Market Trials phase as scheduled. Measurements for the following Market Trials Phase will be available on the Nodal Scorecard on these dates: - Market Trials Phase 3 – 1/13/2010 - Market Trials Phase 4 – 3/4/2010 - Market Trials Phase 5 – 4/8/2010 Phase 2 (9/1/2010 – 12/1/2010) Red - More than 3 ERCOT procedures are not approved for go-live. Amber - > 3 or fewer procedures are not approved for go-live. Green – All ERCOT procedures are approved for go-live. RAG Rules See above. |  |  |  |
| Reporting Data Sources: ERCOT Process/ Procedure Inventory / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E10 - Validate ISM, CDR, and Lodestar Source Reporting Access & Accuracy for internal ERCOT use

| Reported By: ERCOT |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test |  |  |  |
| Metric Description: ERCOT shall provide access to accurate Commercial data via the ISM, CDR, and Lodestar source reporting. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that access to Market Trials test data is available via the ISM, CDR, and Lodestar source reporting for the appropriate departments. Readiness will be met when source system data is accurately represented (based on the upstream Market Trials test data) in the ISM and is accessible to the 13 highly impacted departments listed below. Managers within the specific departments are responsible for determining, which staff needs access Department; ISM; CDR; CMM; Lodestar Source Reporting. Credit Administration; X; X. Treasury; X; X. Market Operations Support; X. Outage Coordination; X. Network Modeling; X. Operations Planning; X. Advanced Network Applications; X. Grid Operations; X. Planning Services; X. Settlement Metering; X. Energy Analysis & Aggregations; X. Settlements & Billing Operations; X; X. Data Integrity and Administration; X; X; X. Wholesale Client Services; X; X. Managers must submit a confirmation that their staff 1) has access to the appropriate data repositories and 2) the data and data structures are accurate based on the Market Trials data in the upstream applications. |
| Reporting Data Sources: Notification from the 13 highly impacted departments / Market Trials Reports Lead |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E12 - MIS Compliance Test

| Reported By: ERCOT |  |  | EDS: |
| --- | --- | --- | --- |
| Target Completion: 168 hour test minus 30 days |  |  |  |
| Metric Description: This metric will measure the completion and implementation of a compliance plan to verify the degree to which protocol requirements for MIS Public, Secure, and Certified areas are met. |  |  |  |
| Background: It is the intent of this metric to ensure the functionality and operability of the Secure, Public and Certified areas of the Market Information System. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT has successfully completed a MIS Compliance Test. Readiness will be met when the completion of the MIS Compliance Test has been accomplished. MIS Compliance Test Successfully Posted according to Protocol Requirements |  |  |  |
| Reporting Data Sources: MIS Compliance Test Plan / MIS Compliance Test Results / ERCOT MIS PM |  |  |  |
| References | TP: 5.4.13 | TNP: 12 & 4.4 & 9.1.3 |  |

### E14 - Verify QSE Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a TAC-approved QSE/Resource monitoring Program. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has developed a program to monitor Generating Resource Performance Requirements as required in the protocols. |  |  |  |
| Criteria: The Readiness Team will verify that a QSE/Resource monitoring Program is documented and approved and that a corresponding test plan has been successfully executed. Plan developed, approved by TAC, and implemented |  |  |  |
| Reporting Data Sources: QSE Performance Monitoring Plan / ERCOT Readiness PM |  |  |  |
| References | TP: 5.4.12 | TNP: 8.1 |  |

### E15 - Verify TSP Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a TAC approved TSP Performance Monitoring program. |  |  |  |
| - Background: The intent of this metric is to ensure that ERCOT has developed a plan to monitor performance of TSP as required in the protocols. |  |  |  |
| Criteria: The Readiness Team will verify that a TSP monitoring Program is documented and approved and that a corresponding test plan has been successfully executed. Plan developed, approved by TAC, and implemented |  |  |  |
| Reporting Data Sources: TSP Performance Monitoring Plan / ERCOT Readiness PM |  |  |  |
| References | TP: 5.4.12 | TNP: 8.3 |  |

# Energy Management Operations Metrics

### EMO1 - Network Security Analysis & Transmission Constraint Management

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 - Release 3 complete plus 60 days |  |  |  |
| Metric Description: ERCOT shall Validate Transmission Constraint Management Functions to include the accurate identification of constraints, the Network Security Analysis Process, the security analysis sequence, operation of Dynamic Ratings processor, Special Protection Scheme (SPS), Remedial Action Plans (RAPs), and Load Rollover. |  |  |  |
| Background: The intent of this metric is to verify the ability of ERCOT manage constraints in a reliable economical manner. |  |  |  |
| Criteria: The Readiness Team shall review documentation that the transmission constraint management functions include the accurate identification of constraints, the Network Security Analysis process, the security analysis sequence and the operation of Dynamic Ratings processor, Special Protection Scheme (SPS), Remedial Action Plans (RAPs), and Load Rollover. Readiness will be achieved when the number of Over Load and Voltage limit alarms are equivalent to the number of actual Over Load and Voltage violations. Readiness will be achieved with the RTCA has been run for every element in system. Number of n-1 contingency violations = Number of Load & Voltage Limit Alarms Sum of N-1 Analyzed = Sum of Elements |  |  |  |
| Reporting Data Sources: SCADA Extract/ EMS Extract / Limit Alarm Log / Extract from Real Time Contingency Analysis Engine (RTCA) / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.3 | TNP: 6.5.7.1 |  |

### EMO2 - Verify Voltage Support Functionality

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Milestone |  |  |  |
| Metric Description: This metric will verify that ERCOT has a functioning process to manage Voltage Support Services (VSS) in the Nodal Market. |  |  |  |
| Background: It is the intent of this metric to ensure that ERCOT can manage the voltage of the system in the Nodal Market through the use of communicating voltage profile requirements to QSEs and TSPs and monitoring of voltages to assure compliance to Protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the proper functionality of the Voltage Support Service. Readiness will be met when a test of the Voltage Support Service has been completed. Voltage Profiles are created and communicated to QSEs & TSPs Ercot monitors voltage and can confirm compliance to protocols during EDS. |  |  |  |
| Reporting Data Sources: Voltage Profiles by QSE and TSP / EMS Extract of Voltage Telemetry Values corresponding to Voltage Profile Locations / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: 3.15(2) |  |

### EMO3 - Verify Outage Evaluation System Functionality

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: This metric will measure the ability of ERCOT to manage the Outage Management Process to include the use by Market Participants and also include a temporary Outage Minimization Plan for use in the first weeks of the Nodal Market. |  |  |  |
| Background: It is the intent of this metric to ensure that Market Participants can schedule, change and receive outage notifications, that the ERCOT Operators can distinguish between forced and scheduled outages and that an Outage Minimization Plan is created for the Nodal Market Go Live. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT developed an Outage Management System capable of efficiently managing Outages submitted by Market Participants . Readiness will be met when the Outage Minimization plan is published and when the Outage Management Test has been successfully completed. An approved Outage Minimization Plan is implemented A test of the Outage Management Process is completed |  |  |  |
| Reporting Data Sources: Outage Minimization Plan/ Test results of Outage Management Test / EDS 4 PM |  |  |  |
| References | TP: 5.4.10 (1) | TNP: |  |

### EMO6 - QSE Individual LFC Testing

| Reported By: QSERs & ERCOT |  |  | Phase: 4,5 |
| --- | --- | --- | --- |
| Target Completion: 2 hour system-wide LFC test |  |  |  |
| Metric Description: This metric will ensure that ERCOT can send control signals to QSEs to verify generation control functions, verify that QSEs can receive control signals from LFC for Regulation and Updated Desired Generation, and that each QSE and its generation can respond to controls. |  |  |  |
| Criteria: As referenced in the Real-Time market Testing Market Participant Handbook, any QSEs with Resources that did not participate in the EDS 3 Release 6.2 testing that was conducted in 2008 are required to participate in individual LFC testing. Additionally, QSEs that have attested that they plan to provide Regulation Service in the Nodal Market will also have to participate in this testing. Based on a QSE’s resources and whether the QSE intends to provide Ancillary Services in the Nodal Market, ERCOT will determine which of the following tests need to be completed: - Individual QSE UDBP and Regulation Completion Test - Constant Frequency Operation Completion Test - Responsive Reserve Service Schedule Completion Test - Telemetry Check Out/Communications Test (primarily for wind-only QSEs) ERCOT Criteria: ERCOT has completed conducting and reviewing individual QSE tests. QSEs with Resources representing 80% of system-wide generation have completed individual QSE tests for LFC, including all QSEs with Resources that plan to provide Regulation Service in the Nodal Market or that did not participate in the EDS 3 Release 6.2 testing that was conducted in 2008. RAG Rules – ERCOT Green = ERCOT is on track to complete individual LFC tests for 80% of system-wide generation by the 2 hour system-wide LFC test Red = ERCOT has completed individual LFC tests for less than 80% of system-wide generation by the 2 hour system-wide LFC test QSE with Resources Criteria: QSEs with Resources representing 80% of system-wide generation have completed individual QSE tests for LFC, including all QSEs with Resources that plan to provide Regulation Service in the Nodal Market or that did not participate in the EDS 3 Release 6.2 testing that was conducted in 2008. RAG Rules – QSEs with Resources Green = Individual LFC test completed successfully Amber = QSE actively addressing issues uncovered in individual LFC test Red = Individual LFC test not completed prior to 2 hour system-wide LFC test RAG Rules – Market Segment (Generation) Green = >= 80% of generation completed Amber = >= 50% and < 80% of generation completed Red = < 50% of generation completed |  |  |  |
| Reporting Data Sources: Results of individual LFC Tests / Market Trials LFC Dashboard |  |  |  |
| References | TP: 5.4.8 (2) | TNP: 6.5.7.6 & 8.1 |  |

### EMO7 - Verify Load Forecast Accuracy

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Start + 120 days |  |  |  |
| Metric Description: This metric will determine the ability of the Short Term Load Forecast(STLF) and Medium Term Load Forecast(MTLF) to meet accuracy standards. |  |  |  |
| Background: It is the intent of this metric to ensure that the STLF and MTLF meet standard accuracy performance measures in order to determine the amount of required generation required for each hour of the day. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the Seven-Day Load Forecast and the 36-Month Load Forecast accuracy is within prescribed limits during market trials. Readiness will be met when the Seven-Day Load Forecast is operating to existing standards. Readiness will be met when the 36-Month Load Forecast is operating to existing standards. Seven-Day Load Forecast is within accuracy limit of actual load 36-Month Load Forecast is within accuracy limit of actual load |  |  |  |
| Reporting Data Sources: EMS extract of Actual Load/ EMS extract of STLF / EMS extract of MTLF / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.2(2) | TNP: 3.12, 3.13, 4.2.2 & 8.2(2)© |  |

### EMO8 - Conduct EECP Test

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT and Market Participants shall conduct a test of the Emergency Electric Curtailment Plan (EECP). |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT can perform the steps of the EECP as outlined in the Protocols.. There must be an orderly, predetermined procedure for managing emergencies. ERCOT shall perform a test to initiate and coordinate the implementation of EECP using the nodal systems. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT conducted a test of the Emergency Electric Curtailment Plan (EECP) with Market Participants. Readiness will be achieved when Control Room procedures have been deployed and the EECP test was conducted. EECP Procedures Published EECP Test Completed Successfully as Defined in the EECP Test Plan |  |  |  |
| Reporting Data Sources: Documentation and Control Room Desk Procedures. All procedures are also posted at www.ercot.com. EDS 4 Notification of EECP Test Complete / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.16 | TNP: 6.5.9.4 |  |

### EMO9(A) – State Estimator Standards Performance Metric

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: 168-hour test |  |  |  |
| Category: Energy Management Operations |  |  |  |
| Metric Description: Verify that ERCOT is meeting the performance requirements defined in the State Estimator Standards. |  |  |  |
| Background: Ensure that ERCOT is meeting the requirements defined in the State Estimator Standards. |  |  |  |
| State Estimator meets the following performance and reporting requirements as identified in the State Estimator Standard: Convergence (Will be updated on a monthly basis based on the results found in the ERCOT Nodal State Estimator Performance Report) - State Estimator converges 97% of runs during a monthly test period. RAG Rules Red – Less than 95 percent Amber – Less than 97 percent and greater than or equal to 95 percent Green – Greater than or equal to 97 percent |  |  |  |
| Reporting Data Sources: Advanced Network Applications |  |  |  |
| References | TP: State Estimator Standards and 5.4.1 (2)(b) | TNP: N/A |  |

### EMO9(B) – Real-Time Contingency Analysis Modeling Differences

| Reported By: ERCOT |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: 168-hour test |  |  |  |
| Category: Energy Management Operations |  |  |  |
| Metric Description: Track model and telemetry differences which impact Real-Time Contingency Analysis (RTCA). |  |  |  |
| Background: The intent of this metric is to highlight model and telemetry differences which impact Real-Time Contingency Analysis (RTCA). |  |  |  |
| RTCA Modeling Comparisons 95% of Transmission Element Impedance values match within RTCA as compared to Zonal and Nodal Model Data. RAG Rules - Impedance Red – Less than 85 percent Amber – Less than 95 percent and greater than or equal to 85 percent Green – Greater than or equal to 95 percent 95% of ratings for Dynamically Rated Line and Non-Dynamically Rated Lines match when comparing telemetered value to Zonal and Nodal modeled values. RAG Rules - Lines Red – Less than 85 percent Amber – Less than 95 percent and greater than or equal to 85 percent Green – Greater than or equal to 95 percent 95% of ratings for Load Tap Settings match when comparing telemetered value to Zonal and Nodal modeled values or overriden values.. RAG Rules – Load Tap Settings Red – Less than 85 percent Amber – Less than 95 percent and greater than or equal to 85 percent Green – Greater than or equal to 95 percent RAG Rules – Overall Will reflect the lowest rating of any of the 3 comparisons. Footnotes: - Exclude elements where there is not a one-for-one match in Zonal/Nodal models (e.g. pseudo switches and multi-section lines that have been split into multiple segments. |  |  |  |
| Reporting Data Sources: SCED / Transmission Constraint Manager (TCM) / Market Trials Phase 5 PM |  |  |  |
| References | TP: 5.4.1 (2)(b) | TNP: N/A |  |

### EMO9(C) - Validate Zonal and Nodal Security Analysis Results

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: 168-hour test |  |  |  |
| Category: Energy Management Operations |  |  |  |
| Metric Description: Verify that Security Analysis Results between the Zonal and Nodal Systems are consistent with one another. |  |  |  |
| Background: The intent of this metric is to provide a litmus test of the Nodal Systems Security Analysis capability. |  |  |  |
| 90% of active constraints utilized in Zonal Congestion Management are also detected in Nodal RTCA as congestion violations. Footnotes: - Elements are NOT included if modeling in Nodal was changed to break a single element into multiple elements. - The time-span allowed for the violation to show in Nodal is a 120-minute window (+/- 1 hour). RAG Rules Red – Less than 70 percent Amber – Less than 90 percent and greater than or equal to 70 percent Green – Greater than or equal to 90 percent |  |  |  |
| Reporting Data Sources: SCED / Transmission Constraint Manager (TCM) / Market Trials Phase 5 PM |  |  |  |
| References | TP: 5.4.1 (2)(b) | TNP: N/A |  |

### EMO9(D) - Validate Zonal and Nodal Security Analysis Results

| Reported By: ERCOT |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: Go-Live |  |  |  |
| Category: Energy Management Operations |  |  |  |
| Metric Description: Verify that Security Analysis Results between the Zonal and Nodal Systems are consistent with one another. |  |  |  |
| Background: The intent of this metric is to provide a litmus test of the Nodal Systems Security Analysis capability. |  |  |  |
| Criteria: The Readiness Team will verify that Zonal and Nodal common constraints are consistent with reasonably comparable results. Readiness will be achieved when constraints are comparable. The set of Zonal Security Violations = The set of Nodal Security Violations Zonal and Nodal Element Security Violations are within 10% of one another as measured monthly RAG Rules Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: SCED / Transmission Constraint Manager (TCM) / Market Trials Phase 5 PM |  |  |  |
| References | TP: 5.4.1 (2)(b) | TNP: N/A |  |

### EMO10 – Anomalous / Auto-Disabled Telemetered Points

| Reported By: ERCOT |  |  | Phase: 5 |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test |  |  |  |
| Metric Description: This metric will monitor telemetry quality received from TSPs as evidenced by the percentage of Anomalous / Auto-Disabled points coming out of the State Estimator. |  |  |  |
| Background: It is the intent of this metric to ensure that the telemetry received is of good quality. |  |  |  |
| Criteria: The Readiness Team will review statistics relating to Anomalous / Auto-Disabled Telemetered Points coming out of State Estimator to identify potential problem areas in the telemetry received from TSPs. ERCOT will be evaluated as follows: Anomolous / Auto-Disabled Telemetered Point The % of Anomalous and Auto-Disabled Measurements is less than 2% of Total Measurements (as observed using a snapshot during the reporting period) RAG Rules Green – Measurements are less than 2% of Total Measurements Red – Measurements are >= 2% of Total Measurements |  |  |  |
| Reporting Data Sources: Nodal and Zonal Network Models / Advanced Network Applications team |  |  |  |
| References | TP: N/A | TNP: |  |

### EMO12 - Network Operations Model

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 - Release 3 complete plus 60 days |  |  |  |
| Metric Description: ERCOT shall verify that all protocol required modeling of Generation and Loads are correctly mapped in the Network Operations Model and that all generation and substation load is either telemetered directly or able to be estimated by the State Estimator. |  |  |  |
| Background: The intent of this metric is to verify the ability of ERCOT construct a network model according to protocols requirements and estimate all genration and load in the ERCOT System. Protocols require minimium SE performance requirements and that SE Performance metrics to be developed and met. |  |  |  |
| Criteria: The Readiness Team shall review documentation that the transmission network operations model is meets protocol requirements. Readiness will be achieved with the TPTF approves the Network Operations Model for nodal go-live. 100 percent of load is modeled per protocols 100 percent of genration as identified in RARF submissions is modeled per protocol RAG Rules Green - >= 99 percent modeled Yellow – between 90 and 99 percent Red – less than 90 percent |  |  |  |
| Reporting Data Sources: SCADA Extract/ SE Performance logs/ TPTF Approval |  |  |  |
| References | TP: | TNP: 3.10 |  |

### EMO13 – Operating Personnel and Facilities Readiness

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go-Live less 150 days |  |  |  |
| Metric Description: ERCOT dispatch operations personnel are assigned to operate nodal systems 7x24 on site and operater consoles deployed in dispatch control rooms operating nodal systems software 7 x 24 in parallel with current operations. Verification of transmisison and generation parameters with synchronized zonal operations. |  |  |  |
| Background: The intent of this metric is to measure the readiness of ERCOT Energy management system personnel readiness to operate in a nodal environment. |  |  |  |
| Criteria: The Readiness Team shall review documentation that the transmission network operations and generation control functional capability is simliar to or superior to the zonal system. Readiness will be achieved when personnel assigned to man shift work and operating consoles are in place and operational. Dispatch Operations Personnel report by survey that the nodal system provides functionality in grid operations and LFC similar to or superior to the zonal market functionality. EMO Personnel Assigned = 100% required Control Room Operator Consoles in place at Taylor and Austin Control Rooms Affirmative Response from System Operators > 95% RAG Rules Green – Criteria Met Red – Criteria Not Met |  |  |  |
| Reporting Data Sources: Readiness team/ Survey of Control Room Opertors |  |  |  |
| References | TP: 6.0 | TNP: |  |

# Network Model Management Metrics

### N1 - ERCOT Telemetry Alarm Processing

| Reported By: MP & ERCOT(EDS 1 Team) |  |  | EDS: 1 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 1 Complete plus 14 days |  |  |  |
| Category: Network Model Management |  |  |  |
| Metric Description: ERCOT initiates alarms for Limit Violations,& Status Changes. |  |  |  |
| Background: The intent of this metric is to ensure that control operators are aware of relevant EMS alarms. |  |  |  |
| - Criteria: The Readiness Team will review the results of the Limit, Status and other EMS Alarm Tests. Readiness will be achieved when alarms are generated from the Limit, Status and other EMS Tests and the attributes of the alarms are correct. Load / Rating > Alarm set point Change of Status inititiates a Status Alarm RAG Rules Red – Failure to meet criteria Amber – Within 10 percent of meeting criteria Green – Meeting criteria |  |  |  |
| Reporting Data Sources: Alarm Log / ERCOT EDS 1 PM |  |  |  |
| References | TP: 5.4.1 (2)(f),(g) | TNP: |  |

### N2 –Telemetry/ICCP System Failover

| Reported By: QSERs, TSPs, ERCOT |  |  | Phase: 4, 5 |
| --- | --- | --- | --- |
| Target Completion: 8-hour LFC test |  |  |  |
| Category: Real-Time Market |  |  |  |
| Metric Description: Verify that all ERCOT and MP ICCP telemetry failover criteria are met. |  |  |  |
| ERCOT Criteria: Readiness will be achieved when ERCOT has failover criteria for the EMMS Habitate servers and the the ICCP Communications servers. ERCOT completes local failover of the ICCP communications servers for every Nodal Database Load, which currently occurs once a month. ERCOT also completes local failover of EMS Habitat servers (for the Austin and Taylor Data Centers) for every Nodal Model (aka DSV) load, which currently occurs every two weeks. ERCOT will provide the failover durations of a random set of Nodal Database and DSV loads up to the 8-hour LFC test as evidence that the criteria listed below has been met. EMS Habitat Server Failover Duration <=5 Minutes ICCP Communications Server Failover Duration <= 30 Seconds ERCOT RAG Rules Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria Please note that ERCOT will also be conducting site failover tests of the entire EMS production environment (ICCP, Habitat, and E-terra Archive servers) between the Austin and Taylor Data Centers. These site failover tests will be conducted concurrently to Market Trials Phases 4 and 5 and are not part of the metric criteria, but they are good indicators of ERCOT’s preparedness in the event a site failover is needed. ERCOT will present the results of the site failover tests to NATF prior to the 8-hour LFC test. MP Criteria: ERCOT will conduct failover tests for QSEs and TSPs with ICCP telemetry links prior to the 8-hour LFC test. The failover tests will be based on the same tests that were conducted for QSEs and TSPs in September of 2007 during the EDS1 trials. All QSEs with ICCP telemetry links will be tested even if they completed a test in 2007 since ICCP communications is a new requirement for QSEs in the Nodal Market. For TSPs, only TSPs that 1) did not complete an EDS1 ICCP failover test or 2) have new equipment since the EDS1 ICCP failover test will be required to complete the test again. TSPs have been required to use ICCP for zonal and it is not a new requirement for TSPs to transition to a Nodal Market. ERCOT will release a dashboard every week of the progress of ICCP failover testing on the Real-Time section of the Market Trials page on the Nodal Readiness Center. MP RAG Rules Red – ICCP failover test has not been completed successfully prior to the 8-hour LFC test. Amber – ICCP failover test not completed by 8-hour LFC test, but QSE or TSP is working with ERCOT to address issues Green – QSE or TSP has passed ICCP failover test prior to 8-hour LFC test. |  |  |  |
| Reporting Data Sources: ICCP failover test dashboard / EMS Production Support |  |  |  |
| References | TP: 5.4.1 (2)(k) | TNP: 3.10.7.4, 6.4.5(1) & 8.1.2 |  |

### N3 - Validate SE Performance and Accuracy

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Release 3 complete |  |  |  |
| Category: Network Model Management |  |  |  |
| Metric Description: Validate State Estimator performance as the time to reach a valid solution and availability as the percent of time the SE is capable of reaching a solution within accuracy limits defined by TAC approved SE standard. |  |  |  |
| Background: The intent of this metric is to prove the State Estimator meets stated performance criteria for Cold Start and Tracking mode and maintains a sufficient level of availability so as to provide rapid response to changing system conditions. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the solution time and availability of the state estimator each pass a threshold value. These criteria will be kept current with the Texas NODAL Market State Estimator Standards. RAG Rules Red – Not meeting criteria Amber – within 10 percent of criteria Green – meeting criteria |  |  |  |
| Reporting Data Sources: State Estimator Statistics from MIS Secure Area / ERCOT EDS 2 PM |  |  |  |
| References | TP: 5.4.2 (2) | TNP: 3.10.9.1, 3.10.9.2 & 8.2(2)(a)(vi) |  |

# Market Operations Metrics

### MO3 - Verify Supplemental Ancillary Services Market (SASM)

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations |  |  |  |
| Metric Description: ERCOT shall test Supplemental Ancillary Services Market Functionality and Procedures. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT can procure additional ancillary services to meet regulation and responsive reserve requirements during the operating day. |  |  |  |
| Criteria: The Readiness Team will review MMS data indicating that supplemental ancillary services are defined by the output of the real time market ERCOT will perform multiple SASM and SASM Auctions that are successfully executed during Market Trials and the 168 hour test. During this test, it is expected that ERCOT will call a SASM and receive the specified ancillary services. It is also expected that ERCOT will call a SASM and not receive the requested ancillary services. In both cases, the expectation is that the market continues to solve. |  |  |  |
| Reporting Data Sources: Nodal MMS Data Extract of RT / Zonal MMS Data Extract of RT / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.14 | TNP: 6.4.8.2 – 6.4.8.2.3 |  |

### MO4 - Verify SCED Execution Quality

| Reported By: ERCOT |  |  | Phase: 3, 4, 5 |
| --- | --- | --- | --- |
| Target Completion: Go Live |  |  |  |
| Category: Market Operations |  |  |  |
| Metric Description: ERCOT will determine the quality of each SCED execution by monitoring locational marginal prices and base points to ensure that they meet the six validation rules detailed below. |  |  |  |
| Criteria: The Readiness Team will review SCED execution results provided by the Market Operations team from ERCOT’s price validation tool. This metric will be reported on a bi-weekly basis scoring the previous two-week period. The tool contains the following fundamental business rule validations that will be measured for LMPs and Base Points: Fundamental Validation Rules for Each SCED Execution: If LMP is greater than or equal to offer price at maximum limit (HDL) then the Resource should be dispatched at maximum limit (HDL) If LMP is less than or equal to offer price at minimum limit (LDL) then the Resource should be dispatched at minimum limit (LDL) If LMP is equal to offered price at dispatched MW point then the Resource should be dispatched within minimum limit (LDL) and maximum limit (HDL) Shadow Price is zero for a transmission constraint which is not binding or violated Shadow Price is non-zero for a transmission constraint which is binding or violated Base Points are between HDL and LDL Performance Calculation: Performance for the metric should be calculated by dividing the # of price validation executions where no error flag was set by the total # of price validation executions for the applicable reporting period. # of price validation executions with no error flags / Total # price validation executions RAG Rules Red – Failed any of the above validation rules Green – None of the above validation rules failed. |  |  |  |
| Reporting Data Sources: Price Validation tool results |  |  |  |
| References | TP: 6.1(c.) | TNP: 6.5.7.1.12, 6.5.7.1.13 |  |

### MO5 - Generate Real-time LMPs for 6 months

| Reported By: ERCOT |  |  | Phase: 3,4,5 |
| --- | --- | --- | --- |
| Target Completion: – Go Live |  |  |  |
| Category: Market Operations |  |  |  |
| Metric Description: Generate LMPs for a six month period. The six month period starts in the beginning of March 2010. The LMPs will be calculated daily for each node and posted for Market Participant Access. |  |  |  |
| Criteria: The Readiness Team will review whether ERCOT has generated and posted LMPs on a daily basis. Readiness will be met when LMPs are produced and posted at regular intervals during six month window during Market Trials Phases 3, 4, and 5. If ERCOT has to use a LMP from a previous interval, it will not be considered a generated LMP and will count against criteria. This metric will be reported on a bi-weekly basis scoring the previous two-week period. This metric’s purpose is to provide visibility to Market Participants of the stability of the Real-Time Market execution, and will exclude planned system maintenance. During the 6 month LMP window: March 1, 2010 through August 31, 2010: - 95 percent SCED execution as evidenced by LMP posting times. RAG Rules Red – Less than 92 percent Amber – Less than 95 percent and greater than or equal to 92 percent Green – Greater than or equal to 95 percent From 168 Hour Test ot Go-Live: September 1, 2010 – Nodal Go-Live - 99 percent SCED execution as evidenced by LMP posting times RAG Rules Red – Less than 97 percent Amber – Less than 99 percent or greater than or equal to 97 percent Green – Greater than or equal to 99 percent |  |  |  |
| Reporting Data Sources: MMS DB and CDR extracts |  |  |  |
| References | TP: 5.1(4) | TNP: N/A |  |

### MO7 – ERCOT Operating Personnel and Facilities Readiness

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go-Live less 150 days |  |  |  |
| Metric Description: ERCOT DAM operations personnel are assigned to operate DAM nodal systems 7x 8 on site and operater consoles deployed operating DAM daily using nodal systems software 7 x 8 in parallel with current operations. |  |  |  |
| Background: The intent of this metric is to measure the readiness of ERCOT Market Operations personnel readiness to operate DAM in a nodal environment. |  |  |  |
| Criteria: Readiness will be achieved when personnel assigned to operate DAM and operating consoles in place. Market Operations Personnel report by survey that the nodal systems for DA activities are sufficiently functional to begin nodal operations. MO Personnel Assigned = 100% required MO Operator Consoles in place at Taylor and Austin Control Rooms Affirmative Response from MO Operators > 95% |  |  |  |
| Reporting Data Sources: Readiness team/ Survey of MO Opertors |  |  |  |
| References | TP: 6.0 | TNP: |  |

### MO8 - Verify DAM Execution Quality

| Reported By: ERCOT |  |  | Phase: 4,5 |
| --- | --- | --- | --- |
| Target Completion: Go Live |  |  |  |
| Category: Market Operations |  |  |  |
| Metric Description: ERCOT will determine the quality of each DAM execution by monitoring locational marginal prices to ensure that they meet the six validation rules detailed below. |  |  |  |
| Criteria: The Readiness Team will review DAM execution results provided by the Market Operations team from ERCOT’s price validation tool. This metric will be reported on a bi-weekly basis scoring the previous two-week period of Day-Ahead Market executions. The tool contains the following fundamental business rule validations that will be measured for Day-Ahead LMPs: Fundamental Validation Rules for Each DAM Execution: - (1) Resource Output Check for resources dispatched by DAM: - For hours when both Three-Part Supply Offers and on-line Ancillary Service Offers are offered inclusive of each other, - If only energy offer is cleared from a Resource: The cleared energy offer, if cleared from the Energy Offer Curve of a Three-Part Supply Offer, shall observe the Resource’s LSL and HSL, i.e., higher than or equal to LSL and lower than or equal to HSL. - If only AS offers are cleared from a Resource: The sum of the awarded Ancillary Service capacities for each Resource must be less than or equal to the offer capacity and must be within the Resource limits specified in COP (LSL, HSL). - If both energy offer and AS offer(s) are cleared from a Resource: The sum of cleared energy offer, Reg-Up offer, Responsive Reserve offer, Non-Spin on-line offer from a Resource should be less than or equal to the minimum of the last quantity on the EOC or the Resource’s HSL. The cleared energy offer minus the cleared Reg-Down offer should be greater than or equal to the maximum of the first quantity on the EOC or the Resource’s LSL. - For Hours when only AS are offered, the sum of Reg-Up, Reg-Down, Responsive Reserve and Online Non-Spin provided must be less than or equal to the HSL for Generation Resources and LPC for Load Resources minus the LSL for Generation Resources and MPC for Load Resources. - For Hours when only Three-Part Supply Offers are offered, the cleared energy offer must be less than or equal to the minimum of the last quantity on the EOC or the Resource’s HSL. - For hours when both Three-Part Supply Offers and on-line Ancillary Service offers are offered exclusive of each other, then either: - The sum of the AS shall be zero, or - AS shall be awarded. In this case energy shall be awarded at the resource low limit (LSL) and the Resource startup cost and minimum generation cost specified in Startup and Minimum Energy Offer of the Three-Part Offer shall be applied. (2)Shadow Price Check #1: Shadow Price is zero for a transmission constraint which is not binding or overloaded. (3) Shadow Price Check #2: Shadow Price is non-zero for a transmission constraint which is binding or overloaded. (4) For a resource that only submitted three part offer, - its LMP is greater than or equal to its energy offer price at min (HSL, max quantity on the EOC) if it is dispatched for energy at min (HSL, max quantity on the EOC); - its LMP is less than its energy offer price max(LSL, minimum quantity on the EOC) if it is not dispatched for energy; - its LMP is equal to offered price at dispatched MW point if it is dispatched within max(LSL, minimum quantity on the EOC) and min (HSL, max quantity on the EOC). (5) A resource is not scheduled for both offline ancillary services and either online ancillary services or energy. Performance Calculation: Performance for the metric should be calculated by dividing the # of price validation executions where no error flag was set by the total # of price validation executions for the applicable reporting period. # of price validation executions with no error flags / Total # price validation executions RAG Rules Red – Failed any of the above validation rules Green – None of the above validation rules failed. |  |  |  |
| Reporting Data Sources: Price Validation tool results |  |  |  |
| References | TP: 6.1(a.) | TNP: 4.5 |  |

### MO9 - Generate Day-Ahead LMPs and Settlement Point Prices

| Reported By: ERCOT |  |  | Phase: 4,5 |
| --- | --- | --- | --- |
| Target Completion: – Go Live |  |  |  |
| Category: Market Operations |  |  |  |
| Metric Description: Generate Day-Ahead LMPs beginning of April 2010 for Market Trials Phase 4. The LMPs will be calculated daily for each node and posted for Market Participant Access. |  |  |  |
| Criteria: The Readiness Team will review whether ERCOT has generated and posted LMPs after each Day-Ahead Market execution. Readiness will be met when LMPs are produced and posted at regular intervals during six month window during Market Trials Phases 4 and 5. This metric will be reported on a bi-weekly basis scoring the previous two-week period of Day-Ahead Market executions. This metric’s purpose is to provide visibility to Market Participants of the stability of the Day-Ahead Market execution, and will exclude planned system maintenance. During the April 1, 2010 through August 31, 2010 window: - 95 percent Day-Ahead Market execution as evidenced by Day-Ahead LMP and Settlement Point Price posting times. RAG Rules Red – Less than 92 percent Amber – Less than 95 percent and greater than or equal to 92 percent Green – Greater than or equal to 95 percent From 168 Hour Test to Go-Live: September 1, 2010 – Nodal Go-Live - 99 percent Day-Ahead Market execution as evidenced by Day-Ahead LMP and Settlement Point Price posting times RAG Rules Red – Less than 97 percent Amber – Less than 99 percent or greater than or equal to 97 percent Green – Greater than or equal to 99 percent |  |  |  |
| Reporting Data Sources: MMS DB and CDR extracts |  |  |  |
| References | TP: 6.1(h) | TNP: 4.5.3.2(a,b,c) |  |

### M10 – DRUC Execution

| Reported By: ERCOT |  |  | Phase: 4,5 |
| --- | --- | --- | --- |
| Target Completion: – Go Live |  |  |  |
| Category: Market Operations |  |  |  |
| Metric Description: Validate that the DRUC process is performed for each hour of the next operating day after each Day-Ahead Market execution. |  |  |  |
| Criteria: The Readiness Team will review the results from the Day-Ahead Reliability Unit Commitment (DRUC) process after each Day-Ahead Market execution. The DRUC results should be performed for each hour of the next Operating Day. The study normally commences at 1430 on the day prior to the Operating Day, and normally concludes at 1600 on the day prior to the Operating Day. This metric will be reported on a bi-weekly basis scoring the previous two-week period. This metric’s purpose is to provide visibility to Market Participants of the stability of DRUC execution, and will exclude planned system maintenance. During the April 1, 2010 through August 31, 2010 window: - 95 percent DRUC execution as evidenced by completion of section 2.4, “Execute DRUC” in the “Day Ahead and Weekly Reliability Unit Commitment” Operating Procedures. RAG Rules Red – Less than 92 percent Amber – Less than 95 percent and greater than or equal to 92 percent Green – Greater than or equal to 95 percent From 168 Hour Test ot Go-Live: September 1, 2010 – Nodal Go-Live - 95 percent DRUC execution as evidenced by completion of section 2.4, “Execute DRUC” in the “Day Ahead and Weekly Reliability Unit Commitment” Operating Procedures. RAG Rules Red – Less than 97 percent Amber – Less than 99 percent or greater than or equal to 97 percent Green – Greater than or equal to 99 percent |  |  |  |
| Reporting Data Sources: MMS DB and CDR extracts |  |  |  |
| References | TP: 6.1(d) | TNP: 5.5.2 |  |

# Contingency Metrics

### C1 - Contingency Plan for Weekly, Daily and Hourly RUC Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for RUC Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has a procedure when the primary RUC system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency plan and procedures document for RUC failure. Readiness will be achieved when the RUC Contingency Plan has been successfully tested. RUC Contingency Plan procedures Exists RUC Contingency Plan Successfully Tested |  |  |  |
| Reporting Data Sources: RUC Contingency Plan / RUC Contingency Plan Test Log / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C2 - Contingency Plan Procuedures for DAM Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures in case the DAM fails to solve. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to properly manage DAM failures |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for DAM failures. Readiness will be achieved when the DAM failure procedure has been successfully tested. DAM Failure Plan procedures Exists Procedures Successfully Executed in a test enviorment |  |  |  |
| Reporting Data Sources: DAM LMP Contingency Plan procedures / DAM / LMP Contingency Plan procedures Test Log / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C3 - Contingency Plan procedures for ICCP Data Failure

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for ICCP Data Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to operate during the loss of ICCP links at a single facility and at both the Taylor and Austin facility. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for ICCP failure. Readiness will be achieved when the ICCP Contingency has been successfully tested. ICCP Contingency Plan procedures Exists ICCP Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: ICCP Contingency Plan procedures / ICCP Contingency Plan procedures Test Log / / ERCOT EDS 2 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C4 - Contingency Plan procedures for SCED Failure

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for SCED Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to control generation and settle the market in the real time when the SCED system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency Plan procedures document for SCED failure. Readiness will be achieved when the SCED Failure Contingency has been successfully tested. SCED Failure Contingency Plan procedures Exists SCED Failure Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: SCED FailureContingency Plan procedures / SCED Failure Contingency Plan procedures Test Log / / ERCOT EDS 3 PM |  |  |  |
| References | TP: N/A | TNP: 6.5.9.2 |  |

### C5 - Contingency Plan procedures for Key Settlement and Financial Transfer Processes

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for the various Settlement and Financial processes that must be performed in order to settle the market in a timely manner. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has tested contingency Plan proceduress in place to overcome (in a timely manner) failures of key components of the Settlement and Billing System and Financial Transfer System. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency Plan procedures document for Settlement and Financial processes. Readiness will be achieved when the Settlement and Financial processes Contingency has been successfully tested. Settlement and Financial processes Contingency Plan procedures Exists Settlement and Financial processes Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Settlement and Financial processes Contingency Plan procedures / Settlement and Financial processes Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C6 - Develop Plan procedures for SE Failure

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for SE Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to maintain system reliability when the SE system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for SE failure. Readiness will be achieved when the SE Contingency has been successfully tested. SE Contingency Plan procedures Exists SE Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: SE Contingency Plan procedures / SE Contingency Plan procedures Test Log / / ERCOT EDS 2 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C7 - Contingency Plan procedures for a Backup Facility

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop Contingency Plan procedures for a Loss of the Primary Control Room. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT and QSEs have the ability to maintain control of the system when the Primary Control Room becomes unavailable. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for the Primary Control Room. Readiness will be achieved when the Primary Control Room Contingency has been successfully tested. Primary Control Room Contingency Plan procedures Exists Primary Control Room Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Primary Control Room Contingency Plan procedures / Primary Control Room Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C8 - Contingency Plan procedures for Portal/API Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop Contingency Plan procedures for a Portal/API Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to receive data from market participants when the API / Portal becomes unavailable. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for a API / Portal Failure. Readiness will be achieved when the API / Portal Contingency has been successfully tested. API / Portal Contingency Plan procedures Exists API / Portal Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: API/Portal Contingency Plan procedures / API/Portal Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C9 - Contingency Plan procedures for Site Unavailability

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test contingency Plan procedures for the event of normal site unavailability. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to facilitate the Nodal Market from the backup site. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for normal site unavailability. Readiness will be achieved when the normal site unavailability Contingency has been successfully tested. Normal site unavailability Contingency Plan procedures Exists Normal site unavailability Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Normal Site Unavailability Contingency Plan procedures / Normal Site Unavailability Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall test that a recovery to full functionality occurs for a single point of failure in EMS, MMS, NMMS and CRR and COMS applications. |  |  |  |
| Background: The intent of this metric is to ensure that systems functionality is not lost due to any single point of failure. |  |  |  |
| Criteria: The Readiness Team shall review documentation that ERCOT tested that a continuation of full functionality occurred during any single point of failure in EMS, MMS, NMMS and CRR and COMS applications. Readiness will be achieved when the Single Point of Failure test has been successfully executed. Single Point of Failure Test Plan procedures Exists Single Point of Failure Test Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Single Point of Failure Test Plan procedures / Single Point of Failure Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

# IMM Metrics

### IMM1 - Market Monitor Systems Capability

| Reported By: WEMM |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: EDS 4 – Release 9 Complete |  |  |  |
| Metric Description: Verify Market Monitor Systems Capability. |  |  |  |
| Background: The intent of this metric is to validate that the PUC Staff and the Wholesale Electric Market Monitor (WEMM) can access all data deemed necessary by the PUCT staff and IMM to perform their market oversite activities. |  |  |  |
| Criteria: The Readiness Team will receive notification from the WEMM that Market Monitor has sufficient staff, systems and access to data to successfully monitor the market. Readiness will be achieved when the Readiness Team receives notification that the Market Monitor is capable of fulfilling its intended purpose. Market Monitor and PUC Asserts Readiness |  |  |  |
| Reporting Data Sources: Letter of Assurance from the Market Monitor / ERCOT PMO PM |  |  |  |
| References | TP: N/A | TNP: 17.3 |  |

# Overall Readiness Metrics

### R0 – Market Participant Nodal Readiness Declaration

| Reported By: ERCOT/Market Particpants |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live less 120 days |  |  |  |
| Metric Description: Market Participants operate the nodal systems on a daily routine basis in parallel with the zonal market systems. |  |  |  |
| Background: The intent of this metric is to assure all systems and operations personnel at ERCOT and at Market Participant facilities are fully trainied and ready to operate in a Nodal environments. |  |  |  |
| Criteria: ERCOT will confirm the state of each Market Particpant’s readiness by observation of each MPs actions in the test environments of the nodal systems. ERCOT Asserts Readiness of Market Participants |  |  |  |
| Reporting Data Sources: PMO Dashboard / Readiness Metric Report |  |  |  |
| References | TP: 6.0 | TNP: N/A |  |

### R1 – ERCOT Nodal Readiness Declaration

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live less 60 days |  |  |  |
| Metric Description: ERCOT Declares the Texas Nodal Readiness State by assessing Program, ERCOT and Market Participant Readiness. |  |  |  |
| Background: The intent of this metric is to provide ERCOT stakeholders with a comprehensive statement of Market Readiness. |  |  |  |
| Criteria: ERCOT will confirm the state of Program Readiness through the PMO dashboard. ERCOT will confirm the state of ERCOT Readiness through assessment of the ERCOT related metrics. ERCOT will confirm the state of Market Participant Readiness through assessment of the MP related metrics. Readiness will be achieved when PMO state has been reported and ERCOT and MP related metric assessments have been completed. ERCOT Asserts Readiness TPTF, TAC and the ERCOT BOD approves Rediness Declaration |  |  |  |
| Reporting Data Sources: PMO Dashboard / Readiness Metric Report / ERCOT Nodal Program Executive Director |  |  |  |
| References | TP: 6.3 | TNP: N/A |  |

### R2 – Develop Texas Nodal Market Launch Plan

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 90 days |  |  |  |
| Metric Description: Develop Texas Nodal Market Launch Plan. |  |  |  |
| Background: The intent of this metric is to ensure that a comprehensive market launch plan exists. The plan will address the activities ERCOT and Market Participants must perform in order to launch the integrated nodal market. TPTF will develop the plan and TAC will approve. |  |  |  |
| Criteria: The Readiness Team will review documentation indicating that the Texas Nodal Market Launch plan has been created and approved by the TAC. Readiness will be achieved when a approved Texas Nodal Market Launch Plan has been published and ERCOT Market Participant communications verifies through voice communication that all Market Particpants are ready. Texas Nodal Market Launch Plan is Posted and communitated to all MarketParticipants |  |  |  |
| Reporting Data Sources: TN Market Launch Plan / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### R3 - 168-Hour System Stability Test and Trial Real Time Settlement

| Reported By: ERCOT |  |  | EDS: NA |
| --- | --- | --- | --- |
| Target Completion: 168 Hour Test Completion Milestone |  |  |  |
| Metric Description: ERCOT shall conduct a 168-hour systems stability test. The systems stability test will include the real time systems performing SCADA, Network Security Analysis, Transmission Constraint Management, SCED, RUC and LFC to operate without significant error for at least 168 continuous hours. On detection of any significant error of the operations systems (non-settlement), ERCOT and the Vendor will correct the problem and re-start the 168-Hour Test. ERCOT will conduct 7 consecutive Day Ahead Markets as part of the stability test. The test will verify the function of supporting systems and the ability of market participants to successfully participate in the test resulting in a DA Market solution and the generation of Settlement Determinants and that the DAM can be run concurrently with RT functions also operating during the test. ERCOT shall provide QSEs with test settlement statements for each Operating Day of the 168 Hour Test as defined in the detailed test plan. The test settlement statements for each Operating Day will use calculated dispatches and LMPs from SCED and actual meter data simulating actual settlement statements for real-time operations. QSEs shall review the test settlement statements for errors and provide feedback to ERCOT for resolution. ERCOT will work with Market Participants to resolve any settlements issues identified during the 168-Hour Test prior to beginning Real-Time Operations. |  |  |  |
| Background: The intent of this metric is to verify that NODAL systems can fully support ERCOT protocols in a stable computer system. |  |  |  |
| Criteria: The Readiness Team shall review documentation that DAM, SCADA, Network Security Analysis, Transmission Constraint Management, SCED, RUC and LFC operated without significant error for at least 168 continuous hours. Readiness will be achieved when the number of Over Load and Voltage limit alarms are equivalent to the number of actual Over Load and Voltage violations. Readiness will be achieved with the RTCA has been run for every element in system. Continuous operation >= 168 hours Number significant errors during continuous operation = 0 DAM Market Solves within the timeframe allowed = 100% Test RT and DAM settlement statements representing 168 hours of continuous operations per QSE = 7 Missing (critical) Settlement Determinants = 0 |  |  |  |
| Reporting Data Sources: ERCOT System Operations and Market Operations Staff DAM / RUC Daily Scorecard Comprised of: 1. DAM Market Solution Timestamp; 2. Missing Settlement Determinant Inventory Time stamped 3. Load of DAM Participants 4. Resolution of MP comments on test settlement statements 5. DAM and RUC Job Timestamps from Job Scheduler / RUC 1,2,3 Timestamps from Job Scheduler |  |  |  |
| References | TP: 6 | TNP: 5.4.9 |  |