## Slide 1: Transition Plan Network Operations Model Change Requests
5/26/2010

## Slide 2: Overview Transitioning Into the Nodal Network Model data submission timelines
Three Part Problem
  Single Entry Model
  Zonal vs Nodal Submission Deadlines
    Zonal timeline for Data Submissions
    Nodal timeline for Data Submissions
    Comparison of the Zonal and Nodal timeline differences
  Temporal Modeling in Nodal
Graduated Approach to the Nodal Timeline

## Slide 3
FACTOR #1
Zonal Network Model changes are
made by entering the changes first
in the Nodal Network Model Database
This is the SEM process

## Slide 4
TSPs
SRs
ERCOT
Zonal Model
TSPs
SRs
ERCOT
Zonal Model
NOMCRs
Nodal Model
TSPs
NOMCRs
ERCOT
Zonal Model
Nodal Model
SRs
TSPs
NOMCRs
ERCOT
Nodal Model
2000 – June 2009
Sep 2009 –Nodal Go-live
June 2009 – Sep 2009
Nodal Go-live
TODAY
Single Entry Model (SEM)
SEM

## Slide 5
FACTOR #2
Nodal and Zonal Timelines for data entry differ
greatly. Nodal Protocols require data
submitters to provide much more notice.

## Slide 6: Zonal timeline for Data Submissions
8.8 Coordination for System Topology Modifications
8.8.1 Coordination with ERCOT
Prior to energizing and placing into service any new or relocated Facility connected to the ERCOT Transmission Grid, TSPs shall coordinate with and receive approval from ERCOT.
8.8.2 Types of Work Requiring Coordination
TSPs shall coordinate with ERCOT the following types of work for any addition, replacement or modification to the ERCOT Transmission Grid:
  (1) Transmission lines forming part of the ERCOT Transmission Grid;
  (2) Equipment including circuit breakers, transformers, disconnects, reactive devices, and wave traps forming part of the Transmission Facility;
  (3) Resource interconnections; and
  (4) Protection and control schemes, including Remedial Action Plan (RAP), Supervisory Control And Data Acquisition, Energy Management System, AGC, or Special Protection Schemes (SPS).
8.8.2.1 TSP Information to be provided to ERCOT
The TSP shall notify ERCOT at least thirty (30) days before starting to energize or place into service any new or relocated Facility. The Notice shall be submitted in accordance with formats and procedures adopted by ERCOT and TSPs. For Notices involving co-owned, co-operated, or co-rated Transmission Facilities, the TSP submitting the initial Notice shall communicate with the other Market Participants responsible for co-owning, co-operating, or co-rating said Transmission Facilities prior to the Notice submittal. The Notice shall include the following information:
  (1) Proposed energize date;
  (2) TSP performing work;
  (3) TSP(s) responsible for rating affected transmission element(s);
  (4) Location Code if applicable (e.g. station code);
  (5) Identification of existing Transmission Facilities involved and new Transmission Facilities (if any) being added or existing Transmission Facilities being permanently removed from service;
  (6) Ratings of existing Transmission Facilities involved and new Transmission Facilities (if any) being added;
  (7) Outages required (clearly identify each Outage if multiple Outages are required), including sequence of Outage and estimate of Outage duration;
  (8) General statement of work to be completed with intermediate progress dates and events identified;
  (9) Supervisory Control and Data Acquisition modification work including descriptions of any new data telemetry points or changes to existing telemetry;
  (10) Additional data determined by ERCOT and TSP(s) as needed to complete the ERCOT model representation of existing Transmission Facilities involved and new Transmission Facilities (if any) being added;
  (11) Statement of completion, including:
  (a) Statement to be made at the completion of each intermediate stage of project; and
  (b) Statement to be made at completion of total project.
  (12) Drawings to be attached, including:
  (a) Existing status;
  (b) For each intermediate stage; and
  (c) Proposed completion of job.
8.8.2.2 Approval of the Work
On receipt of the information set forth in Section 8.8.2.1, TSP Information to be provided to ERCOT, ERCOT shall review the information and notify the TSP of any required modifications. ERCOT may, at its discretion, require changes to and more detail regarding the work for the procedure. The requesting TSP will consult with other Entities likely to be affected and will revise the work plan and Notice documentation, following any necessary or appropriate discussions with ERCOT and other affected Entities. ERCOT shall approve or reject the request, including any revisions made by the TSP, within fifteen (15) days of receipt. Following ERCOT approval, where appropriate, ERCOT shall publish a summary of the approved work on the MIS.
8.8.2.3 Changes to Work Approved by ERCOT
The TSP shall notify ERCOT and any other affected TSPs as soon as practicable of any requested changes to the work plan. ERCOT shall review and approve or reject changes to the work in accordance with Section 8.8, Coordination for System Topology Modifications.
8.8.2.4 Approval of Work Requiring Coordination
ERCOT shall maintain a record of all work approved in accordance with Section 8.8, Coordination for System Topology Modifications, and shall publish information on the MIS regarding each new Transmission Facility to be installed on the ERCOT Transmission Grid.

## Slide 7: Zonal timeline for Data Submissions
8.8.2.1 TSP Information to be provided to ERCOT
The TSP shall notify ERCOT at least thirty (30) days before starting to energize or place into service any new or relocated Facility. The Notice shall be submitted in accordance with formats and procedures adopted by ERCOT and TSPs. For Notices involving co-owned, co-operated, or co-rated Transmission Facilities, the TSP submitting the initial Notice shall communicate with the other Market Participants responsible for co-owning, co-operating, or co-rating said Transmission Facilities prior to the Notice submittal. The Notice shall include the following information:
8.8.2.2 Approval of the Work
On receipt of the information set forth in Section 8.8.2.1, TSP Information to be provided to ERCOT, ERCOT shall review the information and notify the TSP of any required modifications. ERCOT may, at its discretion, require changes to and more detail regarding the work for the procedure. The requesting TSP will consult with other Entities likely to be affected and will revise the work plan and Notice documentation, following any necessary or appropriate discussions with ERCOT and other affected Entities. ERCOT shall approve or reject the request, including any revisions made by the TSP, within fifteen (15) days of receipt. Following ERCOT approval, where appropriate, ERCOT shall publish a summary of the approved work on the MIS.
8.8.2.3 Changes to Work Approved by ERCOT
The TSP shall notify ERCOT and any other affected TSPs as soon as practicable of any requested changes to the work plan. ERCOT shall review and approve or reject changes to the work in accordance with Section 8.8, Coordination for System Topology Modifications.

## Slide 8: Zonal timeline for Data Submissions
Zonal Protocols Section 8
New Equipment Cutoff Date: 30 days
ERCOT Business Process Rules
Generation Cut-Off Date: ~21 days before the scheduled Zonal database load
Transmission Cut-Off Date: ~14 days before the scheduled Zonal database load
Telemetry Cut-Off Date: ~3 days before the scheduled Zonal database load

## Slide 9
Case Used in Production
Deadline for
Model Changes
2 weeks
Production
Validation
Network
Modeling
Validation
Resubmits
8 days
2 weeks
Typical Zonal Validation Timeline for
Model used in Production
3 days
2 days

## Slide 10: Nodal Timeline for Data Submissions
Initial Validation (ERCOT)
Market Validation (Market Participants)
Final Validation (ERCOT)
NOMCR Processing
CaseUsed in Production
Public
Posting
The Nodal “Life Cycle” for a model change
consists of 5 parts which are outlined in
Section 3.10 of the Nodal Protocols
Submission
Deadline
CRR
AUCTION

## Slide 11: Nodal Timeline for Data Submissions
Initial Validation (ERCOT)
Market Validation (Market Participants)
Final Validation (ERCOT)
NOMCR Processing
Cases Used in Production
Deadline for
Model Changes
Public
Posting
Deadline to Submit Information to ERCOT (15 days to Process NOMCRs) | Model Complete and Available for Test (posted to Market) | Updated Network Operations Model Testing Complete (Market testing complete) | Update Network Operations Model Production Environment | Target Physical Equipment In-Service Date
Jan 1 | Feb 15 | March 15 | April 1 | Month of April
Feb 1 | March 15 | April 15 | May 1 | Month of May
March 1 | April 15 | May 15 | June 1 | Months of June–August
June 1 | July 15 | August 15 | September 1 | Month of September
July 1 | August 15 | September 15 | October 1 | Month of October
August 1 | September 15 | October 15 | November 1 | Month of November
September 1 | October 15 | November 15 | December 1 | Month of December
October 1 | November 15 | December 15 | January 1 | Month of January
November 1 | December 15 | January 15 | February 1 | Month of February
December 1 | January 15 | February 15 | March 1 | Month of March
15
days
30
days
30
days
15
days
~ 7 days
Per case
Nodal Protocols Section 3.10.1

## Slide 12: Comparison of Zonal vs Nodal Notice Requirement for Model Change Requests
Case Used in Production
Resubmits
~ 14 days
Zonal
Initial Validation (ERCOT)
Market Validation (Market Participants)
Final Validation (ERCOT)
Case used in Prod
NOMCR Processing
30 days
30 days
15 days
15 days
~ 7 days
~ 90 days
Nodal
Production
Minimum Difference of 76 days
Could be up to 169 days for an August 31st change

## Slide 13
FACTOR #3
Nodal Network Modeling Database is Temporal
which allows modeling and sequencing of future
equipment (up to 1 year)
Zonal Modeling Database is always updated
for the next Model Load

## Slide 14: Temporal Modeling in Nodal
Nodal Network Model Database
(Historic Information)
Change 1
Change 1 + Change 2
Change 1 + Change 2+ Change 3
Change 1 +Change 2 + Change 3 + Change 4
Current day
Base Model + change 1
Base Model + Change 1,2,3
Zonal Network Model Database
(Historic Information)
All future
Changes
Base Model + all future changes
No future Models
Equivalent
Models

## Slide 15
How do we transition from Zonal to Nodal
while taking into account these three factors?

## Slide 16
Dec
Jan
Nov
Oct
Sep
Aug
July
Jun
Zonal
Process
Initial Validation (ERCOT)
Market Validation (Market Participants)
Final Validation (ERCOT)
NOMCR Processing
Cases Used in Production
Deadline for
Model Changes
Nodal
Production
Process
Public
Posting
The Problem with Continuing on Present Process

## Slide 17
Dec
Jan
Nov
Oct
Sep
Aug
July
Jun
Zonal
Process
Transition
Process
Initial Validation (ERCOT)
Market Validation (Market Participants)
Final Validation (ERCOT)
NOMCR Processing
Cases Used in Production
Deadline for
Model Changes
Nodal Go-Live
168-hr Testing
Nodal
Production
Process
Public
Posting
Transition Plan

## Slide 18
Transition Plan – Days of Notice Requirements

## Slide 19: Transition Plan – Interim Updates
Interim Updates during the Transition
Model change submissions that fall outside the Transition Period timeline will be subject to the Interim Update status as defined by the ERCOT Nodal Protocols. Per protocols Interim Updates are included in the model at the discretion of ERCOT and are reported to the PUCT and IMM. Given that section 3.10 of Nodal Protocols will not be activated until 9/1/2010, the Interim Update reports during the Transition Period will be distributed to the ERCOT Board of Directors for Review. The table below outlines the schedule and effective dates for the Interim Update Report.